## Infra EE4 Cases
Number | Created | Executor | Short description | Demand User | Priority-inactive | Account | State | Channel | EE4 Incident Number | Assignment group | Updated | Product module | Case type | Company
CS0215954 | 2026-06-03 14:17 |  | Enos Disconnected | Nitheesh NG | 3-Medium | Fourth_Partner_Tamil_Nadu_Ottapidaram | Open | EE4 Web Service | iCS20260603019 | Infrastructure Network | 2026-06-09 19:46 | Wind Monitoring & Control | Issue
CS0215490 | 2026-05-11 13:09 | Marimuthu | P-8003 Cleanmax-1 Babra Site Sanathali Cluster Reactive Power Not Controlled Through EMS | Vijay Kana Ratiya (Vijay Kana Ratiya) | 3-Medium | Cleanmax_Amreli_132MW_Motadevaliya | Open | EE4 Web Service | iCS20260511024 | Infrastructure Network | 2026-05-21 13:09 | Wind EMS | Issue
CS0215050 | 2026-04-15 15:18 | Mayur | Sprng Mulanur TN (P 1407), Fourth Partner Ottapidaram (P-8015), and Ayana Wankie GJ (P-1567) | Nitheesh NG | 3-Medium | India_Sprng_Mulanur_TN_PH1_52.8MW | Open | EE4 Web Service | iCS20260415024 | Infrastructure Network | 2026-05-18 22:58 | Wind SCADA | Issue
Universe tickets
Assigned to Infra

## Enos Public IP issue
Slno | Project Code | Case description | Status as on 03 -06-2026 | Infra Dependecies
1 | P-1610 | P1610 - pre-check failed | ILL down informed customer Restoration on or before 12th June | Yes
2 | P1429 | To be coordinated between EE, infra team and customer on: 1. Customer site network issue 2. Pre-check failed | ILL down informed customer | Yes

## Galileo
Slno | Project ID | Comments | Infra Dependecies
1 | P-8020 | Infrastructure completed VM import, Hongxia is deploying; pending Galileo deployment check | No
2 | P-1429 | Customer's public network inaccessible; follow-up with customer for troubleshooting in progress. | Yes
3 | P-1486 | Packet loss on customer's public network; follow-up with customer for troubleshooting in progress. | Yes
4 | P-1546 | Customer's public network inaccessible; follow-up with customer for troubleshooting in progress. | Yes
5 | P-8003 | STD has been remounted; 3*VMs can ping the external network. Infra to perform checklist + Galileo deployment check; these can be done in parallel. | No