## WAN IP Details
P-CODE | Month | Public ip | Gateway | Subnet
P-1615 | feb | 136.232.229.34 | 136.232.229.33 | 255.255.255.252
P-1429 | feb | 103.83.106.74 | 103.83.106.65 | 255.255.255.240
P-1707 | mar | 182.73.67.114 | 182.73.67.113 | 255.255.255.252
P-1873 | mar | 103.171.111.178 | 103.171.111.177 | 255.255.255.248
P-1748 | apr | 137.97.99.99 | 137.97.99.97 | 255.255.255.248
p-1427 | apr | 182.95.255.19 | 182.95.255.17 | 255.255.255.248
p-1631 | apr | 125.16.140.146 | 125.16.140.145 | 255.255.255.248
P-1846 | may | 182.95.184.53 | 182.95.184.54 | 255.255.255.252
P-1660 | apr | 172.10.15.2 | 172.10.15.1 | 255.255.255.0 | WAN 1
P-1741 | apr | 172.10.17.2 | 172.10.17.1 | 255.255.255.0 | WAN 1
p-1749 | may | 122.187.209.10 | 122.187.209.9 | 255.255.255.248
p-1811 | may | 103.178.159.75 | 103.178.159.75 | 255.255.255.248
p-1731 | june | 152.52.160.211 | 152.52.160.209 | 255.255.255.248
p-1729 | july | 139.167.153.61 | 139.167.153.57 | 255.255.255.248
P-1799 | July | 125.17.8.114 | 125.17.8.113 | 255.255.255.248
P-1886 | June | 103.197.222.179 | 103.197.222.177 | 255.255.255.248
P-1653 | July | 136.233.147.114 | 136.233.147.113 | 255.255.255.248
P-1897 | July | 125.16.57.219 | 125.16.57.217 | 255.255.255.248
P-1750 | June | 128.185.183.112 | 128.185.183.113 | 255.255.255.248 | Extranet communication is not working.
P-1812 | may | 103.197.222.165 | 103.197.222.161 | 255.255.255.248
P-1566 | may | 59.145.110.194 | 59.145.110.193 | 255.255.255.248
p-2022 | sep | 125.22.234.181 | 125.22.234.177 | 255.255.255.248
p-1945 | sep | 182.71.77.130 | 182.71.77.129 | 255.255.255.248
p-1665 | Aug | 172.30.47.251 | 172.30.47.254 | 255.255.254.0

## Project implementation
No | Project number | Project name | Priority Wise | Project Manager | Network Engineer | Server Engineer | Plan start date | BOM | Jump server Installation | Radius Server | Wiring | Network | Server | Time | Galileo Deployment with checklist | Remark | Additonal Rremarks
1 | P-1741 | Sprng MP | Completed | shaym lal | Shadab.pinitod | Mayur Tisage | 2026-05-30 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | HA
2 | P-1873 | Cleanmax Vagasiya | Completed | Muruganthan | Ashok | Mayur Tisage | 2026-05-30 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | HA
3 | P-1811 | JSW Dharapuram | Completed | Kalimuthu | Ashok | Marimuthu | 2026-05-30 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | HA
4 | P-1631 | Re Infra Karur | Completed | Kalimuthu | Ashok | Marimuthu | 2026-07-15 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | HA
5 | P-1748 | Juniper_Kamlapur | Completed | Naresh/Sunil | Ashok | Mayur Tisage | 2026-05-25 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | HA
6 | P-1707 | Welspun GJ | Completed | Neharu/Arpit | Shadab.pinitod | Mayur Tisage | 2026-05-31 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | Old
7 | P-1429 | JSW Omeraga | Completed | Ashish Jade | Shadab.pinitod | Mayur Tisage | 2026-04-17 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | Old
8 | P-1660 | Spring Phase03 | Completed | shaym lal | Shadab.pinitod | Marimuthu | 2026-05-30 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | Old
9 | P-1427 | Vibrent MP | Completed | Lokendra Dayma | Shadab.pinitod | Marimuthu | 2026-07-15 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | Old | Both Scada everything is done and EMS alredy done but version is latesr vesrion 22.4.5 so we have change the EMS OS version 22.4.4 version still working on it
10 | P-1812 | Opera Jamnagar Scad | Completed | Mukesh Mondal | Shadab.pinitod | Mayur Tisage | 2026-05-30 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | HA | Core Switch 2 failure Shadab Working on this
11 | P-1846 | Juniper_hybrid | Completed | Sunil Rathod | Ashok | Mayur Tisage | 2026-05-30 | Completed | Completed | Completed | Completed | Completed | Completed | Completed
12 | P-1749 | Neelanga MH | Completed | Ramakrishnan G | Ashok | Mayur Tisage | 2026-05-25 | Completed | Completed | Completed | Completed | Completed | Completed | Completed
13 | p-1566 | Serentica solapur | Completed | Ramakrishnan G | Shadab.pinitod | Mayur Tisage | 2026-07-15 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | Old | Core switch 4 failiure Ashok working on this
14 | P-1897 | Renew Solapur Phase 2 | Completed | Rahul Tiwari | Shadab.pinitod | Mayur Tisage | 2026-07-15 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | Two firewall checkpoint issues. HA Issue
15 | P-1731 | Renew Gooty | Completed | Suthan M | Ashok | Marimuthu | 2026-08-28 | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  |  | Server end evething is done only for customer end internet issue going on
16 | P-1729 | Serentica Koppal | Completed | Praveen | Ashok | Marimuthu | 2026-07-15 | Completed | Completed | Completed | Completed | Completed | Completed | Completed
17 | P-1750 | Juniper Chappelgoan | Completed | Ramakrishnan G | Shadab.pinitod | Mayur Tisage | 30.06-2026 | Completed | Completed | Completed | Completed | Completed | Completed
18 | P-1653 | Torrent Bhatiya NS | Completed | Sangappa | Shadab.pinitod | Marimuthu | 2026-08-31 | Completed | Completed | Completed | Completed | Completed | Completed | Completed
19 | P-1886 | Cleanmax kalinkanger | Completed | Thilak | Shadab.pinitod | Marimuthu | 2026-07-15 | Completed | Completed | Completed | Completed | Completed | Completed | Completed
20 | P-1747 | Cleanmax Gadag | Completed |  | Shadab.pinitod | Marimuthu | 2026-08-31 | Completed | Under implementation | Under implementation | Completed | Completed | Completed | Completed | Completed | From Zone1 Time server is not reachble
21 | P-1565 | Serentica Kallam | ROW | Sarita | Shadab.pinitod | Mayur Tisage | 2026-07-15 | Completed | Under implementation | Under implementation | Completed | Under implementation | Under implementation | Under implementation |  | ROW
22 | P-2022 | Cleanmax _Rajula | 1 | Manoj Kewat | Ashok | Mayur Tisage | 30.09.2026 | Completed |  | Completed | Completed | Completed | Completed | Completed |  | PPC<EMS & Gallielo is pending
63 | P-1856 | Prozeal | 1 |  | Shadab.pinitod | Mayur Tisage | 2026-08-31 | Completed |  |  | Completed | Completed | Under implementation
45 | P-1746 | Blupine Alanda | 2 | Niyasdeen | Shadab.pinitod | Mayur Tisage | 2026-07-30 | Completed |  |  | Completed | Completed | Completed | Completed |  | Galileo Pending
57 | P-1752 | Blupine Alanda | 1 | Niyasdeen | Shadab.pinitod | Marimuthu | 2026-08-31 | Completed |  |  | Completed | Completed
23 | P-1546 | JSW |  |  |  |  | 2026-01-05
24 | P-1962 | Forth Partner Karur | Completed |  | Ashok | Mayur Tisage | 2026-07-30 | Completed | Under implementation | Under implementation | Completed | Completed | Completed | Completed
25 | P-1843 | Fourth Partner Amerli |  |  |  |  | 2026-02-15
26 | P-1725 | Cleanmax Gujarat |  |  |  |  | 2026-02-25
27 | P-1587 | India Heo Kurnool | Completed | Sarita | Shadab.pinitod | Mayur Tisage | 2026-07-27 | Completed | Under implementation | Under implementation | Completed | Completed | Completed | Completed
28 | P-3599 | Serentica |  | Sarita |  |  | 2026-03-30
29 | P-1578 | Torrent |  | Sarita |  |  | 2026-05-21
30 | P-1615 | NSL Power |  | Niyasdeen |  |  | 2026-05-25
31 | P-1610 | Juniper ph1 |  | Sarita |  |  | 2026-06-29
32 | P-1799 | Vena Energy | Completed | Niyasdeen | Shadab.pinitod | Mayur Tisage | 2026-07-27 | Completed | Under implementation | Under implementation | Completed | Completed | Completed | Completed
33 | P-1704 | India Ayana Sudil KA |  | Harie Vignesh |  |  | 2026-07-06
34 | P-1689 | IndiaHero Wind Energy |  |  |  |  | 2026-07-15
35 | P-1887 | Cleanmax Aji Diser | Completed |  | Shadab.pinitod | Mayur Tisage | 2026-07-15 | Completed | Under implementation | Under implementation | Completed | Completed | Completed | Completed
36 | P-1588 | Hero Future Kurnool | Completed | Sangappa | Shadab.pinitod | Mayur Tisage | 2026-07-27 | Completed | Under implementation | Under implementation | Completed | Completed | Completed | Completed
37 | P-1945 | Cleanmax Gadag | Completed |  | Ashok | Marimuthu | 2026-07-15 | Completed |  |  | Completed | Completed | Completed | Completed | Completed
38 | P-1888 | Cleanmax Theni |  |  |  |  | 2026-07-27
39 | P-1937 | Serentica Gadag |  | Abdullah |  |  | 2026-07-27
40 | P-1683 | CIP Hatalageri |  | Niyasdeen |  |  | 2026-07-27
41 | P-1687 | India Heo Kurnool |  | Sangappa |  |  | 2026-07-27
42 | P-1848 | Juniper Hybrid |  | Harie Vignesh |  |  | 2026-07-27
43 | P-1887 | Cleanmax Aji Diser |  |  |  |  | 2026-07-27
44 | P-1897 | Renew Solapur |  |  | Shadab.pinitod | Marimuthu | 2026-07-30 | Completed | Completed | Completed | Completed | Completed | Completed | Completed
46 | P-1934 | Aditya Birla RJ |  |  |  |  | 2026-07-31
47 | P-1665 | Ayana AP |  | Sarita | Ashok | Marimuthu | 2026-08-04 | Completed | Under implementation | Under implementation | Completed | completed | Completed | Completed |  | Awaiting for the material
48 | P-1719 | Ayana Kurnool |  |  | Ashok | Marimuthu | 2026-08-07 | Completed | Under implementation | Under implementation | Completed | Under implementation | Under implementation | Under implementation |  | Non started
49 | P-1717 | Ayana Kurnool |  |  |  |  | 2026-08-07
50 | P-1718 | Ayana Sudi |  |  |  |  | 2026-08-07
51 | P-1708 | Ayana Sudi |  |  |  |  | 2026-08-07
52 | P-1744 | Aditya Sheo |  | Sarita |  |  | 2026-08-15
53 | P-1589 | Hero Gadag |  |  |  |  | 2026-08-17
54 | P-1732 | Tuljapur |  | Abdullah |  |  | 2026-08-30
55 | P-1829 | Juniper PH1 NS |  | Sarita |  |  | 2026-08-30
56 | P-1912 | India Ampin |  | Niyasdeen |  |  | 2026-08-30
58 | P-1555 | Blupine Mahadeva |  | Niyasdeen |  |  | 2026-08-31
59 | P-1701 | Cleanmax Honavad |  | Niyasdeen |  |  | 2026-08-31
60 | P-1630 | Torrent Phase 2 NS |  | Abdullah |  |  | 2026-08-31
61 | P-1702 | Cleanmax Kolhapur |  | Harie Vignesh |  |  | 2026-08-31
62 | P-1734 | Torrent Beed |  |  |  |  | 2026-08-31
64 | P-1955 | Prozeal PH2 |  |  |  |  | 2026-08-31
65 | P-1568 | Opera Jamnagr |  |  |  |  | 2026-09-28
66 | P-1569 | Opera Dwaraka |  |  |  |  | 2026-09-28
67 | P-1611 | Juniper |  | Harie Vignesh |  |  | 2026-10-05
68 | P-1735 | Torrent2 new project |  |  |  |  | 2026-10-12
69 | P-1796 | Bijapur |  |  |  |  | 2026-11-01
70 | P-1879 | Cleanmax Guntu and Nandhagiri |  |  |  |  | 2026-11-01
71 | P-1922 | Everen_Kurnool 1 |  |  |  |  | 2026-11-01
72 | P-1858 | Renew Runija |  |  |  |  | 2026-11-13
73 | P-1636 | Blupine NHPC |  |  |  |  | 2026-12-01
74 | P-1900 | Purva AP |  |  |  |  | 2026-12-01
| K-0299 |  |  |  | Ashok |  | 2026-07-10 | Completed
| k-0314 |  |  |  | Ashok |  | 2026-08-01 | Completed
| K-0324 |  |  |  | Ashok |  | 2026-08-03 | Completed
| k-0334 |  |  |  | Ashok |  | 2026-08-22 | Completed
| k-0409 |  |  |  | Ashok |  | 2026-10-14
| k-0410 |  |  |  | Ashok |  | 2026-10-14
Note on E24: Qiang Wang(Outsourcing):

## Galielo Auto Start
P-code | Current Status | Action taken | Changes by | Date | Remarks | P-Code | Site | Oenwer | laptop | Remarks
1528 | Powered off |  |  |  | Applicable for all servers | P-1429 |  | Shrishail Hande( | Laptop 01
8014 | Powered off |  |  |  |  | P-1546 |  | Shailesh Makvana | Laptop 02
8012 | Powered off |  |  |  |  | P-1741 |  | Yashraj Shukla | Laptop 03
1478 | Powered off |  |  |  |  | P-1873 |  | Navin Bhute | Laptop 04
1567 | Powered off
8173 | Powered off
1480 | Powered off | Powered ON |  | 2026-08-31 | Applicable for all servers

## CASE processing
Project Code | Case number | Filled_Date | First engineer(India Team) | Second engineer(China Team) | Case description | Requester | Priority | start date | Problem classification | end time | Status | Close Summary | Current Summary | Hardware Issue or not | Failed Hardware (Disk, Memory, etc.) | Damaged Number | Case Summary to OneNote ？
P-1451 | CS0212968 | 2026-01-15 | qiang.wang |  | India_JSW_Sandur_PH1_KA_191.4MW 伽利略一区到二区通讯异常导致数据无法上云 | 袁天翔 | Low | 2026-01-15 | Firewall configuration | 2026-01-21 | Closed | Pubilc IP internet access issue, closed ticket
| CS0212916 | 2026-01-14 | qiang.wang |  | P3599, P1511, P1725, P1546 - cannot ping Edge and zone 2 firewall from SCADA1 (refer below for clearer descriptions) | AARON LEE WENG HOE | Low | 2026-01-14 | New requirements | 2026-02-26 | Closed
P-8022 | CS0212087 | 2026-01-19 | Ashok |  | JSW Sandur - KA P-8022 disconnected from Enos last one month-ENOS | Avinash Kunder | Low | 2026-01-19 | Firewall configuration | 2026-01-29 | Closed | Pubilc IP internet access issue, closed ticket
P-8003 | CS0213144 | 2026-01-19 | Ashok |  | Clean max Amreli GJ (P-8003) out of 59 WTG 40 WTG disconnected in ENOS | Nagaraj Murugan | Low | 2026-01-19 | Firewall configuration | 2026-01-29 | Closed | public IP issue
P-1466 | CS0213226 | 2025-12-25 |  |  | backup port needs to be assigned on the third-party firewall to the Siemens gateway for EMS and WTG data access. | Sanjay D Chalke | Low | 2025-12-25 | Firewall configuration | 2026-02-09 | Closed
P-1478 | CS0212249 | 2026-01-16 | Ashok |  | P-1478 Site Need to Connect in EnOs |  | Low | 2026-01-16 | public network problem | 2026-01-15 | Closed | There is a problem with the owner's network. ping8.8.8.8 loses packets
P-8003 | CS0213305 | 2026-01-02 | qiang.wang |  | P-8003, PSS - Babra, In EMS Reactive power not controlled as per grid dispatch | Parth Maheta | Low | 2026-01-02 | Firewall configuration | 2026-01-15 | Closed | There is a problem with the owner's network. ping8.8.8.8 loses packets
P-3598 | CS0212613 | 2025-11-24 |  |  | P-3598 Fourth partner Kudligi-KA Disconnected in ENOS | Avinash Kunder | Low | 2025-11-24 | Firewall configuration | 2026-01-29 | Closed | Pubilc IP internet access issue, closed ticket
| CS0212914 | 2026-01-15 | qiang.wang |  | P1721, P1453, P8004 no Edge server installed | AARON LEE WENG HOE | Low | 2026-01-15 | New requirements | 2026-01-19 | Closed | The total 3 sites all finished the Edge installation and conf and tested is normall
P-1632 | CS0213505 | 2026-01-16 | qiang.wang |  | 印度P-1632回传数据自12.23日中断，检查发现二区data机器无法ping通S3地址 |  | Low | 2026-01-16 | Firewall configuration | 2026-01-19 | Closed
P-1528 |  | 2026-01-20 | Ashok |  | ring loop issue | ankit meena | Low | 2026-01-20 | ring switch config issue | 2026-01-23 | Closed | complete
P-8020 |  | 2026-01-19 | Ashok |  | public ip were down |  | Low | 2026-01-19 | public network problem | 2026-01-19 | Closed | Restored /There is a problem with the owner's network. ping8.8.8.8 loses packets
p-1843 |  | 2026-01-20 | Ashok |  | public ip were down |  | Low | 2026-01-20 | public network problem | 2026-01-20 | Closed | Restored /There is a problem with the owner's network. ping8.8.8.8 loses packets
p-3598 |  | 2026-01-20 | Shadab.pinitod |  | Dataforwording | Praveenkumar Elango | Low | 2026-01-20 | New requirements | 2026-01-20 | Closed | need add route informed software team
P-IN01 |  | 2026-01-20 | Ashok |  | syslog synchronize on firewall | nitheesh ng | Low | 2026-01-20 | New requirements | 2026-01-20 | Closed | completed
p-8003 |  | 2026-01-20 | Ashok |  | public ip issue,opc ua forwording issue | Parth Maheta | Low | 2026-01-20 | Firewall configuration | 2026-01-20 | Closed | completed
p-8022 |  |  | Ashok |  | public ip issue | arjun akki | Low |  | Firewall configuration | 2026-01-21 | Closed | 8.8.8.8 working public ip issue resolved
P-1480 | CS0213592 | 2026-01-21 | qiang.wang |  | 1480机器ping伽利略机器不通，需要架构支持 | can.song | Low | 2026-01-21 | Firewall configuration | 2026-01-22 | Closed | 已远程处理，修复问题。
P-1528 | CS0213643 | 2026-01-20 | Ashok |  | P-1528_Turbine scada connectvity Ring loop is not connected | ankit meena | Low | 2026-01-20 | New requirements | 2026-01-23 | Closed | all the ring master switch configuration completed and mapping aslo done need to check ofc cable laying at site level
P-1453 |  | 2026-01-27 | Ashok |  | p-1453 public ip down | nitheesh ng | Low | 2026-01-27 | Firewall configuration | 2026-02-12 | Closed | public ip working fine
P-1436 |  | 2026-01-27 | Ashok |  | p-1436 public ip down | nitheesh ng | Low | 2026-01-27 | Firewall configuration | 2026-03-18 | Closed | extranet communication is okay
P-8023 | CS0213671 | 2026-01-26 | qiang.wang |  | India_Project Twelve_Ayana_Amerli_GJ_141.9MW 伽利略一二区通讯异常数据无法上云 | yuantianxiang | Low | 2026-01-26 | Firewall configuration | ongoing | Closed | Power PSU failed need replace
P-1486 | CS0213775 | 2026-02-03 | Marimuthu |  | P-1486-Zone-1 and Zone-2 IP addresses are not reachable. | Shailesh Makvana | Low | 2026-02-03 | Firewall configuration | 2026-02-06 | Closed | PCI Express device caused a fatal hardware error |  | Motherboard PCIe slot issue hardware issue | Motherboard PCIe slot issue,Faulty RAID / storage controller and Faulty NIC or PCIe card | 3 | The power was interrupted, which caused the problem. The server was already running on a single power card, which led to PCI overheating, and the server stopped working. After removing the power card and shutting down the server for 2 hours, we reinserted the power card and checked the status the server was up. However, after monitoring for 1 week, the issue occurred again because the logs already indicated a PCI fault, and the server kept crashing. Therefore, the hardware needs to be replaced. Now the same issue has occurred again, and the server must be replaced. | Unders ubservation
P-3598 | iCS20260203026 | 2026-02-03 | Ashok |  | P-1486-Zone-1 and Zone-2 IP addresses are not reachable. | abhijith | Low | 2026-02-03 | Firewall configuration | 2026-02-03 | Closed | issue resolved only single host route were added
P-1429 |  | 2026-03-17 | Mayur Tisage |  | Reinstallation of correct Ubantu OS Version completed for EMS servers | Sarita | Low | 2026-03-17 | New requirements | 2026-03-17 | Closed | issue resolved.
P-1725 |  | 2026-03-18 | Mayur Tisage |  | Time Synchronization issue in EMS Servers | Abdullah | Low | 2026-03-18 | Network cabe connection error | 2026-03-18 | Closed | issue resolved.
P-1725 |  | 2026-03-18 | Mayur Tisage |  | SSH not Enabled in Scada Servers | Abdullah | Low | 2026-03-18 |  | 2026-03-18 | Closed | issue resolved.
P-8003 | CS0214309 | 2026-03-05 | qiang.wang |  | P-8003 Cleanmax Amereli -GJ -49 turbines disconnected in ENOS | Avinash Kunder | Low | 2026-03-05 | Firewall configuration | 2026-03-27 | Closed | Public IP changed and fixed
P-8016 | CS0214490 | 2026-03-12 | qiang.wang |  | P-8016/ SCADA disconnected/ ANB-142,190,201&232 | Abhishek Gangadharaiah | Low | 2026-03-12 | Firewall configuration | 2026-03-27 | Closed | Public IP changed and fixed
P-8016/8013 | CS0214249 | 2026-03-25 | qiang.wang |  | p-8016/8013 scada can not ping S3 |  | Low | 2026-03-25 | Firewall configuration | 2026-03-25 | Closed | Scada server not setting DNS (/etc/resolv.conf --> nameserver = 8.8.8.8 )
P-3598 | CS0213899 | 2026-03-12 | qiang.wang |  | Resolution for SCADA connectivity issue -ENOS-P-3598 | Avinash Kunder | Low | 2026-03-12 | Firewall configuration | 2026-03-31 | Closed | issue resolved only single host route were added
P-1436 | CS0214486 | 2026-03-12 | Mayur Tisage |  | P-1436 Blupine Mahadev Scada OS 2nd IP Not Working | Sanjay Kachhela (sanjay kachhela) | Low | 2026-03-12 | Firewall configuration | 2026-04-02 | Closed
p-8002 |  | 2018-03-16 | Ashok |  | pqm dataforwoding port number checkup | sarita suresh | Low | 2018-03-16 | Firewall configuration | 2026-03-16 | Closed | issue resolved port 502 added
P-1436 |  | 2026-03-16 | Ashok |  | cutomer public ip changed | Sanjay Kachhela (sanjay kachhela) | Low | 2026-03-16 | Firewall configuration | 2026-03-16 | Closed | extranet now working fine
bess scada |  | 2026-03-19 | Ashok |  | data forwording requirements | mantri | Low | 2026-03-19 | Firewall configuration | 2026-03-19 | Closed | new requirements
P-1486 |  | 2026-03-23 | Marimuthu |  | DATA server unable reach | song zhenyang | Low | 2026-03-23 | Server crash | 2026-03-23 | Closed | A power log was generated because the server was running on a single power supply. The site team was asked to connect the second power supply. After restarting the server and clearing the log, the server is now up and running. The issue is resolved.
P-3599 |  | 2026-03-23 | Mayur Tisage |  | 3 Servers File system Failure | sarita suresh | Low | 2026-03-23 | Server crash | 2026-03-23 | Closed | Repaired the files system and restored the servers.
P-8001 |  | 2026-03-18 | Marimuthu |  | Scada BE 1 and EMS 26 and 27 not rechable | sarita suresh | Low | 2026-03-18 | Network cabe connection error | 2026-03-23 | Closed | Scada BE 1Server is hang mode and EMs system network cable connectivity issue now both server and system working fine issue reslved.
P-1451/8022 |  | 2026-03-23 | Ashok |  | inside frewall not reachable from network | thirupathi | Low | 2026-03-23 | Network cabe connection error | 2026-03-23 | Closed | identifed that wan1 cable inside firewall disconnected
P-1578 |  | 2026-03-20 | Ashok |  | EMS TO MPPC data forwording | sarita suresh | Low | 2026-03-20 | Firewall configuration | 2026-03-24 | Closed | completed
P-1578 |  | 2026-03-20 | Ashok |  | scada to OPC data forwording | sarita suresh | Low | 2026-03-20 | Firewall configuration | 2026-03-24 | Closed | completed
P-1578 |  | 2026-03-20 | Ashok |  | scada to WRLDC data forwording | sarita suresh | Low | 2026-03-20 | Firewall configuration | 2026-03-24 | Closed | completed
P-1511 |  | 2026-03-24 | Marimuthu |  | P1511 APP server is able to ping but unable to access the server, please help to look into this | Aaron Lee | Low | 2026-03-24 | Galileo APP Server pinging but not connecting SSH | 27-04-2026 | Closed | Issue resolved Pre check list everything is completed | Issue resolved Pre check list everything is completed
P-1615 |  | 2026-03-24 | Ashok |  | scada to OPC data forwording | Harie | Low | 2026-03-24 | Firewall configuration | 2026-03-24 | Closed | completed
P-1429 |  | 2026-03-24 | Ashok |  | scada to OPC data forwording | sagappa | Low | 2026-03-24 | Firewall configuration | 2026-03-25 | Closed | third-party firewall hardware failure need to replace the firewall
P-1429 |  | 2026-03-24 | Ashok |  | scada to WRLDC data forwording | sagappa | Low | 2026-03-24 | Firewall configuration | 2026-03-25 | Closed | third-party firewall hardware failure need to replace the firewall
P-1429 |  | 2026-03-24 | Ashok |  | EMS TO MPPC data forwording | sagappa | Low | 2026-03-24 | Firewall configuration | 2026-03-25 | Closed | third-party firewall hardware failure need to replace the firewall
p-1578 |  | 2026-03-24 | Ashok |  | EMS server 2 were un reachable | ashok | Low | 2026-03-24 | Server crash | 2026-03-24 | Closed | after power reboot it resolved
P-1610 |  | 2026-03-19 | Mayur Tisage |  | Reinstallation of correct ubantu version in EMS Servers | sarita suresh | Low | 2026-03-19 | New requirements | 2026-03-30 | Closed | Installation Completed
P-3599 |  | 2026-03-25 | Marimuthu |  | EMS 3 and EMS 4 not working | sarita suresh | Low | 2026-03-25 | Network cabe connection error | 2026-03-25 | Closed | EMS 3, EMS 4, and PPC 2 were not reachable from the desktop. Tested from a laptop (Zone 1) and found reachable. Issue was with desktop LAN cable. Cable replaced, now all servers are working fine
P-1567 |  | 2026-03-25 | Marimuthu |  | WTG data server not reachable | thirupathi | Low | 2026-03-25 | Server crash | 2026-03-25 | Closed | Power log issue and ROW issue going
p-8004 |  | 2026-03-25 | Ashok |  | opc_ua data issue | ravi | Low | 2026-03-25 | Firewall configuration | 2026-03-25 | Closed | opc data is okay configure port 5
P-1615 |  | 2026-03-25 | Ashok |  | scada_gw1 data forwording | Harie | Low | 2026-03-25 | Firewall configuration | 2026-03-25 | Closed | need to test site team awaiting for site team support
P-1615 |  | 2026-03-25 | Ashok |  | scada_gw2 data forwording | Harie | Low | 2026-03-25 | Firewall configuration | 2026-03-25 | Closed | need to test site team awaiting for site team support
p-3599 |  | 2026-03-25 | Ashok |  | data forwoding issue | Ravi | Low | 2026-03-25 | Firewall configuration | 2026-03-25 | Closed | third-party firewall hardware failure need to replace the firewall
P-1436 |  | 2026-03-25 | Marimuthu |  | Install Zone2 data server |  | Low | 2026-03-25 | Server crash |  | Closed | New server need install data server
P-1546 |  | 2026-03-26 | Marimuthu |  | 528 | sarita suresh | Low | 2026-03-26 | check the IST time issue and Data server IP reachability | On going | Closed | Site end laptop is not avalable i asked to site person he will be arrrange
P-1586 |  | 2026-03-26 | Ashok |  | public ip issue | thirupathi | Low | 2026-03-26 | Firewall configuration | 2026-03-26 | Closed | working fine
p-8004 |  | 2026-03-26 | Ashok |  | edge synchronous issue | nitheesh | Low | 2026-03-26 | Firewall configuration | 2026-03-26 | Closed | extranet now working fine
P-1453 |  | 2026-03-26 | Ashok |  | edge synchronous issue | nitheesh | Low | 2026-03-26 | Firewall configuration | 2026-03-26 | Closed | extranet now working fine
P-8012 |  | 2026-03-26 | qiang.wang |  | 8012_AMP_Energy_Jamanagar 伽利略虚机对时问题导致伽利略数据无法上云 | yuantianxiang | Low | 2026-03-26 | timeserver | 2026-03-30 | Closed
P-8003 |  | 2026-03-27 | Tao.li |  | EMS not working | Cleanmax Site | Low | 2026-03-27 | server problem | 2026-03-27 | Closed | Restart server recovery
p-8004 | CS0214605 | 2026-03-20 | Ashok |  | P8004 Renew Customer OPC Data issue (Renew4patoda site ) | Vasudev Suryavanshi (vasudev suryavanshi) | Low | 2026-03-20 | New requirements | 2026-03-22 | Closed | cable wrong connectivity
p-3599 |  |  | Mayur Tisage |  | Scada BE 1 Server Motherboard issue, New server installation | nitheesh | Low |  |  |  | Closed | Pending
P-1546 |  | 2026-03-27 | yuan.qin |  | Time server's issue, the gps cable was removed by customer | Mayur Tisage | Low | 2026-03-27 | Network cabe connection error | 2026-03-27 | Closed | extranet now working fine
P-1429 |  | 2026-03-27 | Mayur Tisage |  | Scada Laptop showing compatibility error while opening internet browsers | Nikhil Soni | Low | 2026-03-27 | Network cabe connection error | 2026-03-27 | Closed | Sementic Antivirus Application issue, removed it from laptop, issue resolved.
P-1610 |  | 2026-03-18 | jun.zhang |  | PA firewall system crash | shadab | Low | 2026-03-18 | Server crash | 2026-03-19 | Closed | Enter maintenance mode to restore the system
p-1429 |  | 2026-03-26 | jun.zhang |  | PA firewall system crash | Ashok | Low | 2026-03-26 | Server crash | 2026-04-02 | Closed
p-3599 |  | 2026-03-26 | jun.zhang |  | PA firewall system crash | Ashok | Low | 2026-03-26 | Server crash | 2026-04-02 | Closed
p-8015 |  | 2026-03-26 | jun.zhang |  | The VPN tunnel is down | Jiuding Wang | Low | 2026-03-26 | Network cabe connection error | 2026-04-02 | Closed
P-1615 |  | 2026-03-27 | qiang.wang |  | MPPC_EMS data forwarding | Harie Vignesh | Low | 2026-03-27 | New requirements | 2026-03-27 | Closed | Created MPPC_EMS&2, EMS_MPPC&2 Firewall policy and NAT policy vbia LAN 6,port 5020 from EMS 1&2 both open
P-1429 |  | 2026-03-27 | Ashok |  | Re-configuration | nikhil soni | Low | 2026-03-27 | Firewall configuration | 2026-03-27 | Closed | restared and intial debugging is completed
P-3599 |  | 2026-03-27 | Ashok |  | Re-configuration | pawan | Low | 2026-03-27 | Firewall configuration | 2026-03-27 | Closed | restared and intial debugging is completed
P-1436 | CS0214486 | 2026-03-19 | qiang.wang |  | P-1436 Blupine Mahadev Scada OS 2nd IP Not Working | Sanjay Kachhela (sanjay kachhela) | Low | 2026-03-19 |  |  | Closed
p-1528 | CS0214657 |  | jun.zhang |  | P-1528_Scada Ring not working | Sajulal Kumawat | Low |  |  |  | Closed
P-8012 | CS0214713 | 2026-03-26 | qiang.wang |  | AMP_Energy_Jamanagar Gailileo data time issue unable upload Gaililieo data to cloud | yuantianxiang | Low | 2026-03-26 |  | 2026-03-31 | Closed | Time issue fixed by remote, closed ticket
P-8015 | CS0214770 | 2026-03-30 | qiang.wang |  | AMP_Energy_Jamanagar Gailileo data time issue unable upload Gaililieo data to cloud | yuantianxiang | Low | 2026-03-30 |  | 2026-03-31 | Closed
P-1567 |  | 2026-03-31 | Marimuthu |  | WTG health front server issue not resolved |  | Low | 2026-03-31 | Network cabe connection error |  | Closed | Working on it inprogress
p-1429 |  | 2026-03-26 | Ashok |  | wrldc data forwoding | sangappa | Low | 2026-03-26 | Firewall configuration | 2026-03-30 | Closed | firewall new requirements
p-1429 |  | 2026-03-27 | Ashok |  | opc dataforwording | sangappa | Low | 2026-03-27 | Firewall configuration | 2026-03-30 | Closed | firewall new requirements
p-1429 |  | 2026-03-26 | Ashok |  | mppc dataforwording | sangappa | Low | 2026-03-26 | Firewall configuration | 2026-03-30 | Closed | firewall new requirements
p-8015 |  | 2026-03-30 | Ashok |  | public ip modification | praveen | Low | 2026-03-30 | Firewall configuration | 2026-03-30 | Closed | firewall new requirements
p-1725 |  | 2026-04-22 | Ashok |  | data forwoding requirements | abdulla | Low | 2026-04-22 | Firewall configuration | 2026-04-01 | Closed | need to test waiting for site assistance
p-1731 |  | 2026-04-01 | Mayur Tisage |  | internet is blocked due to semantic | Shoyab billari | Low | 2026-04-01 | Network cabe connection error | 2026-04-01 | Closed | Issue resolved
P-3359 |  | 2026-03-25 | yuan.qin |  | PPC bridge can not pinging | Mayur Tisage | Low | 2026-03-25 | Server crash | 2026-04-21 | Closed | The route of PPC2 is wrong, and the esxi is configuration is wrong JunjieMa and yuanqin support this,
P-1436 |  | 2026-04-01 | yuan.qin |  | WTG health front server reinstall KVM | Mayur Tisage | Low | 2026-04-01 | Server crash | 2026-04-02 | Closed | The configuration of the virtual machine hasn't been deleted total, redeploy the virtual machine will solve this issue.
P-1725 |  | 2026-04-02 | qiang.wang |  | the turbines are showing offline | Aaron Lee | Low | 2026-04-02 | Firewall configuration | 2026-04-02 | Closed | Add port 2406 at inside firewall
P-1429 |  | 2026-04-02 | Mayur Tisage |  | SCADA Web page not open | Nitheesh | Low | 2026-04-02 | Network cabe connection error | 2026-04-02 | Closed | Issue resolved.
P-1707 |  | 2026-04-02 | Ashok |  | firewall password reset | shadab | Low | 2026-04-02 | Firewall configuration | 2026-04-02 | Closed | now outside firewall is okay
P-3599 |  | 2026-04-06 | Marimuthu |  | Scada BE 1 Server OS resote done password loggien issue | sarita suresh | Low | 2026-04-06 | Server crash | 2026-04-08 | Closed | The issue resolved Cento OS image restore done and server working fine.
bess scada |  | 2026-04-06 | Ashok |  | data forwoding | manthri | Low | 2026-04-06 | Firewall configuration | 2026-04-06 | Closed
1873 |  | 2026-04-06 | Mayur Tisage |  | PPC Server Configuration | Ajeet Mishra | Low | 2026-04-06 | New requirements | 2026-04-06 | Closed | PPC Server Configuration completed.
1873 |  | 2026-04-06 | Mayur Tisage |  | Scada BE 1 and Scada BE 2 Server Configuration | Ajeet Mishra | Low | 2026-04-06 | New requirements | 2026-04-06 | Closed | BE Server Configuration completed.
p-1810/1815 |  | 2026-03-30 | Ashok |  | customer vpn pending juniper | palani kumar | Low | 2026-03-30 |  |  | Closed | issue resolved customer updated new public ip
P-1725 |  |  | Ashok | Tao.li | customer vpn pending juniper |  | Low | 2026-04-12 |  | 2026-04-14 | Closed | customer vpn established
1578 |  | 2026-04-07 | Mayur Tisage |  | Scada and EMS web pages not opening | Vijendra Jadhav | Low | 2026-04-07 | Network cabe connection error | 2026-04-07 | Closed | Servers were shutdown and ip was wrong. Now resolved.
3598 |  | 2026-04-07 | Mayur Tisage |  | internet is blocked due to semantic | Abhishekh G | Low | 2026-04-07 | Network cabe connection error | 2026-04-07 | Closed | Issue resolved.
P-3599 |  | 2026-04-08 | Marimuthu |  | Bridge Issue | sarita suresh | Low | 2026-04-08 | Scada server bridge issue | working on it | Closed
P-1344 |  | 2026-04-09 | yuan.qin |  | ipsec vpn create | JIn.zhang | Low | 2026-04-09 | New requirements | 2026-04-09 | Closed | create a ipsec vpn from Morocco to cloud, this requirement is finished
P-3599 |  | 2026-04-09 | yuan.qin |  | The PPC1 can not be ssh | sarita suresh | Low | 2026-04-09 | Server crash |  | Closed | The IP conflict cause
P-1576 |  | 2026-04-09 | yuan.qin |  | ipsec vpn create | shadab | Low | 2026-04-09 | New requirements | 2026-04-10 | Closed | The RCC public network's issue
P-8003 |  | 2026-04-09 | Marimuthu |  | Zone1 Gailileo server raid card faiure | rongrong.huang | Medium | 2026-04-09 |  | Server crash | Closed | Server Configured
P-1873 |  | 2026-04-06 | Ashok |  | EMS and SCADA Configuration and OS Reinstallation | sarita suresh | Low | 2026-04-06 | New requirements | 2026-04-10 | Closed | Issue resolved
P-1453 | CS0214962 | 2026-04-10 | Shadab.pinitod |  | 1453 scada master can not ping standby ,pls support | OM.Rollout1@univers.com | Low | 2026-04-10 |  | 2026-04-12 | Closed | contact onsite waiting reply
p-0839 |  | 2026-04-13 | qiang.wang |  | NTP not sync at CMS server issue | tianxiang.yuan | Low | 2026-04-13 |  | 2026-04-13 | Closed | Add default route fixed the issue (越南)
p-1874 |  | 2026-04-13 | yuan.qin |  | kvm can not login and virtual machine can not open. physical server can not pinging time server | Mayur | Low | 2026-04-13 |  | 2026-04-13 | Closed | Add route and configure inside firewall nat can solve the timeserver problem. Change the name of virtual machine's network card can solve the virtual machine can not open's issue
P-1749 |  | 2026-04-13 | Mayur Tisage |  | Internet broswer not working, compatibility error | on site person | Low | 2026-04-13 |  | 2026-04-13 | Closed | Issue resolved, uninstalled Semantic endopint protection
P-1436 |  | 2026-04-13 | Shadab.pinitod |  | on PA firewall light is not glowing and also need to do Data forwarding configuration | on site person | Low | 2026-04-13 |  | 2026-04-14 | Closed | TPM Lock restored
P-1586 |  | 2026-04-14 | Mayur Tisage |  | DATA Vm not accessible in Front end server | Yanzhi Liu | Low | 2026-04-14 | Network cabe connection error | 2026-04-14 | Closed
P-1478 |  | 2026-04-14 | Shadab.pinitod |  | Checked the public ip | on site person | Low | 2026-04-14 |  | 2026-06-01 | Closed | Public IP restored
P-1586 |  | 2026-04-14 | Mayur Tisage |  | Both Scada Servers cannot SSH in Moba | Yannzhi Liu | Low | 2026-04-14 | New requirements | 2026-04-14 | Closed | Issue resolved, allow ssh traffic to pass.
P-1451 |  | 2026-04-14 | jun.zhang |  | customer vpn pending juniper | Nitheesh | Medium | 2026-04-14 | New requirements | 2026-05-28 | Closed
P-1567 |  | 2026-04-14 | Ashok |  | customer vpn pending juniper | Nitheesh | Low | 2026-04-14 | Network cabe connection error | 2026-04-15 | Closed | access server down yang zhu supported on this issue
P-1843 |  | 2026-04-14 | Shadab.pinitod |  | Checked the public ip | on site person | Low | 2026-04-14 |  | 2026-06-01 | Closed | Public IP restored
P-1748 |  | 2026-04-14 | Shadab.pinitod |  | Core switch Configuration | on site person | Low | 2026-04-14 |  | 2026-06-01 | Closed | Configuration completed
8022/1451 | CS0214880 | 2026-04-06 | Shadab.pinitod |  | Facing SCADA issues at JSW Sandur during WTG operational stage. |  | Low | 2026-04-06 |  |  | Closed | OFC fiber optic issue and fixed
P-1748 |  | 2026-04-14 | Mayur Tisage |  | EMS and Scada Server Bridge Configuration not completed | Marimuthu | Low | 2026-04-14 | New requirements | 2026-04-14 | Closed | Bridge configuration completed.
P-1511 | CS0215019 | 2026-04-14 |  | qiang.wang | P1511 - From Edge, can ping SCADA1 but unable to telnet SCADA1 (172.30.181.15 2406). |  | High | 2026-04-14 |  | 2026-04-16 | Closed | Isuue fixed by remote, add TCP_2404 port at Inside firewall Zone2_Zone1 policy.
P-1707 |  | 2026-04-14 | Mayur Tisage |  | EMS Configuration not completed | Nitheesh | Low | 2026-04-14 | New requirements | 2026-04-14 | Closed | EMS server configuration completed.
P-8004 | CS0215023 |  | Ashok | qiang.wang | P8004 - cannot ping/connect to zone2 |  | High |  |  | 2026-04-14 | Closed | Issue fixed and provide capture screen to end user confirmed
P-1429 | CS0215024 |  | Ashok |  | P1429 - pre-check failed |  | High |  |  |  | Closed | closed
P-1615 | CS0215025 |  | Shadab.pinitod | jun.zhang | P1615 - pre-check failed |  | High |  |  | 2026-04-21 | Closed
P-1843 | CS0215026 | 2026-04-22 | yuan.qin |  | P1843 - pre-check failed | Aaron | High | 2026-04-22 | New requirements | 2026-04-22 | Closed | The edge gateway should add route and dns configuration
P-1610 | CS0215022 |  | Mayur Tisage |  | P1610 - pre-check failed |  | Low |  |  |  | Closed | Pending on CX. Deadline: 7/05/2026 Follow up Every 2 days. Current Status - Currently site was down due to power supply problem and there is no planned date for grid restoration. Status on 04-06-2025 ILL down customer not replying | Customer side Public Interent down
P-8022 | CS0215020 |  | Marimuthu |  | P8002 - pre-check failed |  | High |  |  |  | Closed
P-1546 | CS0215021 |  | Marimuthu |  | P1546 - install Edge + pre-check |  | High | 27-04-2026 |  | 29-04-2026 | Closed | Pre-checklist is done, but the DNS IP is not pinging. The laptop is connected to the Zone 2 server, but ping to DNS IP 8.8.8.8 is not working. After logging into the firewall, the WAN 1 interface status is down. Except for DNS IP 8.8.8.8 and telnet, everything else is working and has been checked.
p-1428 | CS0215021 | 2026.4.15 | jun.zhang |  | port can not glowing in the firewall | Shadab.pinitod | Low | 2026.4.15 | Hard drive failure | 2026-04-15 | Closed
P-1478 |  | 2026-04-15 | Mayur Tisage | qiang.wang | Time Sync issue for CMS webportal | RongRong.Huang | Low | 2026-04-15 |  | 2026-06-01 | Closed | Time issue fixed by remote, closed ticket
P-1428 |  | 2026-04-15 | Shadab.pinitod | jun.zhang | New Data forwarding requirement |  | Low | 2026-04-15 |  |  | Closed
p-1478 | CS0215022 | 2026-04-15 | Ashok | jun.zhang | Juniper vpn break down |  | Low | 2026-04-15 |  |  | Closed
p-1567 |  | 2026-04-13 | Ashok | Ashok | juniper vpn down | nitheesh | Low | 2026-04-13 | Server crash | 2026-04-14 | Closed | access server down yang zhu supported on this issue
p-8004 |  | 2026-04-13 | Ashok | Ashok | juniper vpn down | praveen | Low | 2026-04-13 |  |  | Closed | customer ports down
p-1725 |  | 2026-04-13 | Ashok | Tao.li | radius server install | praveen | Low | 2026-04-13 | New requirements | 2026-04-15 | Closed | installed
p-1615 |  | 2026-04-15 | Shadab.pinitod | Ashok | mppc data forwording issue | navaneethan | Low | 2026-04-15 | New requirements | 2026-04-15 | Closed | firewall configurations
p-8020 |  | 2026-04-15 |  | Ashok | ssl vpn creations | Praveen | Low | 2026-04-15 |  | 2026-04-15 | Closed | firewall configurations
p-1528 |  | 2026-04-15 |  | Ashok | ring master switch config | ravi | Low | 2026-04-15 |  | 2026-04-15 | Closed | completed rstp config
p-1843 |  | 2026-04-09 |  | Ashok | firewall licesence upgrade | tao li | Low | 2026-04-09 |  | 2026-04-16 | Closed | license upgrade
P-3599 |  | 2026-04-15 | Marimuthu | yuan.qin | PPC1 can not use windos to ssh | Sarita | Low | 2026-04-15 | Server crash | 2026-04-16 | Closed | Ip address confilt
P-1427 |  | 2026-04-13 | Marimuthu | yuan.qin | Scada2 can not pinging | Marimuthu | Low | 2026-04-13 |  | 2026-04-16 | Closed | The label is wrong, find a really server, and find the configuration is wrong
P-1428 |  | 2026-04-16 | Shadab.pinitod | jun.zhang | Public ip changes | Nitheesh | Low | 2026-04-16 | New requirements | 2026-04-16 | Closed | chang the public ip addr
P-1511 |  | 2026-04-16 |  | qiang.wang | Edge server time sync issue | Aaron | Low | 2026-04-16 |  | 2026-04-16 | Closed | Add NTP server iburst and restart chronyd servcie, fixed
P-1546 |  | 2026-04-16 | Mayur Tisage | yuan.qin | time server's issue | Mayur | Low | 2026-04-16 |  | 2026-04-16 | Closed | Galileo APP is time is 2005/5/1 the error is too large, so time sync failed
p-8015 |  | 2026-04-16 | Ashok | Ashok | juniper vpn down | Praveen | Low | 2026-04-16 |  | 2026-04-16 | Closed | yang zhu supported on this issue customer side public ip changed and ports were down
P-1486 |  | 2026-04-16 | Marimuthu | jun.zhang | WTG server network card fail | Marimuthu | Low | 2026-04-16 | Server crash | 2026-04-16 | Closed
P-1451 |  | 2026-04-17 | Shadab.pinitod | jun.zhang | IP SEC vpn down | shadab | Low | 2026-04-17 | Network cabe connection error | 2026-04-17 | Closed
P-1486 |  | 2026-04-20 | Mayur Tisage | yuan.qin | time sync | Mayur | Low | 2026-04-16 |  | 2026-04-20 | Closed | The esxi's time is wrong, so it will force sync to virtial machine
P-1427 |  | 2026-04-13 | Marimuthu | yuan.qin | scada2 can not pinging | Marimuthu | Low | 2026-04-13 | Network cabe connection error | 2026-04-16 | Closed | The network configuration is wrong
P-0839 | CS0215005 | 2026-04-14 | qiang.wang | yuan.qin | The Galileo server can not upload data to cloud | RongRong.Huang | Low | 2026-04-14 | Network cabe connection error | 2026-04-21 | Closed | The Internet can not be pinging
P-1478 |  | 2026-04-17 | Ashok | Shadab.pinitod | New SSL VPN configuration |  | Low | 2026-04-17 |  |  | Closed
P-8020 |  | 2026-04-17 | Ashok | qiang.wang | radius server install |  | Low | 2026-04-17 |  | 2026-04-17 | Closed
p-3599 |  | 2026-04-20 |  | Ashok | ssl vpn creation |  | Low | 2026-04-20 |  | 2026-06-01 | Closed | Customer account created
P-1576 |  | 2026-04-17 | Shadab.pinitod | Ashok | New Data forwarding requirement | Nitheesh | Low | 2026-04-17 |  | 2026-04-17 | Closed
P-3599 | iC20260416015 | 2026-04-16 | Ashok |  | Connectivity issue as the turbines are connecting and disconnecting on it's own. | Nitheesh | Low | 2026-04-16 |  | 2026-04-20 | Closed | customer side optical connectivity issue resolved
P-1567 |  | 2026-04-20 | Mayur Tisage |  | servers status since most of the server not auto powered ON after power supply resumed.! | Nitheesh | Low | 2026-04-20 |  |  | Closed
P-3599 |  | 2026-04-20 | Ashok | qiang.wang | VPN creation for site | Nitheesh | High | 2026-04-20 |  | 2026-04-20 | Closed | Created SSL vpn site and tested successfully
P-8014 |  | 2026-04-20 |  | qiang.wang | The Gailileo data server IP not reachable | feiyao.xi | Low | 2026-04-20 |  | 2026-04-20 | Closed | Server power off and power on
P-1478 |  | 2026-04-20 | Ashok | qiang.wang | The Gailleo CMS time sync having issue | rongrong.huang | Low | 2026-04-20 |  |  | Closed | Changed time server IP 192.168.45.85 and chronyc -a makestep
P-8014 |  | 2026-04-20 | Mayur Tisage |  | servers status since most of the server not auto powered ON after power supply resumed.! | Nitheesh | Low | 2026-04-20 |  |  | Closed
P-1567 |  | 2026-04-20 | Marimuthu |  | servers status since most of the server not auto powered ON after power supply resumed.! | Nitheesh | Low | 2026-04-20 |  |  | Closed
P-1576 |  | 2026-04-20 | Mayur Tisage | yuan.qin | WTG Health Front end server OS Issue | Thirupathi | High | 2026-04-20 | Server crash |  | Closed | Checking inside the server if any cables removed. Qinyuan: Solved by replacing Hard disk | Solved by replacing Hard disk | Yes | Hard DIsk
P-1632 |  | 2026-04-20 | Mayur Tisage |  | Scada Primary Ip not reachable | Nitheesh | Low | 2026-04-20 |  | 2026-04-20 | Closed
P-1478 |  | 2026-04-21 | Shadab.pinitod |  | Radius server installation |  | Low | 2026-04-21 |  | 2026-05-28 | Closed | installed, need to do troubleshooting | Installed and working
P-1407 | CS0215050 | 2026-04-21 | Mayur Tisage | jun.zhang | Sprng Mulanur TN (P 1407), Fourth Partner Ottapidaram (P-8015), and Ayana Wankie GJ (P-1567) | Nitheesh NG | Low |  |  | 2026-05-28 | Closed |  | Closed after performing the Pre check
P-1578 |  | 2026-04-21 | Mayur Tisage |  | SCADA server ntp not synchronized | Sangappa | Low | 2026-04-21 |  | 2026-04-21 | Closed
P-1511 | CS0215104 | 2026-04-21 | Mayur Tisage | yuan.qin | P1511: 2 issues, DATA server unable to access, but can ping (check data interruption issue) & check firewall NAT settings (turbines in EnOS disconnect) | Aaron | Medium | 2026-04-21 |  |  | Closed
P-1453 | CS0214962 | 2026-04-21 | Mayur Tisage |  | 1453 scada master can not ping standby ,pls support |  | Low | 2026-04-20 |  | 2026-06-01 | Closed | Checked the configuration and closed
P-1429 |  | 2026-04-21 | Mayur Tisage |  | Scada, EMS, PPC server ntp configuration | Sangappa | Low | 2026-04-21 |  | 2026-04-21 | Closed
p-1586 | CS0215105 | 2026-04-21 | Mayur Tisage |  | P1586 APP server cannot ping and access |  | Low | 2026-04-21 |  |  | Closed | All VMs are running with auto start enabled, provided ss on the group
P-1576 |  | 2026-04-21 | Mayur Tisage | jun.zhang | P-1576 Galileo data server reinstall OS | RongRong.Huang | High | 2026-04-21 | Hard drive failure | 2026-04-22 | Closed | issue closed | Replaced the HDD of faulty server to backup server and restored it. | yes | Raid Controller
P-1428 |  | 2026-04-21 | Shadab.pinitod | jun.zhang | Public IP configurations | Nitheesh | Low | 2026-04-22 |  | 2026-04-22 | Closed
p-3599 |  | 2026-04-21 | Ashok |  | vpn configuration | praveen | Low | 2026-04-22 |  | 2026-04-21 | Closed
P-1480 |  | 2026-04-22 | Shadab.pinitod | jun.zhang | IP SEC VPN Configuration |  | Low | 2026-04-22 |  | 2026-04-22 | Closed
1334 |  | 2026-04-22 | yuan.qin |  | IP SEC VPN issue | jin.zhang | Low | 2026-04-22 |  | 2026-04-22 | Closed | Edit the configuration, and solve this issue, this site should be monitored for a period of time
P-1567 |  | 2026-04-22 | Shadab.pinitod | jun.zhang | new IP SEC VPN Configuration |  | Low | 2026-04-22 |  | 2026-04-22 | Closed | Tunnel is down , need to chcek from RCC end
P-1436 |  | 2026-04-22 | Mayur Tisage |  | STD, CMS, DATA VM time sync issues | yanzhi liu | Low | 2026-04-22 |  | 2026-04-23 | Closed
P-1486 |  | 2026-04-23 | Shadab.pinitod | jun.zhang | To cheeck public ip and ipsec configuration |  | Low | 2026-04-23 |  | 2026-04-23 | Closed | in P-1486, private ip is used for WAN. Ipsec tunnel showing done. need to contact customer.
P-1610 |  | 2026-04-23 | Shadab.pinitod |  | To check the internet status | Mayur Tisage | Low | 2026-04-23 |  | 2026-04-23 | Closed | public ip gateway and 8.8.8.8 is not pinging. due to supply
p-1478 |  | 2026-04-23 | Ashok |  | radius server RE- install | PRAVEEN | Low | 2026-04-23 |  | 2026-04-23 | Closed |  | Installed and working
P-8020 |  | 2026-04-23 | Ashok |  | SSL VPN | PRAVEEN | Low | 2026-04-23 |  | 2026-04-23 | Closed | firewall new requirements
P-8004 |  | 2026-04-21 | Mayur Tisage |  | WTG Health Back end server 2 HDD Failure | Revappa | High | 2026-04-21 | Hard drive failure |  | Closed | Purchased and ordered hard disk | Purchased and ordered hard disk | Yes | Hard DIsk
P-8003 | CS0214891 | 2026-04-17 | Mayur Tisage |  | P-8003 Cleanmax_Amreli Galileo server communication exception | tianxiang.yuan | Low |  | Server crash | 2026-06-01 | Closed | New Server replaced and configuration completed |  | Yes
P-1725 | CS0215080 | 2026-04-16 | Marimuthu |  | P-1725 no CMS data upload | rongrong.huang | Medium |  |  | 2026-06-01 | Closed | P-1725: This ticket is related to software, not infrastructure. Please assigen to universe software end.
P-3598 | CS0215195 | 2026-04-22 | Shadab.pinitod |  | P-3598 three WTGs IPC data interrupted since 1/10/2026 | rongrong.huang | Medium |  |  | 2026-06-01 | Closed | this has to be checked by Site team individual location handled by syite team
P-1632 | CS0215215 | 2026-04-24 | Marimuthu |  | P-1632,CMS collector has generated the data there is no data on SCADA server-IN-01/68-B-013 | Sheik Mohammed | Medium |  |  | 2026-06-01 | Closed
P-8004 |  | 2026-04-27 | Ashok | qiang.wang | edge issue |  | Medium | 2026-04-27 | Server crash | 2026-04-27 | Closed | edge status was offline
p-3599 |  | 2026-04-27 | Ashok |  | svg forwording issue | Sarita | High | 2026-04-27 | New requirements | 2026-04-27 | Closed | svg cabling issue
p-1511 |  | 2026-04-27 | Ashok |  | edge telnet issue | aaron | Medium | 2026-04-27 | New requirements | 2026-04-27 | Closed | in server 2406 port were not added :now added and working
P-1846 |  | 2026-04-27 | Mayur Tisage |  | SCADA BE Server 1 and 2 OS Reinstallation | Praveen | Low | 2026-05-13 | New requirements |  | Closed | Infra side Server Conf Completed.
P-1427 |  | 2026-04-27 | Mayur Tisage |  | SCADA BE Server 1 and 2 OS Reinstallation | Marimuthu | Low | 2026-04-27 | Server crash | 2026-05-08 | Closed | Server reinstallation completed, ip configuration is also completed.
p-8020 |  | 2026-04-29 | Ashok | qiang.wang | cutomer port isssue | nitheesh | High | 2026-04-28 | New requirements | 2026-04-28 | Closed | virul Ips mapping was wrong, after corrected customer private IP, issue solved changed 1.2
P-1429 |  | 2026-04-27 | Marimuthu |  | Scada server not reachble | Saritha | Medium | 2026-04-28 | Network cabe connection error | 2026-04-28 | Closed | Scada BE 2 not recahble and i have checked now it's working fine
P-1576 | CS0215283 | 2026-04-28 | Marimuthu |  | P-1576 Galileo configruation check | rongrong.huang | Low |  |  |  | Closed | Server was up and shred the
P-1486 | CS0215285 | 2026-04-28 | Mayur Tisage |  | P-1486 no Galileo site Alarm data upload | rongrong.huang | Medium |  |  | 0-06-2026 | Closed | As per infra team everything is working fine. Screenshots attached in the group
P-1453 | CS0215284 | 2026-04-28 | Marimuthu |  | P-1453 all data interrupted from 4.25 | rongrong.huang | Medium |  |  | 2026-06-04 | Closed | Server was off cxonddition and restored
P-3598 | CS0215282 | 2026-04-28 | Mayur Tisage |  | P-3598 all data interrupted from 4.18 except IPC | rongrong.huang | Medium |  |  |  | Closed | ̥
8020 |  | 2026-04-29 | Ashok |  | ssl vpn completed | nitheesh | High | 2026-04-29 | New requirements | 2026-04-29 | Closed | completed and provided cutomer access
P-1428 | CS0215300 | 2026-04-29 | yuan.qin |  | The Galileo server can not pinging 8.8.8.8 | yuantianxiang | Medium | 2026-04-30 |  | 2026-05-06 | Closed | The outside firewall can also not pinging the 8.8.8.8 , The thing has told customer to check
P-8020 |  | 2026-04-30 | Ashok |  | moniter url | nitheesh | Medium | 2026-04-30 | New requirements | 2026-04-30 | Closed
p-1428 |  | 2026-04-30 | Ashok |  | public ip down | Praveen | Medium |  | New requirements | 2026-06-01 | Closed | Customer Public IP restored
p-1436 |  | 2026-04-30 | Ashok |  | 65443 not open | praveen | Medium |  | New requirements | 2026-06-01 | Closed | Customer Public IP restored and ports allowed
p-1486 |  | 2026-04-30 | qiang.wang |  | customer publi ip down ,spped issue uploading to cloud | praveen | Low |  | New requirements |  | Closed | Diwscuss with the customer
P-1660 |  | 2026-04-29 | Mayur Tisage | yuan.qin | SCADA OS File System issue | Mayur | High | 2026-04-01 | New requirements | 2026-05-01 | Closed | Issue resolved
P-1660 |  | 2026-05-01 | Mayur Tisage |  | EMS OS install correct version | Mayur | Medium | 2026-05-01 | New requirements | 2026-05-06 | Closed | issue resolved
P-1453 |  | 2026-05-01 | Mayur Tisage |  | WTG Health BE server VM auto start | Mayur | Medium | 2026-05-01 | Network cabe connection error | 2026-05-04 | Closed | Issue resolved and proof attached in the group
P-1725 |  | 2026-05-01 | Mayur Tisage | yuan.qin | EMS Server Network configuration file currupted | Abdullah | High | 2026-05-01 | Network cabe connection error | 2026-05-01 | Closed | Reconfigured the IPs and closed the issue
P-1546 |  | 2026-05-05 | Marimuthu |  | Time Issue | Thiruppathi | Medium | 2026-05-05 | time issue | 2026-05-05 | Closed | WTG scada server Time synchronization
P-8020 |  | 2026-05-01 | yuan.qin |  | WTG Health Back end server Motherboard issue | Niteesh | Medium | 2026-05-05 | Server crash | 2026-05-05 | Closed | Yuan restored with configuration
P-1741 |  | 2026-05-05 | Mayur Tisage |  | EMS Server Configuration | Praveen | High | 2026-05-05 | New requirements |  | Closed | SCADA configuration is completed for this site
P-8003 |  | 2026-05-05 | Marimuthu |  | WTG health front end server hardware failed | Cleanmax Site | Medium | 2026-05-10 | Hardware failed | 2026-05-15 | Closed | OS re installed and reconfigured |  | Yes | Disk
p-1486 |  | 2026-05-05 | Ashok |  | third party firewall os reinstall | nitheesh | Medium | 2026-05-05 | Hardware failed | 2026-05-05 | Closed | after reinstalling os it got resolved
P-1428 | CS0215300 | 2026-04-29 | Shadab.pinitod |  | P-1428 Blupine Gujarat 198MW public ip unable reach | nitheesh | Medium | 2026-05-06 |  |  | Closed
P-8020 | CS0215383 | 2026-05-06 | Shadab.pinitod | yuan.qin | P-8020/1420 All Galileo data interrupted from 4.30 | rongrong.huang | High | 2026-05-21 | Server crash | 2026-05-21 | Closed | The galileo server's network card is damaged
P-8023 | CS0215377 | 2026-05-07 | Mayur Tisage |  | P-8023 India_Project Twelve_Ayana_Amerli_GJ_141.9MW The server communication in Galileo II region is abnormal and requires infrastructure troubleshooting | yuantianxiang | Medium | 2026-05-06 |  | 2026-06-01 | Closed | Issue is resolved, already communication is provided in the group
P-8004 | CS0215405 | 2026-05-07 | Mayur Tisage |  | P8004 EMS SSD eschange activities | Zhang Jin | Medium |  |  | 2026-06-01 | Closed | OS Reconfigured after changing the HDD
P-8014 |  | 2026-05-06 | Marimuthu |  | Scada upgrate activity | Jin Zhang(Outsourcing | Medium | 2026-05-06 | Scada upgrade file download and upgrade |  | Closed | File download done and pending with universe team end
P-1725 |  | 2026-05-06 | Marimuthu |  | EMS backup system bridge issue | Nizyaz | Medium | 2026-05-06 | EMS backup system bridge issue eno1 not showing then reconfigure and after showing | 2026-05-06 | Closed | EMS bridge reconfiguration and after shwoing eno1 issue resolved
P-8004 | CS0215405 | 2026-05-07 |  |  | P8004 EMS SSD exchange Activities | Vasudev Suryavanshi (vasudev suryavanshi) | Medium |  |  | 2026-06-01 | Closed | OS Reconfigured after changing the HDD
P-8012 | CS0215413 | 2026-05-09 | qiang.wang |  | P-8012 unable upload data to cloud | yuantianxiang | Medium | 2026-05-12 |  | 2026-05-12 | Closed | issue fixed aftyer modify DNS conf
P-1436 |  | 2026-05-06 | Shadab.pinitod |  | Changed the Public ip and extranet is working fine | Nitheesh NG | Medium | 2026-05-06 |  | 2026-05-12 | Closed
p-3598 |  | 2026-05-08 | Ashok | qiang.wang | time sync issue | nitheesh | High | 2026-05-08 | Server crash | 2026-05-08 | Closed | after configurring time server it resolved
p-1707 |  | 2026-05-08 | Ashok |  | wrldc data forwording | harie | medium | 2026-05-08 |  | 2026-05-08 | Closed | Firewall configuration
P-1511 |  | 2026-05-11 | Mayur Tisage |  | APP Server cannot ssh | Sangappa | Low | 2026-05-11 |  | 2026-05-11 | Closed | Allowed the SSH for APP server
p-1725 | CS0215522 | 2026-05-12 | Marimuthu |  | P-1725 CleanMax PH2 CMS NTP synchronization Error | Maiyariya kara masari (kara Maiyariya) | Medium |  |  | 2026-06-03 | Closed | Issue resolved form infra end and time is corretely shwoing
P-1466 |  | 2026-05-12 | Shadab.pinitod |  | Public ip reachable | Nitheesh | Medium | 2026-05-12 |  | 2026-05-12 | Closed
p-1725 |  | 2026-05-12 | Ashok | qiang.wang | vpn down | Nitheesh | High | 2026-05-12 | Server crash | 2026-05-12 | Closed | radius server down
p-1610 |  | 2026-05-11 | Ashok |  | scada not ping to zone2 | mayur | Medium | 2026-05-11 | Network cabe connection error | 2026-05-11 | Closed | cable issue
p-1453 |  | 2026-05-12 | Ashok |  | srldc data forwording issue | praveen | Medium | 2026-05-12 | New requirements | 1900-01-11 | Closed | firewall ports are open
P-1610 |  | 2026-05-13 | Shadab.pinitod |  | Mppc data forwarding issue | praveen | Medium | 2026-05-13 |  | 2026-05-13 | Closed | firewall ports are open
P-1428 |  | 2026-05-13 | Shadab.pinitod |  | Mirror porting on cisco switch | Nitheesh | Medium | 2026-05-13 |  | 2026-05-13 | Closed
P-8012 | CS0215479 | 2026-05-11 | qiang.wang |  | 8012 scada can not ping S3,pls support. | rongrong.huang | Medium | 2026-05-12 |  | 2026-05-12 | Closed | DNS issue soolved
P-1466 | CS0215565 | 2026-05-13 | Shadab.pinitod | jun.zhang | P-1466 all Galileo data upload interrupted since May 5 | rongrong.huang | Medium |  |  |  | Closed | Routes was not there , then we added the routes it resolved now
P-1436 |  | 2026-05-11 | yuan.qin |  | Galileo app and cms need to extend space | liu.yang | Medium | 2026-05-11 | Server crash | 2026-05-11 | Closed | These servers's space be extended
P-1436 |  | 2026-05-11 | yuan.qin |  | Galileo data virtual machine will shutdown suddenly | liu.yang | Medium | 2026-05-11 | Server crash | 2026-05-11 | Closed | The virtual machine's memery is too small
P-1436 |  | 2026-05-14 | Shadab.pinitod |  | Mirror porting on cisco switch | Nitheesh | Medium | 2026-05-14 |  | 2026-05-14 | Closed
p-8001 |  | 2026-05-14 | Ashok |  | ppc server not reachable to wtg | saritha | High | 2026-05-14 | Network cabe connection error | 2026-05-14 | Closed | cable loose issue
P-1749 |  | 2026-05-14 | Mayur Tisage |  | Server Configuration | Revappa | Low | 2026-05-15 | New requirements | 2026-05-15 | Closed | Configuration Completed
p-8020 |  | 2026-05-15 | Ashok | qiang.wang | vpn down | sanjay | High | 2026-05-15 | New requirements | 2026-05-15 | Closed | vpn down radius server down
p-1749 |  | 2026-05-13 | Ashok |  | ring loop config | Ravi | medium | 2026-05-13 | New requirements | 2026-05-15 | Closed
p-1725 |  | 2026-05-15 | Ashok | qiang.wang | cms time sync issue | wang | High | 2026-05-15 | New requirements | 2026-05-15 | Closed | port 123 is not enabled on server after adding its worked.
p-1749 |  | 2026-05-15 | Ashok |  | time server config | Ravi | High | 2026-05-15 | New requirements | 2026-05-15 | Closed | config completed
p-1749 |  | 2026-05-15 | Ashok |  | public ip down | Ravi | High | 2026-05-15 | Network cabe connection error | 2026-05-15 | Closed | after correct the cable its okay now
p-8006 |  | 2026-05-15 | Ashok |  | ppc forword issue | praveen | Low | 2026-05-15 |  | 2026-05-29 | Closed | customer will arrange the serial cable
p-8020 | CS0215578 | 2026-05-14 | Ashok |  | P-8020 scada can not ping galileo ,data stuck at scada ,pls help |  | Medium | 2026-05-18 |  | 2026-05-29 | Closed
p-1632 |  | 2026-05-18 | Ashok | jun.zhang | juniper vpn unable to login | nitheesh | high | 2026-05-18 | New requirements | 2026-05-18 | Closed | now its working fine
p-1707 |  | 2026-05-18 | Ashok |  | data forwording port modification | sarita | high | 2026-05-18 | New requirements | 2026-05-18 | Closed | after adding ports working fine
p-8020 |  | 2026-05-18 | Ashok |  | ems monitering page creation | nithesh | high | 2026-05-18 | New requirements | 2026-05-18 | Closed
p-1843 |  | 2026-05-18 | Ashok |  | scada moniter issue | nithesh | high | 2026-05-18 | New requirements | 2026-05-18 | Closed
P-1847 |  | 2026-05-19 | Marimuthu |  | Both Scada is not pingking | Abdullah | High | 2026-05-19 | Network cabe connection error | 2026-05-19 | Closed | After corrcet the network conectivity both scada is working fine. | Issue resolved
P-8023 | CS0215611 | 2026-05-15 | Mayur Tisage | yuan.qin | P-8023 India_Project Twelve_Ayana_Amerli_GJ_141.9MW The server in Galileo II region frequently crashes. Please have the architecture team handle it and investig | rongrong.huang | High | 2026-05-18 | Server crash | 2026-05-22 | Closed | Open the autostart | issue resolved
P-8014 | CS0215641 | 2026-05-18 | yuan.qin |  | P-8014 India_AMGEPL_148.5MW_Pinnapuram_Kurnool Galileo server communication anomaly | yuantianxiaing | low |  | Server crash |  | Closed | Customer Public IP resolved
P-1632 | CS0215674 | 2026-05-19 | Marimuthu |  | P-1632 Renfra ;Galilieo server configuration request | Sheik Mohammed | Medium |  | Server crash |  | Closed | Public IP Restored
p-8014 |  | 2026-05-19 | Ashok |  | ems monitering page | nitheesh | Medium | 2026-05-19 | New requirements | 2026-05-19 | Closed | juniper fw port 8702 added
P-1610 |  | 2026-05-19 | Shadab.pinitod |  | third party firewall issue | Praveen | Medium | 2026-05-19 |  | 2026-05-19 | Closed
P-8020 | CS0215578 | 2026-05-06 | Ashok | yuan.qin | P-8020 scada can not ping galileo ,data stuck at scada ,pls help |  | Medium |  | Server crash | 2026-05-22 | Closed | netwok card failure
P-8020 | CS0215383 | 2026-05-06 | Ashok |  | P-8020/1420 All Galileo data interrupted from 4.30 |  | Medium |  | Server crash | 2026-05-22 | Closed | netwok card failure
P-8004 | CS0215405 | 2026-05-07 | Mayur Tisage |  | P8004 EMS SSD exchange Activities |  | Medium |  |  | 2026-06-01 | Closed | EMS 2 currupted HDD is replaced with SSD. Issue is resolved
P-1632 | CS0215674 | 2026-05-19 | Marimuthu |  | P-1632 Renfra ;Galilieo server configuration request |  | Medium |  |  |  | Closed | Public IP Restored
P-1836 | CS0215479 | 2026-05-11 | Ashok |  | 0836 scada can not ping S3,pls support. |  | Medium |  |  |  | Closed | Vietnam Gia Lai Pat Trien Mien Nui Wind Plant 50MW(not related to India Project)
P-1610 |  | 2026-05-20 | Mayur Tisage |  | 5 Scada Laptops Configuration | Shreeram Pandey | Low | 2026-05-20 | New requirements | 2026-05-20 | Closed
p-8014 |  | 2026-05-20 | Ashok |  | galileo app was not reachable | wang | medium | 2026-05-20 | Server crash | 2026-05-20 | Closed | vm down issue
p-1511 |  | 2026-05-20 | Ashok |  | vpn down | nitheesh | high | 2026-05-20 | New requirements | 2026-05-20 | Closed | ports were not open at customer side
p-1707 |  | 2026-05-20 | Ashok |  | zone 2 reachablity issue | Aaron | high | 2026-05-20 | Network cabe connection error | 2026-05-20 | Closed | connected to the zone 2 switch its working
P-1725 |  | 2026-05-21 | Ashok |  | This tiicket was under Thiru,he had investigated previously and found is due to network issue,he communicated with network team,the ticket is also currently under infrastructure team | rongrong.huang | Medium |  | Network cabe connection error | 2026-06-04 | Closed | now extranet communication is ok
P-1843 |  | 2026-05-21 | Mayur Tisage |  | Alarm data interrupted since 4/10/2026 | rongrong.huang | Low |  |  |  | Closed | Public IP Restored
P-1576 | CS0215283 | 2026-05-21 | Marimuthu |  | Galileo configruation check | rongrong.huang | Low |  |  |  | Closed
P-1453 |  | 2026-05-20 | Shadab.pinitod |  | New Data Forwarding requirement | Sarita | Medium | 2026-05-20 | New requirements | 2026-05-20 | Closed
P-1511 |  | 2026-05-21 | Shadab.pinitod |  | Alarm data interrupted since 3/6/2026 | rongrong.huang | high | 2026-05-21 |  |  | Closed | Public IP Restored
P-1586 |  | 2026-05-21 | Mayur Tisage |  | Galileo data server deployment CMS 2.1 | rongrong.huang | high | 2026-05-21 |  |  | Closed | Public IP Restored
P-3598 | CS0215195 | 2026-05-21 | Marimuthu |  | three WTGs IPC data interrupted since 10/1/2026 | rongrong.huang | Low | 2026-05-21 |  |  | Closed | Turbine Communication restored
P-3598 | CS0215282 | 2026-05-21 | Marimuthu |  | all data interrupted from 4.18 except IPC | rongrong.huang | Low | 2026-05-21 |  |  | Closed | Public IP Restored
P-1453 | CS0215284 | 2026-05-21 | Mayur Tisage |  | all data interrupted from 4.25 | rongrong.huang | high | 2026-05-21 |  | 2026-06-03 | Closed | Issue resolved
P-1420 | CS0215383 | 2026-05-21 | Ashok |  | P-8020/1420 All Galileo data interrupted from 4.30 | rongrong.huang | high |  |  |  | Closed | network card of health front end server failure reconfigured and closed
P-1632 | CS0215215 | 2026-05-21 | Marimuthu |  | CMS collector has generated the data there is no data on SCADA server-IN-01/68-B-013 | rongrong.huang | high |  |  |  | Closed | Public IP Restored
P-1707 |  | 2026-05-21 | Ashok |  | Scada route issue | Hari | Medium | 20-05-2026 | Server crash | 21-05-2025 | Closed | Issue resolved route IP is addred now it's pingking sucessfully
P-1846 |  |  | Mayur Tisage |  | Mob is not conecting | Abudulla | Medium | 21-05-2026 | Network cabe connection error | 21-05-2025 | Closed | Issue resolved now is mob connecting
P-1707 |  | 2026-05-21 | Ashok |  | WRLDC 2 REQUIREMENT NOT PINGING | HARI | Low | 21-05-2026 | New requirements | 21-05-2025 | Closed | Issue resolved now ITS WORKING fine
P-1566 |  | 2026-05-21 | Shadab.pinitod |  | HA configurtions |  | Medium | 21-05-2026 | New requirements | 21-05-2025 | Closed
P-1741 |  | 2026-05-21 | Shadab.pinitod |  | Time server Configuration | Sanjay | Medium | 21-05-2026 | New requirements | 21-05-2025 | Closed
P-1429 |  |  | Mayur Tisage |  | WTG Health BE and Front Server VM issues and Pre check | Qiang wang | Medium | 2026-05-22 |  |  | Closed | issue resolved
P-1707 |  | 2026-05-22 | Shadab.pinitod |  | Data forwarding requirement | Harie | Medium | 2026-05-22 | New requirements | 2026-05-22 | Closed
P-1576 |  | 2026-05-22 | Shadab.pinitod |  | public ip changes | Nitheesh | Medium | 2026-05-22 |  | 2026-05-22 | Closed | extranet communication working fine
P-1407 |  |  | Mayur Tisage |  | EMS server time is not synced | Praveen Elango | Low | 2026-05-22 |  | 2026-05-22 | Closed
P-1615 |  |  | Mayur Tisage |  | SCADA AND EMS IP conflict | Niyasdin | Low | 2026-05-22 | Network cabe connection error | 2026-05-22 | Closed
p-1453 |  | 2026-05-22 | Ashok |  | data forwording mppc | sangappa | high | 2026-05-22 | New requirements | 2026-05-22 | Closed | firewall config complete
p-1811 |  | 2026-05-22 | Ashok |  | time server config |  | medium | 2026-05-22 | New requirements | 2026-05-22 | Closed | config completed
p-1811 |  | 2026-05-22 | Ashok |  | ring loop configuration |  | medium | 2026-05-22 | New requirements | 2026-05-22 | Closed | config completed
P-1812 |  | 2026-05-22 | Shadab.pinitod |  | Core switch Configuration |  | medium | 2026-05-22 | New requirements | 2026-05-22 | Closed
P-1843 |  | 2026-05-25 | Marimuthu |  | Scada BE 1 it's not working | Sangappa | High | 2026-05-25 | Network cabe connection error | 2026-05-25 | Closed | Network cable issue after change the NW cable it's working fine and issue resolved
P-1566 |  | 2026-05-25 | Shadab.pinitod |  | Switch configuration |  | medium | 2026-05-25 | New requirements | 2026-05-25 | Closed
P-1453 |  | 2026-05-26 | Ashok |  | infra team to check on network Enos related Issue need to follow Pre check | Nitheesh/Aaron | medium | 2026-05-26 | Network cabe connection error | 2026-06-04 | Closed
P-1511 |  | 2026-05-26 | Ashok |  | ENOS disconnect issue - infra team to disable NAT settings | Nitheesh/Aaron | medium | 2026-05-26 | Network cabe connection error | 2026-05-29 | Closed
P-1511 |  | 2026-05-26 | Ashok |  | APP server can ping but cannot access, cannot check further data interruption issue | Nitheesh/Aaron | medium | 2026-05-26 | Network cabe connection error |  | Closed | Server off condition server restored
P-1451/8022 |  | 2026-05-26 | Ashok |  | infra team to disable NAT settings | Nitheesh/Aaron | medium | 2026-05-26 | Network cabe connection error | 2026-05-29 | Closed
P-1725 |  | 2026-05-26 | Ashok |  | ENOS disconnect issue - edge password not working and infra team to disable NAT settings | Nitheesh/Aaron | medium | 2026-05-26 | Network cabe connection error | 2026-06-04 | Closed | nat setting disabled
P-8015 |  | 2026-05-26 | Mayur Tisage |  | pre-check failed | Nitheesh/Aaron | medium | 2026-05-26 | Network cabe connection error | 2026-06-01 | Closed | Precheck completed, screenshots shared on group
P-1707 |  | 2026-05-26 | Marimuthu |  | pre-check failed | Nitheesh/Aaron | medium | 2026-05-26 | Network cabe connection error | 2026-06-03 | Closed | Issue resolved form infra end
P-8002 |  | 2026-05-26 | Marimuthu |  | pending Qiang Wang(Outsourcing) to provide reserved IP for zone2 192 series IP | Nitheesh/Aaron | medium | 2026-05-26 | Network cabe connection error | 2026-06-01 | Closed | Reserved Ip alredy assigedn the site laptop
P-1480 |  | 2026-05-26 | jun.zhang |  | juniper vpn unable to login | Nitheesh | medium |  |  | 2026-06-01 | Closed | Juniper VPN accountg created
p-1615 |  | 2026-05-25 | Ashok |  | time server config | mayur | medium | 2026-05-25 | Server crash | 2026-05-25 | Closed | time server route issue
p-1615 |  | 2026-05-25 | Ashok |  | mppc forwording issue | praveen | medium | 2026-05-25 | New requirements | 2026-05-25 | Closed | server route missing now working
p-1610 |  | 2026-05-25 | Ashok |  | zone 2 not reachable | aaron | medium | 2026-05-25 | Network cabe connection error | 2026-05-25 | Closed | connected to zone 2 switch and set reserve ip
p-1811 |  | 2026-05-26 | Ashok |  | zone 1 ip not pinging | mari muthu | medium | 2026-05-26 | Network cabe connection error | 2026-05-26 | Closed | two cable connected to switch occur loop
P-1420 | CS0215809 | 2026-05-19 | yuan.qin |  | communication issue for zone 1 serve | rongrong.huang | Medium | 2026-05-26 | Network cabe connection error |  | Closed | The server was failed to start after re configuring of the VM it is solved and confirmed by Wu honxia
P-1478 | CS0215709 | 2026-05-21 | Marimuthu |  | P-1478 all data interrupted from May 16 | rongrong.huang | Medium |  |  |  | Closed | Public IP issue resolved
P-1812 |  | 2026-05-27 | Shadab.pinitod |  | firewall configuration |  | Medium | 2026-05-27 |  | 2026-05-27 | Closed | configuration completed
P-1721 | CS0215748 | 2026-05-22 | Shadab.pinitod |  | CMS sensors not connecting to HQ because of NTP time issue at P1721 | Palanikumar P | Medium |  |  |  | Closed | Time syn issue resolved
P-0513 |  | 2026-05-28 | qiang.wang |  | CMS network card issue | TIANXIANG YUAN | Low | 2026-05-28 |  | 2026-05-28 | Closed | ip -s link show --> systemctl restart NetwrokManger, fixed issue
P-1480 |  | 2026-05-27 | Ashok | qiang.wang | Juniper VPM issue | Nitheesh | High | 2026-05-27 |  | 2026-05-29 | Closed
P-1480 |  | 2026-05-27 | Ashok | jun.zhang | juniper VPN issue | Nitheesh | High | 2026-05-27 |  | 2026-06-29 | Closed
p-1725 |  |  | Ashok | jun.zhang | static route issue | Nitheesh | High | 2026-05-27 |  | 2026-05-29 | Closed
p-1615 |  | 2026-05-28 | Ashok |  | mppc data not receiving to cutomer | saritha | High | 2026-05-28 | New requirements | 2026-05-28 | Closed | HA Cconfigution secondary firewall was forwording
IN-01 |  | 2026-05-28 | Ashok |  | MGMT ip were not pinging | praveen | High | 2026-05-28 | New requirements | 2026-05-28 | Closed | mgmt ip segment was 192.168.10.99
p-1615 |  | 2026-05-28 | Ashok |  | Time Sync issue | mayur | High | 2026-05-28 | New requirements | 2026-05-28 | Closed | after doing Nat on inside firewall its worked
p-8010 |  | 2026-05-28 | Ashok | jun.zhang | juniper vpn down | Nitheesh | High | 2026-05-28 | New requirements | 2026-05-28 | Closed | after restarting juniper server it got resolved
P-1748 |  | 2026-05-28 | Ashok |  | OPC PORTS NOT OPEN | niyasdeen | Medium | 2026-05-28 | New requirements | 2026-05-28 | Closed
iIN-01 |  | 2026-05-28 | Ashok |  | IAF DATA FORWORDING | praveen kumar | Medium | 2026-05-28 | New requirements | 2026-05-28 | Closed
P-1707 |  | 2026-05-29 | Ashok | qiang.wang | Connnect to Zonew sw 1 unable reach outstide firewall |  | High |  |  | 2026-06-04 | Closed
p-1429 |  | 2026-05-29 | qiang.wang | jun.zhang | EDGE pre check | Aaron | High | 2026-05-29 |  | 2026-06-01 | Closed | Customer public IP issue resolved
P-1725 |  | 2026-05-26 | yuan.qin |  | Galileo can not upload data to cloud | rongrong.huang | High | 2026-05-26 | Server crash | 2026-05-26 | Closed | The server should enable auto start
P-1749 |  | 2026-05-22 | yuan.qin |  | Some files can not upload to scada server the speed is too slow | Niyasdeen | High | 2026-05-26 | Network cabe connection error | 2026-05-26 | Closed | The laptop's network card has some issue, when I change a new laptop this issue restored
P-1843 |  | 2026-05-27 | yuan.qin |  | Galileo data usually shutdown | rongrong.huang | Medium | 2026-05-27 | Server crash | 2026-05-27 | Closed | The virtual machine has the same space as the physical machine
P-1721 |  | 2026-05-28 | yuan.qin |  | CMS ntp issue | rongrong.huang | Medium | 2026-05-28 | Server crash | 2026-05-28 | Closed
P-8020 |  | 2026-05-30 | yuan.qin |  | Galileo can not upload data to cloud | rongrong.huang | High | 2026-05-29 | Server crash | 2026-05-30 | Closed | The server configuration has some issue
P-1566 |  | 2026-06-01 | Shadab.pinitod | qiang.wang | Cisco sw configuration issue |  | Medium |  |  | 2026-06-01 | Closed | configuration completed
P-1429 |  | 2026-06-01 | Shadab.pinitod | qiang.wang | public ip issue | jun zhang | Medium | 2026-06-01 |  | 2026-06-01 | Closed | public ip and gatewai is not reachable.
P-1812 |  | 2026-05-29 | Mayur Tisage | jun.zhang | SCADA Servers SSH not working and Servers getting hanged | Niteesh | High | 2026-05-30 | Network cabe connection error | 2026-06-01 | Closed | The issue occurred due to Core Switch 2 was not working properly, we removed the cables betwenn core switch and servers, the issue resolved.
P-1615 |  | 2026-06-01 | Shadab.pinitod |  | Ports are not open at firewall end | Sarita | High | 2026-06-01 |  | 2026-06-01 | Closed | completed
P-1429 |  |  | Mayur Tisage |  | Telnet not working in galilio data | sangappa | Low | 2026-06-01 | New requirements | 2026-06-02 | Closed | telnet ports added in the server, issue closed
P-8006 | CS0215879 | 2026-06-02 | Mayur Tisage | yuan.qin | 8006The network link between primary and standby bridge adapters is down. Please ask the architecture team for assistance. |  | Medium | 2026-06-02 |  | 2026-06-03 | Closed | The issue fixed by Infra Team Mate after remote support it and confirmed by end user
P-8003 | CS0215897 | 2026-06-02 | Shadab.pinitod | yuan.qin | Babra Communication fluctuation |  | Medium | 2026-06-02 |  | 2026-06-03 | Closed | Master switch configuration updated
P-8006 |  |  | Mayur Tisage |  | Scada server bridge issue | Jin Zhang(Outsourcing | Low | 2026-06-03 | Network cabe connection error | 2026-06-03 | Closed | Issue resolved
P-1578 | CS0215961 | 2026-06-03 | Marimuthu | yuan.qin | P-1578 The server OS for Galileo needs to be in ubuntu | [5 empty] | Closed | Reinstalled the OS and re configured
P-1615 |  | 2026-06-03 | Mayur Tisage | jun.zhang | SCADA server Core switch ip is not pinging | Ashok Arvind | Low | 2026-06-03 | Network cabe connection error | 2026-06-03 | Closed
P-1566 |  | 2026-06-03 | Shadab.pinitod |  | Ring Switch Configuration |  | Medium | 2026-06-03 | New requirements | 2026-06-03 | Closed | configuration completed
p-1660 |  | 2026-06-03 | Ashok | qiang.wang | mppc,opc forwording | harie | Medium | 2026-06-03 | New requirements | 2026-06-03 | Closed | configuration completed
p-1615 |  | 2026-06-03 | Ashok |  | scada secondary not reachable from core | Sarita | high | 2026-06-03 | Network cabe connection error | 2026-06-03 | Closed | subnet issue in server
p-8014 |  | 2026-06-03 | Ashok | qiang.wang | wtd disconnected from scadA and EMS | praveen kumar | high | 2026-06-03 | Network cabe connection error | 2026-06-03 | Closed | core switch ports were down enabled
P-1567 |  | 2026-06-04 | Shadab.pinitod | yuan.qin | VPN tunnel is showing down | Veeresh | Medium | 2026-06-04 |  | 2026-06-04 | Closed | VPN tunnel is UP after changing the parameter in IPSEC VPN
P-8014 |  | 2026-06-04 | Shadab.pinitod | qiang.wang | Internet issue | Yuan Qin | Medium | 2026-06-04 |  | 2026-06-04 | Closed | Internet and GAteway is not reachable. checking with customer
P-1466 |  | 2026-06-05 | Shadab.pinitod | qiang.wang | VPN tunnel is showing down | Veeresh | Medium | Medium |  | 2026-06-05 | Closed | changes the prameter of IPSEC VPN and now VPN came up.
P-1546 |  | 2026-06-05 | Shadab.pinitod | jun.zhang | from Core switch ip is not pinging | Mayur | Medium | Medium | Network cabe connection error | 2026-06-05 | Closed | Completed
P-1429 |  | 2026-06-06 | Mayur Tisage | qiang.wang | NTP synchronization | Yanjun Ning | Medium | 2026-06-06 |  |  | Closed | Routes added and solved
p-1741 |  | 2026-06-09 | Ashok | qiang.wang | opc mppc forwarding | harie | Medium | 2026-06-06 | New requirements | 2026-06-06 | Closed
P-1428 |  | 2026-06-08 | Shadab.pinitod |  | VPN tunnel down | Veeresh | Medium | 2026-06-08 |  | 2026-06-08 | Closed | Changed the parameter of VPN and changed the public ip at RCC end.
P-1707 |  | 2026-06-09 | Shadab.pinitod |  | Timesyn Issue | Abdulla | Medium | 2026-06-09 |  |  | Closed | Routes added and solved
P-1546 |  | 2026-06-08 | Shadab.pinitod | qiang.wang | Time sync | qiang.wang | Medium | 2026-06-08 |  |  | Closed
P-1610 |  | 2026-06-09 | Shadab.pinitod |  | public ip changed | Nitheesh | Medium | 2026-06-09 |  | 2026-06-09 | Closed | configuration completed but gateway and 8.8.8.8 is not pinging.customer need to connect internet cable
P-1741 |  | 2026-06-09 | Ashok | yuan.qin | dataforwording | harie | Medium | 2026-06-09 |  | 2026-06-09 | Closed | port 5020 not open server side port not open
P-8002 |  | 2026-06-09 | Shadab.pinitod |  | pre checked issue | Nitheesh | Medium | 2026-06-09 |  | 2026-06-09 | Closed | Pre checked completed.
P-1660 |  | 2026-06-09 | Shadab.pinitod |  | dataforwording | harie | Medium | 2026-06-09 | New requirements | 2026-06-09 | Closed | configuration completed
P-1749 |  | 2026-06-09 | Shadab.pinitod | jun.zhang | dataforwording | Niyasdeen | Medium | 2026-06-09 | New requirements | 2026-06-09 | Closed | new configuration completed
P-1578 |  | 2026-06-10 | Ashok | qiang.wang | Torrent kambaliya (P-1578) Customer VPN account creation | Nitheesh | Medium |  | New requirements |  | Closed | created vpn
P-1812 |  | 2026-06-10 | Ashok | qiang.wang | Opera Vayu (P-1812) Customer VPN account creation | Nitheesh | Medium |  | New requirements |  | Closed | vpn created
P-1407 |  | 2026-05-20 | Marimuthu |  | Edgegateway issue | Nitheesh/Aaron | Medium | 2026-06-09 | Server crash | 2026-06-10 | Closed | Edgegateway server automatically shutdown then check the status now is working .
P-1429 |  | 2026-06-10 | Marimuthu | yuan.qin | Both EMS not recahble | Sangappa | Medium | 2026-06-10 | Server crash | 2026-06-10 | Closed | I'm checking the issue both EMS is powerd off so then turn the EMS now server is reachbled
P-1873 |  | 2026-06-10 | Marimuthu | yuan.qin | All server is not reachble | Niyasdin | Medium | 2026-06-11 | Server crash | 2026-06-11 | Closed | I checked the issue network switch differentely conected then ask to site cotrrect the network connectivity after that all server is pinking sucessfully.
P-1578 |  | 2026-06-12 | Shadab.pinitod | jun.zhang | 1. Pre-check all failed 2. Additionally, telnet s3.ap-south-1.amazonaws.com also | Aaron | Medium |  | New requirements |  | Closed | ILL restored and pre check completed
P-3599 | CS0216160 | 2026-06-12 | Marimuthu | yuan.qin | Prec check for Galielo need to follow checklist since new site | WU Honxia | Medium |  | New requirements |  | Closed | Checklist provided
P-1576 | CS0216158 |  | Mayur Tisage |  | P-1576 public ip issue(Galielo data VM not connecting to inetrent) | WU Honxia | Medium |  | New requirements |  | Closed
P-3599 |  | 2026-06-12 | Mayur Tisage | qiang.wang | EMS & PPC servers Restoration | sarita | medium |  | New requirements |  | Closed | Restored proper connections, investigated the issue and provided to software team. Issure resolved
P-3599 |  | 2026-06-12 | Shadab.pinitod |  | IPSec tunnel configuration | Veeresh | medium |  | New requirements |  | Closed | VPN tunnel is UP.
P-1566 |  | 2026-06-12 | Marimuthu | yuan.qin | time synchorinastion | sarita | medium |  | New requirements | 2026-06-18 | Closed | Time issue resolved
P-1873 |  | 2026-06-12 | Shadab.pinitod | jun.zhang | Data forwarding requirement | Niyas | medium |  | New requirements |  | Closed
P-1707 |  | 2026-06-12 | Shadab.pinitod | jun.zhang | Reconfiguration of MPPC to EMS | Abdullah | medium | 2026-06-12 |  | 2026-06-12 | Closed | completed
P-8002 |  | 2026-06-13 | Mayur Tisage | qiang.wang | Edge VM not reachable | Shadab | Medium | 2026-06-13 |  | 2026-06-13 | Closed | issue resolved, duplicate ips found
P-1707 |  | 2026-06-16 | Shadab.pinitod | jun.zhang | IPSec tunnel configuration |  | medium | 2026-06-16 | New requirements | 2026-06-16 | Closed | Completed and also tunnel is UP.
P-1429 |  | 2026-06-19 | Mayur Tisage | jun.zhang | EMS Time not sync | Sangappa | medium | 2026-06-19 |  | 2026-06-19 | Closed | Issure resolved.
P-1631 |  | 2026-06-18 | Mayur Tisage | jun.zhang | EMS server not pinging | Harie | medium | 2026-06-18 |  | 2026-06-18 | Closed | Issure resolved.
P-1478 |  | 2026-06-17 | Mayur Tisage | jun.zhang | Front end and backend server not pinging | Niteesh | Medium | 2026-06-17 |  | 2026-06-18 | Closed | Issure resolved.
P-8012 |  | 2026-06-18 | Mayur Tisage | yuan.qin | Amazon services not reaching internet issue | Niteesh | Medium | 2026-06-18 |  | 2026-06-18 | Closed | Dns was the issue, resolved
P-1576 |  | 2026-06-19 | Mayur Tisage | yuan.qin | Data vm cannot reach internet | Niteesh | Medium | 2026-06-19 |  | 2026-06-19 | Closed | route was the issue, resolved
P-1748 |  | 2026-06-19 | Mayur Tisage | yuan.qin | EMS and Scada time not sync | Niyasdeen | Medium | 2026-06-19 |  | 2026-06-19 | Closed | route was the issue, resolved
P-1748 |  | 2026-06-19 | Shadab.pinitod | jun.zhang | Data forwarding requirement | Niyasdeen | Medium | 2026-06-19 |  | 2026-06-19 | Closed | new configuration completed
P-1707 |  | 2026-06-18 | Shadab.pinitod | jun.zhang | Ports open issue at firewall end | Abdullah | High | 2026-06-18 |  | 2026-06-18 | Closed | One extra cable connected to switch
P-1748 |  | 2026-06-18 | Shadab.pinitod | jun.zhang | reset HA cluster | Praveen | Medium | 2026-06-18 |  | 2026-06-18 | Closed | From scada server 192 segment ips are not pinging thats why we have reseted the cluster and Again created.and now it is working fine.
P-8014 |  | 2026-06-19 | Shadab.pinitod | jun.zhang | New IPSEC vpn created | Veeresh | Medium | 2026-06-19 |  | 2026-06-19 | Closed | new ipsec vpn created and also tunnel is UP.
p-1548 |  | 2026-06-18 | Ashok |  | public ip down | naveen | high | 2026-06-17 |  | 2026-06-17 | Closed | customer provided new ip also connection was wrong in outside firewall 1 to customer firewall
P-1707 |  | 2026-06-22 | Shadab.pinitod | jun.zhang | Data forwarding opc to scada | Abdullah | Medium | 2026-06-22 |  | 2026-06-22 | Closed
P-1725 |  | 2026-06-23 | qiang.wang |  | Edge gateway can not login | Aaron | Medium | 2026-06-23 |  | 2026-06-23 | Closed | Some security policy may have issue,reset password and confirmed with Aaron
P-1725 |  | 2026-06-23 | qiang.wang |  | SSL VPN unable reach | Customer | High | 2026-06-23 |  | 2026-06-23 | Closed | remote check fortigate working no issue, found SSL and Freeraidus server shutdown, powner on and check autostart
p-1840 |  | 2026-06-23 | jun.zhang |  | juniper VPN unable reach | Customer | High | 2026-06-23 |  | 2026-06-23 | Closed | The customer changed their public IP, which caused an SSL VPN certificate error
P-1466 |  | 2026-06-23 | jun.zhang |  | juniper VPN unable reach | Customer | High | 2026-06-23 | Network cabe connection error |  | Closed | ILL issue
P-1566 |  | 2026-06-22 | jun.zhang |  | time sync issue | Marimuthu | Medium | 2026-06-22 |  | 2026-06-23 | Closed | Gateway configuration wrong,and lack security policy to pass throngh the traffic
p-1566 |  | 2026-06-23 | Ashok |  | time server config |  | high | 2026-06-23 |  | 2026-06-23 | Closed | time server config
P-8004 |  |  | Mayur Tisage |  | EMS 1 HDD Backup and Restore to SSD | Jin Zhang(Outsourcing | medium | 2026-06-23 |  | 2026-06-23 | Closed | Took the backup and restore to SSD
P-1750 |  | 2026-06-24 | Shadab.pinitod |  | core 1 & 2 switch RSTP |  | medium | 2026-06-24 |  | 2026-06-24 | Closed | Explained RSTP and issue solved
P8022 |  | 2026-06-24 | yuan.qin |  | Galileo APP,cms and STD can not pinging Galileo Data | rongronghuang | medium | 2026-06-24 |  | 2026-06-24 | Closed | The Galileo data lack routing
p-IN01 |  | 2026-06-24 | Ashok |  | IAF Gateway config | praveen | medium | 2026-06-24 |  | 2026-06-24 | Closed | new requirement
K-0334 |  | 2026-06-24 | Ashok | qiang.wang | INTERNET FIREWALL | praveen | medium | 2026-06-24 |  | 2026-06-24 | Closed | new requirement
K-0334 |  | 2026-06-24 | Ashok | qiang.wang | DMZ FIREWALL CONFIG | praveen | medium | 2026-06-24 |  | 2026-06-24 | Closed
P-1748 |  | 2026-06-24 | Ashok |  | MINI RTU FIREWALL CONFIG | praveen | medium | 2026-06-24 |  | 2026-06-24 | Closed | compleated
P-1749 |  | 2026-06-24 | Shadab.pinitod | jun.zhang | SCADA to SRLDC port isssue | praveen | high | 2026-06-24 |  | 2026-06-24 | Closed | compleated
P-1429 |  | 2026-06-24 | Shadab.pinitod | jun.zhang | wiring connection was wrong | Sangappa | medium | 2026-06-24 |  | 2026-06-24 | Closed | cable conenction was wrong thats why scada back end server 2 ip is not pinging and also restarted the server once after propely connected it is pinging.
P-1436 |  | 2026-06-24 | yuan.qin |  | SCADA standby server on-site is unreachable by ping | Nitheesh | medium | 2026-06-25 |  | 2026-06-26 | Closed | The network cable connection is wrong
P-1586 |  | 2026-06-29 | Shadab.pinitod | jun.zhang | vpn tunnel down | Veeresh | medium | 2026-06-29 |  | 2026-06-29 | Closed | changed the parameter in ipsec vpn and vpn is UP.
P-1873 |  | 2026-06-30 | Mayur Tisage | qiang.wang | Time sync issue | Niyasdeen | medium | 2026-06-30 |  | 2026-06-30 | Closed | Issue resolved
P-1578 |  | 2026-06-30 | Mayur Tisage | yuan.qin | Turbine Time sync | Niteesh | medium | 2026-06-30 |  | 2026-06-30 | Closed | Issue resolved
K-334 |  | 2026-06-29 | Mayur Tisage | jun.zhang | Monitor and Security server installation | Jun Zhang | medium | 2026-06-29 |  | 2026-06-29 | Closed | Installation completed
K-334 |  | 2026-06-29 | Ashok | Marimuthu | DMZ FIREWALL ISSUE |  | medium | 2026-06-29 |  | 2026-06-29 | Closed | OS CORREPTED RE INSTALLED
K-334 |  | 2026-06-29 | Ashok |  | DMZ SWITCH CONFIGURTION |  | medium | 2026-06-29 |  | 2026-06-29 | Closed | Installation completed
P-1846 |  | 2026-07-01 | Shadab.pinitod | qiang.wang | data forwarding ems to mppc | Abdullah | medium | 2026-07-01 | New requirements | 2026-07-01 | Closed | configuration is completed both ports are open at firewall end
P-1846 |  | 2026-07-01 | Shadab.pinitod |  | data forwarding opc to scada | Abdullah | medium | 2026-07-01 | New requirements | 2026-07-01 | Closed | configuration is completed both ports are open at firewall end
p-1511 |  | 2026-07-01 | Ashok | qiang.wang | data forwarding substation | jeffin | medium | 2026-07-01 |  | 2026-07-01 | Closed | configuration is completed both ports are open at firewall end
P-1748 |  | 2026-07-01 | Mayur Tisage | yuan.qin | STD VM telnet issue | Niteesh | medium | 2026-07-01 |  | 2026-07-01 | Closed | added the correct route, issue resolved
K-334 |  | 2026-07-01 | Mayur Tisage | qiang.wang | Monitor and Security server Ip configuration | Jun Zhang | medium | 2026-07-01 |  | 2026-07-01 | Closed | Ip Configuration completed
P-1566 |  | 2026-07-01 | Shadab.pinitod | jun.zhang | HA config restored and firewalls lights not flowing | sarita | medium | 2026-07-01 |  | 2026-07-01 | Closed | HA is sync now and also port is glowing on all the ports .
P-1741 |  | 2026-06-30 | Marimuthu | yuan.qin | time synchorinastion | Hari | Medium | 01-07-2026 | New requirements | 2026-07-01 | Closed | Time issue resolved
p-1511 |  | 2026-07-01 | Ashok |  | data forwarding substation | jeffin | medium | 2026-07-01 |  | 2026-07-01 | Closed | server ports were not open
p-1748 |  | 2026-07-01 | Ashok | qiang.wang | auto swapping ha | niyasdeen | high | 2026-07-01 |  | 2026-07-01 | Closed | after balancing cpu core its become stable
P-1812 |  | 2026-07-02 | Shadab.pinitod | qiang.wang | data forwarding of opc to scada | Sangappa | Medium | 2026-07-02 | New requirements | 2026-07-02 | Closed | new requirement
P-1566 |  | 2026-07-02 | Shadab.pinitod | jun.zhang | data forwarding of WRLDC to Scada and OPC to scada | Sarita | Medium | 2026-07-02 | New requirements | 2026-07-02 | Closed | configuration completed and also data is coming
P-1566 |  | 2026-07-02 | Shadab.pinitod |  | data forwarding of EMS1, EMS2 to MPPC1, MPPC2 | Sarita | Medium | 2026-07-02 | New requirements | 2026-07-02 | Closed | configuration completed and also data is coming
P-1731 |  | 2026-07-03 | Shadab.pinitod | qiang.wang | data forwarding of scada to srldc1 and scada to srldc2 | Sarita | Medium | 2026-07-03 | New requirements | 2026-07-03 | Closed | configuration completed
P-8001 |  | 2026-07-07 | Marimuthu | yuan.qin | EMS not working | Niteesh | High | 2026-07-07 | Network cabe connection error | 2026-07-07 | Closed | I'm checked that issue now EMS is working fine
P-1578 |  | 2026-07-03 | Marimuthu | qiang.wang | time synchorinastion | Niteesh | Medium | 2026-07-03 | New requirements | 2026-07-03 | Closed | time synchorinastion resolved form server end
k-0334 |  | 2026-07-07 | Ashok | qiang.wang | vpn creation | Niteesh | Medium | 2026-07-07 |  | 2026-07-07 | Closed | vpn created
k-0334 |  | 2026-07-07 | Ashok | qiang.wang | scada monitring | Niteesh | Medium | 2026-07-07 |  | 2026-07-07 | Closed | created the scada monitering
p-1873 |  | 2026-07-07 | Ashok | jun.zhang | mmpc forwording | niyaz | Medium | 2026-07-07 |  | 2026-07-07 | Closed | compled the config
p-1578 |  | 2026-07-07 | Ashok | qiang.wang | vpn creation | nitheesh | Medium | 2026-07-07 |  | 2026-07-07 | Closed | vpn created
p-1578 |  | 2026-07-07 | Ashok |  | scada monitring | nitheesh | Medium | 2026-07-07 |  | 2026-07-07 | Closed | created the scada monitering
k-0334 |  | 2026-07-07 | Ashok | yuan.qin | user creation | praveen | Medium | 2026-07-07 |  | 2026-07-07 | Closed | created the users
k-0334 |  | 2026-07-07 | Ashok |  | EMS_monitering port 8702-8701 | praveen | Medium | 2026-07-07 |  | 2026-07-07 | Closed | modified the port number
P-1897 |  | 2026-07-07 | Shadab.pinitod | jun.zhang | Checkpoint OS restoration and HA configuration |  | Medium | 2026-07-07 | New requirements | 2026-07-07 | Closed | through pendrive restore the os and created new HA.
P-1653 |  | 2026-07-07 | Mayur Tisage | qiang.wang | Scada configuration | Niteesh | Medium | 2026-07-07 | New requirements | 2026-07-07 | Closed | Server configured
K-0299 |  | 2026-07-07 | Mayur Tisage |  | Monitor Server configuration | Niteesh | Medium | 2026-07-07 | New requirements | 2026-07-07 | Closed | Server configured
p-1707 |  | 2026-07-08 | Ashok | qiang.wang | 6666 telnet | mari muthu | Medium | 2026-07-08 | New requirements | 2026-07-08 | Closed | sevcer port 6666 not enabled
p-1707 |  | 2026-07-08 | Ashok | jun.zhang | data forwording issue opc | abdulla | Medium | 2026-07-08 | New requirements | 2026-07-08 | Closed | ip set up wrong
4k-0034 |  | 2026-07-08 | Ashok | qiang.wang | ems monitering | pravee | Medium | 2026-07-08 | New requirements | 2026-07-08 | Closed | configured and provided to customer
P-1897 |  | 2026-07-08 | Shadab.pinitod | jun.zhang | inside firewall os issue and HA sync | Niteesh | Medium | 2026-07-08 | New requirements | 2026-07-08 | Closed | HA is sync and inside firewall os issue resolved.
P-1707 |  | 2026-07-08 | Marimuthu |  | telnet issue STD edge server | Abdulla | Medium | 2026-07-08 | New requirements | 2026-07-08 | Closed | After add the routing file the issue resolved
P-1707 |  | 2026-07-08 | Marimuthu | yuan.qin | Interface issue | Abdulla | Medium | 2026-07-08 | New requirements | 2026-07-08 | Closed | Interface name is not shwoing nmi network connection after change the remane the intrafce name is shwoing issue resolved
P-1653 |  | 2026-07-08 | Shadab.pinitod | qiang.wang | Swithes Configuratuion | Niteesh | Medium | 2026-07-08 | New requirements | 2026-07-08 | Closed | New Switches configuration
p-8004 |  | 2026-07-09 | Ashok |  | turbine ip not reachable | sarita | Medium | 2026-07-09 | New requirements | 2026-07-09 | Closed | ip are reachable server os down
p-1750 |  | 2026-07-09 | Ashok | qiang.wang | outside ha ip not reachable | mayur | Medium | 2026-07-09 | New requirements | 2026-07-09 | Closed | ha core issue fixes nowf fixed
p-1750 |  | 2026-07-09 | Ashok |  | inside Ha swapping issue |  | Medium | 2026-07-09 | New requirements | 2026-07-09 | Closed | ha core issue fixes nowf fixed
P-1653 |  | 2026-07-09 | Shadab.pinitod | jun.zhang | Core switches configuration | Nitheesh | Medium | 2026-07-09 | New requirements | 2026-07-09 | Closed | completed
p-1731 |  | 2026-07-09 | Ashok |  | scada srldc1 forwording | sarita | Medium | 2026-07-09 | New requirements | 2026-07-09 | Closed | completed
IN-01 |  | 2026-07-10 | Ashok | qiang.wang | iil check | nitheesh | Medium | 2026-07-10 | New requirements | 2026-07-10 | Closed | reachable
IN-01 |  | 2026-07-10 | Ashok |  | iaf forwording ip change | praveen | Medium | 2026-07-10 | New requirements | 2026-07-10 | Closed | reachable
P-1653 |  | 2026-07-10 | Shadab.pinitod | jun.zhang | Outside fw 1, 2 configuration | nitheesh | Medium | 2026-07-10 | New requirements | 2026-07-10 | Closed | compeleted and also HA is sync
K-0334 |  | 2026-06-24 | Ashok | qiang.wang | VPN CREATINON CONFIG | praveen | medium | 2026-06-24 |  | 2026-07-08 | Closed | New VPN users created
P-1707 |  | 2026-07-11 | Mayur Tisage | jun.zhang | SCADA Health Backend server not reachable via Core IP + EMS Time sync issues | Abdulla | Medium |  | New requirements |  | Closed | time synchorinastion resolved form server end
P-1631 |  | 2025-07-11 | Marimuthu |  | Time Sync Issue | Harie Vignesh | Medium |  | New requirements | 13-07-2026 | Closed | Time issue resolved
P-1653 |  | 2025-07-11 | Shadab.pinitod |  | Firewall configuration with HA | Nitheesh | Medium | 2025-07-11 | New requirements | 2025-07-11 | Closed | completed.
P-1749 |  | 2025-07-11 | Ashok |  | ILL Down | Revappa | Medium |  | New requirements | 2026-07-14 | Closed | completed.
P-1731 |  | 2025-07-11 | Ashok |  | ILL Down + Pre Check | Suthan | Medium |  | New requirements | 2026-07-28 | Closed
P-1897 |  | 2025-07-11 | Shadab.pinitod |  | ILL Down | Nitheesh | Medium |  | New requirements |  | Closed
P-1653 |  | 2025-07-11 | Shadab.pinitod |  | ILL Down | Ritesh | Medium |  | New requirements |  | Closed | Extranet Communication working fine
P-1812 |  | 2025-07-11 | Mayur Tisage |  | rst step pre-check fail + Edge server unable to ping and access + please help to verify pre-check once you can access Edge server | Aaron | Medium |  | New requirements |  | Closed | Serial Cabled arranged and reconfigured the systems
P-1615 |  | 2025-07-11 | Ashok |  | HA issue + PreCheck | Harie | Medium |  | New requirements | 14-07-2026 | Closed | now Ha is stable
P-1610 |  | 2025-07-11 | Mayur Tisage |  | unable to telnet SCADA1 port 2406 from Edgegateway + please make sure NAT is disabled | Aaron | Medium |  | New requirements |  | Closed | telnet ports added in the server, issue closed
P-1749 |  | 2026-07-11 | Marimuthu | jun.zhang | issues, pre-check failed + Edgegateway server unable to log in with original password, tried many different password | Aaron | Medium |  | New requirements |  | Closed | Issue resolved password logined done
P-1750 |  | 2025-07-11 | Mayur Tisage |  | Galileo servers reachability | Wn Shen | Medium |  | New requirements |  | Closed
P-1653 |  | 2025-07-11 | Mayur Tisage |  | scada and EMS servers not pinging | .Sangappa | High |  | New requirements |  | Closed
P-1578 |  | 2025-07-11 | Ashok |  | VPN Details | Nitheesh | Medium |  | New requirements | 2026-07-13 | Closed | completed
p-1578 |  | 2026-07-13 | Ashok | qiang.wang | scada moniter page | Nitheesh | Medium |  | New requirements | 2026-07-13 | Closed | completed
k-0334 |  | 2026-07-13 | Ashok |  | data forwording issue | Nitheesh | Medium |  | New requirements | 2026-07-13 | Closed | due to cable error this happed
p-1731 |  | 2026-07-13 | Ashok | qiang.wang | scada data forwording issue | sarita | Medium |  | New requirements | 2026-07-13 | Closed | configured
p-1731 |  | 2026-07-13 | Ashok | jun.zhang | mppcdata forwording issue | sarita | Medium |  | New requirements | 2026-07-13 | Closed | configured
p-1631 |  | 2026-07-13 | Ashok | qiang.wang | TIME SERVER IP IS NOT REACHBLE | MARI muthu | Medium |  | New requirements | 2026-07-13 | Closed | HA broken
P-1750 |  | 2026-07-13 | Mayur Tisage |  | Time synchronization issue in SCADA and EMS | Niteesh | Medium |  |  |  | Closed | Issure resolved.
P-1886 |  | 2026-07-14 | Shadab.pinitod | jun.zhang | all Zone switch configuration | Niteesh | Medium |  | New requirements | 2026-07-14 | Closed | completed
P-1407 |  | 2026-07-14 | Marimuthu | qiang.wang | Scada wep page monitoring hang issue | jayapraksh | Medium |  | New requirements | 14-07-2026 | Closed | The Java application was experiencing high resource utilization. We investigated and rectified the issue, and it is now functioning normally.
p-1653 |  | 2026-07-14 | Ashok |  | outside Ha vip stabilize | shadab | Medium |  |  | 14-07-2026 | Closed | configured
p-1750 |  | 2026-07-14 | Ashok | yuan.qin | check point vip not reachable | mayur | Medium |  |  | 14-07-2026 | Closed | configured
p-1749 |  | 2026-07-14 | Shadab.pinitod | Ashok | wan ip config issue 8.8.8.8 | ravi | Medium |  |  | 14-07-2026 | Closed | configured
K-334 |  | 2026-07-15 | Mayur Tisage |  | FEP server main and standby installed and configured | Pravin | medium |  |  | 2026-07-15 | Closed | Configured
1812 |  | 2026-07-15 | Mayur Tisage |  | WTG health BE server os installed | Niteesh | medium |  |  | 2026-07-15 | Closed | Installed
P-1653 |  | 2026-07-15 | Shadab.pinitod | jun.zhang | fortigate HA issue | Nitheesh | medium |  |  | 2026-07-15 | Closed | configured
1749 |  | 2026-07-15 | Mayur Tisage | jun.zhang | Core switch ips not pinging | Niteesh | Medium |  |  | 2026-07-15 | Closed | ips are pingng now
P-1660 |  | 2026-07-15 |  |  | Python application not woring in Windows server 2025 | Praveen | medium |  |  | 2026-07-15 | Closed | Now it's working and server details also showing
P-1653 |  | 2026-07-15 | Shadab.pinitod | jun.zhang | Data forwarding wrldc to scada | .Sangappa | medium |  | New requirements | 2026-07-15 | Closed | complted and ports are open
P-1660 |  | 2026-07-15 | Marimuthu | jun.zhang | Python application issue on windows 2025 server | Praveen | Medium |  | New requirements | 15-07-2026 | Closed | Again install the python software and check modules then issue resolved and server deatils shwoing
P-1886 |  | 2026-07-16 | Shadab.pinitod | jun.zhang | Core switch configuration | Niteesh | Medium |  | New requirements | 2026-07-16 | Closed | configuration completed
P-8004 |  | 2026-07-16 | Marimuthu | yuan.qin | Scada BE 1 server HD space issue | Praveen | Medium |  | New requirements | 2026-07-16 | Closed | Scada BE 1 server HDD space 1TB extended
P-1453 |  | 2026-07-16 | Marimuthu | jun.zhang | Scada BE 2 server 10 serias IP not reachble | Harie Vignesh | Medium |  | Network cabe connection error |  | Closed | Network cable issue after corrcetely connected the cable 10 series IP reachble and issue resolved.
P-1886 |  | 2026-07-17 | Shadab.pinitod | jun.zhang | checkpoint Os issue |  | Medium |  |  | 2026-07-17 | Closed
P-1653 |  | 2026-07-18 | Shadab.pinitod | jun.zhang | Data forwarding requirement changes | Praveen | High |  |  | 2026-07-18 | Closed | Data is coming
p-1748 |  | 2026-07-18 | Ashok | qiang.wang | vpn creatiojn | nitheesh | Medium |  | New requirements | 2026-07-18 | Closed | creaated
p-1750 |  | 2026-07-18 | Ashok |  | insdi firewall HA Issues | mayur | Medium |  | New requirements | 2026-07-18 | Closed | configured
P-1886 |  | 2026-07-20 | Shadab.pinitod | jun.zhang | Inside fw 1 and inside fw 2 configuration and HA sync | nitheesh | Medium |  | New requirements | 2026-07-20 | Closed | configured and HA sync
P-1886 |  | 2026-07-20 | Shadab.pinitod | jun.zhang | Outside fw 1 and outside fw 2 configuration and HA sync | nitheesh | Medium |  | New requirements | 2026-07-20 | Closed | configured and HA sync
P-8004 |  | 2026-07-20 | Mayur Tisage |  | Core Switch Ip was not pining | Jin Zhang(Outsourcing | medium |  |  | 2026-07-20 | Closed | Its a centos os ports were not assigned to the ip correctly, after that issue resolved
P-1632 |  | 2026-07-21 | Shadab.pinitod |  | OPC to SCADA data forwarding | Jeffin Vinod | medium |  | New requirements | 2026-07-21 | Closed | configuration completed
P-1578 |  | 2026-07-21 | Mayur Tisage | yuan.qin | PLC Ips not pinging 1578 | Marimuthu | medium |  |  | 2026-07-21 | Closed | Issue resolved
P-1962 |  | 2026-07-21 | Mayur Tisage |  | Scada configuration | Niteesh | medium |  | New requirements | 2026-07-21 | Closed | configuration completed
P-1887 |  | 2026-07-21 | Shadab.pinitod |  | Zone1 and zone 2 switch configuration | Niteesh | medium |  | New requirements | 2026-07-21 | Closed | configuration completed
P-1731 |  | 2026-07-21 | Shadab.pinitod | Ashok | Port open issue | sarita | medium |  | New requirements | 2026-07-21 | Closed | Ports are open
p-1749 |  | 2026-07-21 | Ashok | jun.zhang | Ha ip issue | mayur | medium |  | New requirements | 2026-07-21 | Closed | resolved
p-1653 |  | 2026-07-21 | Ashok |  | time server config | mari muthu | medium |  | New requirements | 2026-07-21 | Closed | time server configured
p-1748 |  | 2026-07-21 | Ashok | yuan.qin | time server config | shadadab | medium |  | New requirements | 2026-07-21 | Closed | time server configured
p-1729 |  | 2026-07-21 | Ashok | yuan.qin | inside outside firewall config | ashok | medium |  |  | 2026-07-21 | Closed | config
P-1631 |  | 2026-07-22 | Shadab.pinitod |  | opc to scada data forwarding | Harie Vignesh | medium |  | New requirements | 2026-07-22 | Closed | config completed
P-1731 |  | 2026-07-22 | Shadab.pinitod |  | Ems to mppc data forwarding | sarita | medium |  | New requirements | 2026-07-22 | Closed | config completed
P-8020 |  | 2026-07-22 | Mayur Tisage | yuan.qin | WTG Health Front end and Backend server autostart configuration | Niteesh | medium |  |  | 2026-07-22 | Closed | config completed
P-1731 |  | 2026-07-22 | Shadab.pinitod |  | opc to scada data forwarding | sarita | medium |  | New requirements | 2026-07-22 | Closed | config completed
P-1653 |  | 2026-07-23 | Shadab.pinitod |  | mppc2 to ems2 data forwarding | Sangappa | medium |  | New requirements | 2026-07-23 | Closed | config completed
P-1749 |  | 2026-07-23 | Shadab.pinitod | jun.zhang | opc to scada data forwarding | Niyasdeen | medium |  | New requirements | 2026-07-23 | Closed | config completed
P-1897 |  | 2026-07-23 | Shadab.pinitod | jun.zhang | switch ip is not pinging and also servers | Marimuthu | medium |  | New requirements | 2026-07-23 | Closed | cabling issue and laptop ip was setted wrong.
P-1731 |  | 2026-07-23 | Shadab.pinitod |  | ems 1 to srldc gw1 data forwarding | sarita | medium |  | New requirements | 2026-07-23 | Closed | config completed
P-1731 |  | 2026-07-23 | Marimuthu | yuan.qin | Scada and EMS 10 series ip not reachable | Sarita | High | 2026-07-23 | Network cabe connection error | 2026-07-23 | Closed | Afetr check the network cable isue resolved
P-1897 |  | 2026-07-23 | Marimuthu |  | Scada and EMS not reachable | praveen | Medium | 2026-07-23 | Network cabe connection error | 2026-07-23 | Closed | Network Switch end cable connectivity issue after check the network issue resolved and servre reachble
p-1729 |  | 2026-07-24 | Ashok |  | zone 1 zone 2 switch conifg | Nitheesh | Medium | 2026-07-24 | New requirements | 2026-07-24 | Closed | config completed
k-0339 |  | 2026-07-24 | Ashok | yuan.qin | DMZ switch internet config | praveen | Medium | 2026-07-24 | New requirements | 2026-07-24 | Closed | config completed
P-8004 |  | 2026-07-24 | Marimuthu | yuan.qin | Scada server time issue | Can song | Medium | 2026-07-24 | New requirements | 2026-07-24 | Closed | NTPD server after restarted both scada server time corrctely showing so issue resolved
P-1451/8022 |  | 2026-07-24 | Shadab.pinitod |  | ems to mppc data forwarding ip modified | vinod | Medium | 2026-07-24 |  | 2026-07-24 | Closed | ip modified and done the configuration.
P-1799 |  | 2026-07-27 | Shadab.pinitod |  | Zone 1 and Zone 2 switch configuartion | Nitheesh | Medium | 2026-07-27 | New requirements | 2026-07-27 | Closed | config completed
P-1799 |  | 2026-07-27 | Shadab.pinitod |  | Core switch 1 | Nitheesh | Medium | 2026-07-27 | New requirements | 2026-07-27 | Closed | config completed
k-0334 |  | 2026-07-28 | Ashok |  | DMZ switch internet config | praveen | Medium | 2026-07-27 | New requirements | 2026-07-27 | Closed | config completed
p-1729 |  | 2026-07-28 | Ashok | qiang.wang | core switch third party firewaall config ping test | praveen | Medium | 2026-07-27 | New requirements | 2026-07-27 | Closed | config completed
P-1962 |  | 2026-07-27 | Shadab.pinitod |  | level 3 switch 1 config | Nitheesh | Medium | 2026-07-27 | New requirements | 2026-07-27 | Closed | config completed
p-0229 |  | 2026-07-28 | Ashok | yuan.qin | vpn creation | praveen | Medium | 2026-07-28 | New requirements | 2026-07-28 | Closed | config completed
p-0317 |  | 2026-07-28 | Ashok |  | vpn creation | praveen | Medium | 2026-07-28 | New requirements | 2026-07-28 | Closed | config completed
p-1479 |  | 2026-07-28 | Ashok | qiang.wang | mppc to ems data forwording | tilak | Medium | 2026-07-28 | New requirements | 2026-07-28 | Closed | config completed
P-1799 |  | 2026-07-28 | Shadab.pinitod |  | Core switch 2 configuration | Nitheesh | Medium | 2026-07-28 | New requirements | 2026-07-28 | Closed | config completed
P-1653 |  | 2026-07-29 | Shadab.pinitod |  | data forwarding modification | sarita | Medium | 2026-07-29 | New requirements | 2026-07-29 | Closed
P-1799 |  | 28-0702026 | Mayur Tisage |  | SCADA and EMS configuration completed | Niteesh | Medium | 27-07-2-026 | New requirements | 2026-07-28 | Closed | config completed
P-1610 |  | 28-0702026 | Mayur Tisage |  | EMS server not pinging | Sarita | Medium | 2026-07-28 | New requirements | 2026-07-28 | Closed | Issue resolved
P-1799 |  | 2026-07-29 | Shadab.pinitod | qiang.wang | inside fw 1 and inside fw2 new configuration and HA | Niteesh | Medium | 2026-07-29 | New requirements | 2026-07-29 | Closed | config completed and HA sync
P-1741 |  | 2026-07-29 | Shadab.pinitod |  | ems to mppc data forwarding issue | Sangappa | High | 2026-07-29 | New requirements | 2026-07-29 | Closed | now the ports are open.
P-1587 |  | 2026-07-29 | Mayur Tisage | yuan.qin | Scada configuration | Niteesh | Medium | 2026-07-29 | New requirements | 30--7-2026 | Closed | config completed
p-1886 |  | 2026-07-29 | Ashok |  | time server config | Niteesh | Medium | 2026-07-29 | New requirements | 30--7-2026 | Closed
P-1741 |  | 2026-07-29 | Mayur Tisage | yuan.qin | Core switch ips not pinging and moba not connecting | Sangappa | Medium | 2026-07-29 | New requirements | 2026-07-29 | Closed | config completed
P-1578 | CS0216161 | 2026-06-12 | yuan.qin | yuan.qin | re-install OS for P-1578 | wu.hongxia |  |  |  |  | Closed | Reinstalled the OS and re configured
P-1707 |  | 2026-07-30 | Mayur Tisage |  | EMS is not synced with time | Niteesh | Medium | 2026-07-29 |  | 2026-07-30 | Closed | issue with software database not connected to correct IST
P-1653 |  | 2026-07-30 | Mayur Tisage | yuan.qin | EMS ip conflict issue | Sarita | Medium | 2026-07-30 |  | 2026-07-30 | Closed | issue resolved
P-1887 |  | 2026-07-30 | Shadab.pinitod | yuan.qin | Core switch 1 and Core switch 2 Configuration | Niteesh | Medium | 2026-07-30 | New requirements | 2026-07-30 | Closed | config completed
P1799 |  | 2026-07-30 | Shadab.pinitod |  | outside fw 1 & outside fw 2 config and HA implementation | Niteesh | Medium | 2026-07-30 | New requirements | 2026-07-30 | Closed | config completed and HA is stable now
p-1926 |  | 2026-07-30 | Ashok |  | outside 1,2firewall HA | Niteesh | Medium | 2026-07-30 | New requirements | 2026-07-30 | Closed | configured
p-1748 |  | 2026-07-30 | Ashok | qiang.wang | vpn configuration | Niteesh | Medium | 2026-07-30 | New requirements | 2026-07-30 | Closed | configured
p-1748 |  | 2026-07-30 | Ashok | yuan.qin | Ha isssue public ip issue | Niteesh | Medium | 2026-07-30 | New requirements | 2026-07-30 | Closed | configured
p-1962 |  | 2026-07-31 | Ashok |  | ouside fw 1,2 ha outside firewall os missing | Niteesh | Medium | 2026-07-31 | New requirements | 2026-07-31 | Closed
p-1748 |  | 2026-07-31 | Ashok | qiang.wang | scada monirtering ,user creation | Niteesh | Medium | 2026-07-31 | New requirements | 2026-07-31 | Closed
P-1843 |  | 2026-07-31 | Shadab.pinitod |  | port issue | vinod | Medium | 2026-07-31 |  | 2026-07-31 | Closed
P-1741 |  | 2026-08-03 | Mayur Tisage | yuan.qin | WTG Health BE servers Unable to connect telnet issue Galileo data ip network is unreachable | Sangappa | Medium |  | New requirements |  | Closed | Issure resolved.
P-1660 |  | 2026-08-03 | Mayur Tisage | yuan.qin | WTG Health BE servers Unable to connect telnet issue Galileo data ip network is unreachable | Sanagappa | Medium |  | New requirements |  | Closed | issue resolved
K-334 |  | 2026-08-03 | Mayur Tisage | yuan.qin | Time server sync issue in FEP servers | Niteesh | Medium | 2026-08-03 |  | 2026-08-03 | Closed | Issue resolved
k-0317 |  | 2026-08-01 | Ashok | qiang.wang | monitering and user creation | Niteesh | Medium | 2026-08-01 | New requirements | 2026-08-01 | Closed | Issue resolved
k-0229 |  | 2026-08-01 | Ashok |  | monitering and user creation | Niteesh | Medium | 2026-08-01 | New requirements | 2026-08-01 | Closed
P-1479 |  | 2026-08-03 | Shadab.pinitod |  | data forwarding ems to mpps | sarita | Medium | 2026-08-03 | New requirements | 2026-08-03 | Closed | config completed
P-1587 |  | 2026-08-03 | Shadab.pinitod |  | level 3 switches config | Niteesh | Medium | 2026-08-03 | New requirements | 2026-08-03 | Closed | config completed
p-1750 |  | 2026-08-03 | Ashok | qiang.wang | time server config | mayur | Medium | 2026-08-03 | New requirements | 2026-08-03 | Closed
p-1451 |  | 2026-08-03 | Ashok | yuan.qin | ems to mppc port changing | praveen | high |  |  | 2026-08-03 | Closed
P-1729 |  | 2026-08-03 | Mayur Tisage | yuan.qin | Scada server bridge issue | Abdullah | Medium | 2026-08-03 |  | 2026-08-03 | Closed | Issue resolved
p-1750 |  | 2026-08-03 | Mayur Tisage | yuan.qin | Time sync issue | Sarita | Medium | 2026-08-03 |  | 2026-08-03 | Closed | After network configuration I checked the server configuration.
P-1799 |  | 2026-07-31 | Marimuthu | yuan.qin | SSH issue mob not conneteing | Niyadeen | Medium | 20267/31 | New requirements | 2026-07-31 | Closed
P-1731 |  | 2026-08-04 | Shadab.pinitod |  | modification of data forwarding | sarita | Medium | 2026-08-04 |  | 2026-08-04 | Closed | modification done
P-1799 |  | 2026-07-31 | Marimuthu | yuan.qin | SSH not connected and mob also not conected | Niyaz | Medium | 2026-07-29 | Network cabe connection error | 2026-07-31 | Closed | Firewall SSh service blocked after uenabked the service issue resolved
P-1843 |  | 2026-08-04 | Shadab.pinitod |  | ports are not open | vinod | Medium | 2026-08-04 |  | 2026-08-04 | Closed | routes are missing in .24 server
P-1653 |  | 2026-08-04 | Shadab.pinitod |  | data forwarding ems to mppc modification | sarita | Medium | 2026-08-04 |  | 2026-08-04 | Closed
P-1578 |  | 2026-08-04 | Shadab.pinitod |  | Scada to SubstationGW2 data forwarding | sarita | Medium | 2026-08-04 | New requirements | 2026-08-04 | Closed | config completed
P-1587 |  | 2026-08-04 | Shadab.pinitod |  | level 2 switches config | Niteesh | Medium | 2026-08-04 | New requirements | 2026-08-04 | Closed | config completed
p-1843 |  | 2026-08-04 | Ashok |  | data dorwording mppc issue | jeffin | Medium | 2026-08-04 | New requirements | 2026-08-04 | Closed | config completed
p-1451 |  | 2026-08-04 | Ashok | qiang.wang | data forwording mppc | praveen | high | 2026-08-04 | New requirements | 2026-08-04 | Closed | config completed
p-1962 |  | 2026-08-04 | Ashok |  | level2 swictchconfig | nitheesh | Medium | 2026-08-04 | New requirements | 2026-08-04 | Closed | config completed
k-0334 |  | 2026-08-04 | Ashok |  | data forwording opc_ua | albert | Medium | 2026-08-04 | New requirements | 2026-08-04 | Closed | config completed
P-1886 |  | 2026-08-05 | Marimuthu | yuan.qin | Scada BE 1 not recahble issue |  | Medium | 2026-08-05 | New requirements |  | Closed | All server are reachable network end still looping issue on going
P-1749 |  | 2026-08-05 | Marimuthu | yuan.qin | Both Scada and EMS not recahble |  | Medium | 12026/8/4 | Network cabe connection error | 2026-08-05 | Closed | I have check the issue server end everything it's ok but network switch end issue network team working on it
k-0229 |  | 2026-08-05 | Ashok | qiang.wang | vpn user add | sathish | Medium | 12026/8/5 | New requirements | 2026-08-05 | Closed | config completed
k-0317 |  | 2026-08-05 | Ashok | qiang.wang | vpn user add | sathish | Medium | 12026/8/5 | New requirements | 2026-08-05 | Closed | config completed
P-1749 |  | 2026-08-05 | Shadab.pinitod |  | switchip is not pinging | Niyaz | Medium | 2026-08-05 | New requirements | 2026-08-05 | Closed | Switch ip and servers ip also pinging
P-1653 |  | 2026-08-05 | Shadab.pinitod |  | ports are not open | sarita | Medium | 2026-08-05 | New requirements | 2026-08-05 | Closed | ports are open at firewall end.
p-1962 |  | 2026-08-05 | Ashok | qiang.wang | zone1 switch 1,2 config | Niteesh | Medium | 2026-08-05 | New requirements | 2026-08-05 | Closed | config completed
p-1962 |  | 2026-08-05 | Ashok |  | outside firwall Ha | Niteesh | Medium | 2026-08-05 | New requirements | 2026-08-05 | Closed | config completed
P-1587 |  | 2026-08-05 | Shadab.pinitod |  | Core switch 1,2 confg | Niteesh | Medium | 2026-08-05 | New requirements | 2026-08-05 | Closed | config completed
P-1750 |  | 2026-08-06 | Shadab.pinitod |  | data forwording scada to substation | sarita | Medium | 2026-08-06 | New requirements | 2026-08-06 | Closed | config completed
P-1887 |  | 2026-08-06 | Shadab.pinitod | yuan.qin | outside fw 1,2 firewall configuration | Niteesh | Medium | 2026-08-06 | New requirements | 2026-08-06 | Closed | config completed
p-1962 |  | 2026-08-06 | Ashok |  | core switch1,2 | Niteesh | Medium | 2026-08-06 | New requirements | 2026-08-06 | Closed | config completed
p-1962 |  | 2026-08-06 | Ashok | qiang.wang | ouside firewall core xl | Niteesh | Medium | 2026-08-06 | New requirements | 2026-08-06 | Closed | config completed
k-0234 |  | 2026-08-06 | Ashok |  | inside firewall 1,2 | Niteesh | Medium | 2026-08-06 | New requirements | 2026-08-06 | Closed | config completed
p-1731 |  | 2026-08-06 | Ashok |  | inside firewall 1,2 | Niteesh | Medium | 2026-08-06 | New requirements | 2026-08-06 | Closed | config completed
P-1887 |  | 2026-08-07 | Shadab.pinitod |  | inside firewall 1,2 | Niteesh | Medium | 2026-08-07 | New requirements | 2026-08-07 | Closed | config completed
P-1578 |  | 2026-08-07 | Shadab.pinitod |  | Port changes | sarita | Medium | 2026-08-07 | New requirements | 2026-08-07 | Closed | config completed
p-1750 |  | 2026-08-07 | Ashok | qiang.wang | public ip not reachable | ravi | Medium | 2026-08-07 | New requirements | 2026-08-07 | Closed | config completed
p-1962 |  | 2026-08-07 | Ashok |  | time server | muthu | Medium | 2026-08-07 | New requirements | 2026-08-07 | Closed | config completed
k-0234 |  | 2026-08-07 | Ashok | qiang.wang | time server | nitheesh | Medium | 2026-08-07 | New requirements | 2026-08-07 | Closed | config completed
k-0234 |  | 2026-08-07 | Ashok |  | inside firewall 1,2 | nitheesh | Medium | 2026-08-07 | New requirements | 2026-08-07 | Closed | config completed
k-0234 |  | 2026-08-07 | Ashok | qiang.wang | zon2 1 swicth 1,2 | nitheesh | Medium | 2026-08-07 | New requirements | 2026-08-07 | Closed | config completed
k-0234 |  | 2026-08-07 | Ashok |  | core 1 swicth 1,2,3 | nitheesh | Medium | 2026-08-07 | New requirements | 2026-08-07 | Closed | config completed
k-0234 |  | 2026-08-07 | Ashok | qiang.wang | dmz swith | nitheesh | Medium | 2026-08-07 | New requirements | 2026-08-07 | Closed | config completed
P-1799 |  | 2026-08-06 | Marimuthu | yuan.qin | Docker Issue | Niyadeen | Medium | 2026-08-07 | New requirements | 2026-08-08 | Closed | Docker Issue resolved
P-1887 |  | 2026-08-07 | Shadab.pinitod |  | level 2 switches config | nitheesh | Medium | 2026-08-07 | New requirements | 2026-08-07 | Closed | config completed
P-1436 |  | 2026-08-10 | Marimuthu |  | Time server issue | praveen | Medium | 2026-08-10 | New requirements |  | Closed | Time issue resolved
P-8004 |  | 2026-08-10 | Mayur Tisage |  | EMS not synchronized with time server | Niteesh | medium | 2026-08-10 | New requirements | 2026-08-10 | Closed | Issue resolved
P-1665 |  | 2026-08-10 | Shadab.pinitod |  | PA firewall port glow and OS issue | Niteesh | medium | 2026-08-10 | New requirements | 2026-08-10 | Closed | Issue resolved
p-1962 |  | 2026-08-10 | Ashok |  | inbside firewall core xl | nitheesh | medium | 2026-08-10 | New requirements | 2026-08-10 | Closed | Issue resolved
p-1615 |  | 2026-08-10 | Ashok | qiang.wang | mppc to ems | nitheesh | medium | 2026-08-10 | New requirements | 2026-08-10 | Closed | Issue resolved
p-1615 |  | 2026-08-10 | Ashok |  | srldc to scada | nitheesh | medium | 2026-08-10 | New requirements | 2026-08-10 | Closed | Issue resolved
p-1528 |  | 2026-08-10 | Ashok | qiang.wang | ems url | nitheesh | medium | 2026-08-10 | New requirements | 2026-08-10 | Closed | Issue resolved
P-1587 |  | 2026-08-10 | Shadab.pinitod |  | outside fw1 config | nitheesh | medium | 2026-08-10 | New requirements | 2026-08-10 | Closed | config completed
P-1887 |  | 2026-08-11 | Mayur Tisage |  | Scada server configuration | Niteesh | medium | 2026-08-11 | New requirements |  | Closed
P-1748 |  | 2026-08-11 | Mayur Tisage | yuan.qin | CMS data server not reachable | Niteesh | medium | 2026-08-11 | New requirements |  | Closed | issue resolved
P-1799 |  | 2026-08-11 | Mayur Tisage |  | EMS server not reachable | Niteesh | medium | 2026-08-11 | New requirements |  | Closed | issue resolved
P-1546 |  | 2026-08-11 | Shadab.pinitod | Ashok | opc to scada port issue | Niteesh | medium | 2026-08-11 | New requirements | 2026-08-11 | Closed | ports are open at firewall end.
P-1653 |  | 2026-08-11 | Mayur Tisage |  | Gallio servers showing down | Niteesh | medium | 2026-08-11 | New requirements |  | Closed | Resolved
P-1741 |  | 2026-08-11 | Marimuthu | qiang.wang | Data server not recahble and telnet issue | sangappa | Medium | 2026-08-11 | New requirements | 2026-08-11 | Closed | Afer add the port and route files issue resolved
p-1741 |  | 2026-08-11 | Ashok | qiang.wang | telnet 6666 not working | mari muthu | Medium | 2026-08-11 | New requirements | 2026-08-11 | Closed | Issue resolved
P-1528 |  | 2026-08-11 | Shadab.pinitod |  | Backup files for Cyber security purpose | Niteesh | Medium | 2026-08-11 | New requirements | 2026-08-11 | Closed
P-1610 |  | 2026-08-12 | Mayur Tisage |  | WTG Health BE server not reachable | tilak | medium | 2026-08-12 |  | 2026-08-12 | Closed | Issure resolved.
P-1799 |  | 2026-08-12 | Shadab.pinitod | qiang.wang | time server configuration | Niteesh | medium | 2026-08-12 | New requirements | 2026-08-12 | Closed | config completed
p-1436 |  | 2026-08-12 | Ashok |  | time server configuration | mari muthu | medium | 2026-08-12 | New requirements | 2026-08-12 | Closed | config completed
K-0229 |  | 2026-08-12 | Ashok | qiang.wang | User creation | nitheesh | medium | 2026-08-12 | New requirements | 2026-08-12 | Closed | config completed
k-0334 |  | 2026-08-12 | Ashok |  | User creation | nitheesh | medium | 2026-08-12 | New requirements | 2026-08-12 | Closed | config completed
k-0317 |  | 2026-08-12 | Ashok | qiang.wang | User creation | nitheesh | medium | 2026-08-12 | New requirements | 2026-08-12 | Closed | config completed
P-1887 |  | 2026-08-13 | Shadab.pinitod |  | time server configuration | nitheesh | medium | 2026-08-13 | New requirements | 2026-08-13 | Closed | config completed
p-1962 |  | 2026-08-13 | Ashok |  | core switch rstp config | nitheesh | medium | 2026-08-13 | New requirements | 2026-08-13 | Closed | config completed
p-1887 |  | 2026-08-13 | Ashok | qiang.wang | cpu utilization high | nitheesh | medium | 2026-08-13 | New requirements |  | Closed | waiting for rstp configuration anadh/revappa | Turbine side Configuration conmpleted
P-1451 |  | 2026-08-13 | Marimuthu | yuan.qin | New EMS server installction request | Praveen | High | 2026-08-13 | New requirements | 2026-08-13 | Closed | config completed
P-8001 |  | 2026-08-13 | Marimuthu |  | EMS 1 HDD issue | Saritha | medium | 2026-08-13 |  | 20-08-2026 | Closed | After changed the SSD HDD and issue has been resloved
P-8001 |  | 2026-08-13 | Marimuthu | yuan.qin | EMS 3 HDD issue | Saritha | medium | 2026-08-13 |  |  | Pending on Manufacturers | Awaitinmg for thematerial santhosh taking care 31Aug
p-1407 |  | 2026-08-13 | Marimuthu | yuan.qin | Stand by WTG server hardware issue | Praveen | medium | 2026-08-13 | Server crash |  | Closed | Reconfigured the OS
p-1660 |  | 2026-08-14 | Ashok |  | internet not reachable | mayur | medium | 2026-08-14 | New requirements | 2026-08-14 | Closed | config completed
P-1528 |  | 2026-08-14 | Shadab.pinitod | yuan.qin | VAPT testing | nitheesh | medium | 2026-08-14 | New requirements | 2026-08-14 | Closed | completed
P-1811 |  | 2026-08-14 | Shadab.pinitod | jun.zhang | opc to scada data forwarding | Abdullah | medium | 2026-08-14 | New requirements | 2026-08-14 | Closed | config completed
p-1665 |  | 2026-08-14 | Ashok | jun.zhang | inside firewall config | Nitheesh | medium | 2026-08-14 | New requirements | 2026-08-14 | Closed | config completed
p-1665 |  | 2026-08-14 | Ashok | qiang.wang | outside firewall config | Nitheesh |  |  | New requirements | 2026-08-14 | Closed | config completed
P-1811 |  | 2026-08-14 | Shadab.pinitod |  | ems to mppc data forwarding | Abdullah | medium | 2026-08-14 | New requirements | 2026-08-14 | Closed | config completed
P-1731 |  | 2026-08-16 | Ashok |  | VPN Creations | Nitheesh | Medium |  | New requirements |  | Closed | customer wifi down
P-1528 |  | 2026-08-14 | Shadab.pinitod |  | port mirroring on switches | Nitheesh | medium |  | New requirements |  | Closed | completed.
P-8020/1420 |  | 2026-08-16 | Ashok | qiang.wang | VPN Check Sanjay Varfa Account not working | Nitheesh | Medium |  | Network cabe connection error |  | Closed | radidus server down
P-1528 |  | 2026-08-16 | Ashok |  | EMS Link Enable | Nitheesh | Medium |  | New requirements |  | Closed | after adding port 8702 in juniper its worked
P-1478 | CS0217147 | 2026-08-16 | Shadab.pinitod | jun.zhang | unable to telnet SCADA1 port 2406 from edge server | Aaron | Medium |  | New requirements |  | Closed
P-1615 |  | 2026-08-16 | Shadab.pinitod | jun.zhang | precheck failed + unable to telnet SCADA1 port 2406 from Edgegateway + please check time sync from Edgegateway | Aaron | Medium |  | New requirements |  | Ongoing | Public IP Issue
P-1749 |  | 2026-08-16 | Marimuthu | jun.zhang | pre-check failed + telnet s3.ap-south-1.amazonaws.com 443 also failed + all SCADA/EMS servers keep not pinging | AAron | Medium |  | New requirements |  | Ongoing | Revappa will check the pre check
P-1436 |  | 2026-08-16 | Mayur Tisage | yuan.qin | Pre- check failed(Autostart) | Aaron | Medium |  | New requirements |  | Closed | Pre check completed
P-3598 |  | 2026-08-16 | Marimuthu | jun.zhang | Pre- check failed(Autostart) | AAron | Medium |  | New requirements |  | Closed | Pre check done
P-1748 | CS0217203 | 2026-08-16 | Mayur Tisage | jun.zhang | DATA VM has some issues | Rong Rong | Medium |  | New requirements |  | Closed | issue resolved
P-8004 | CS0217273 | 2026-08-16 | Marimuthu |  | Unable to login or SSH of Galileo Servers | Rong Rong | Medium |  | New requirements |  | Closed | Issue resolved and all vm are running
P-1660 |  | 2026-08-16 | Marimuthu | jun.zhang | Galileo deployment has been completed, but still has communication issue . | Rong Rong | Medium |  | New requirements |  | Closed | DNS Issue has been solved
P-1962 |  | 2026-08-15 | Mayur Tisage | jun.zhang | Software team having issues to run docker in scada to complete configuration | praveen | high |  |  |  | Closed | Issue resolved
P-1887 |  | 2026-08-14 | Mayur Tisage | jun.zhang | Server Configuration | Niteesh | Medium |  |  |  | Closed | All configuration is completed
p-1665 |  | 2026-08-17 | Ashok | qiang.wang | inside firewall config ha | Niteesh | Medium |  | New requirements |  | Closed | configuration is completed
P-8001 |  | 2026-08-17 | Ashok |  | ems cant ping zone2 | mari | Medium |  | New requirements |  | Closed | cable issues
P-8004 |  | 2026-08-17 | Marimuthu | jun.zhang | WTG Scada server SSH issue | Rong Rong | Medium | 2026-08-17 | Server crash | 2026-08-17 | Closed | SSH IP allow in the Moba
P-1873 |  | 2026-08-17 | Marimuthu | yuan.qin | Network server Not recahble | Veeresh | Medium | 2026-08-17 | Server crash | 2026-08-17 | Closed | After change the corrcet ip it's working
P-1451 |  | 2026-08-17 | Marimuthu | yuan.qin | EMS 2 Ubuntu OS issue | Praveen | High | 2026-08-17 | Server crash | 2026-08-17 | Closed | After Grup installed Os issue resolved
P-1665 |  | 2026-08-17 | Marimuthu | yuan.qin | Scada and EMS OS version wrong | Nitheesh | Medium | 2026-08-17 | Server crash |  | Closed | Alredy installed OS version from HQ emd it's wrong after confirm with unverse team infra team junling then corrcet os image sent it 20-8-2026 so still os image download is going
P-1587 |  | 2026-08-17 | Shadab.pinitod |  | Third party firewall 1,2 configuration | Nitheesh | Medium | 2026-08-17 | New requirements | 2026-08-17 | Closed | config completed.
P-1451 |  | 2026-08-17 | Shadab.pinitod |  | ems to mppc additianal ip add | Praveen | Medium | 2026-08-17 | New requirements | 2026-08-17 | Closed | config completed.
P-1576 |  | 10-06-2026 | Marimuthu |  | Bridge issue | Saritha | Medium | 10-06-2026 | New requirements | 10-06-2026 | Closed | Issue resolved
P-1436 |  | 10-06-2026 | Marimuthu |  | EMS Bridge issue | Saritha | Medium | 10-06-2026 | New requirements | 10-06-2026 | Closed | Issue resolved
P-1587 |  | 11-06-2025 | Marimuthu |  | Scda Bridge issue | Saritha | Medium | 11-06-2025 | New requirements | 11-06-2025 | Closed | Issue resolved
P-1511 |  | 17-06-2025 | Marimuthu |  | scada not pinging | Saritha | Medium | 17-06-2025 | New requirements | 20-06-2025 | Closed | Issue resolved
P-1407 |  | 26-08-2025 | Marimuthu |  | Time and EMS server hardware issue | Niyaz | Medium | 26-08-2025 | Server crash | 27-08-2025 | Closed | Issue resolved
P-1576 |  | 04-09-2025 | Marimuthu |  | esxi vm Licence issue | Niya | Medium | 04-09-2025 | Server crash | 04-09-2025 | Closed | Issue resolved
P-8004 |  | 29-10-2025 | Marimuthu |  | Hard disk space incrased | Praveen kumar | Medium | 29-10-2025 | New requirements | 2-11-2025 | Closed | Issue resolved
P-1725 |  | 13-11-2025 | Marimuthu |  | SCADA and EMS server configuration | Saritha | Medium | 13-11-2025 | New requirements | 15-11-2025 | Closed | Issue resolved
P-1547 |  | 13-11-2025 | Marimuthu |  | SCADA and EMS server configuration | Saritha | Medium | 13-11-2025 | New requirements | 14-11-2025 | Closed | Issue resolved
P-1407 |  | 14-11-2025 | Marimuthu |  | Uesr created and password set | Saritha | Medium | 14-11-2025 | New requirements | 15-11-2025 | Closed | Issue resolved
P-1632 |  | 23-11-2025 | Marimuthu |  | Route Ip added | Saritha | Medium | 23-11-2025 | Network cabe connection error | 24-11-2025 | Closed | Issue resolved
P-8014 |  | 25-11-2025 | Marimuthu |  | Hard disk replacement activity | Niyaz | Medium | 25-11-2025 | Hard drive failure | 29-11-2025 | Closed | Issue resolved
P-1407 |  | 13-08-2026 | Marimuthu |  | WTG stand by faulty server replacement | Nithish | Medium | 13-08-2026 | Server crash | 15-08-2026 | Closed | The new server recived after checking the hardware leavel now it's working
P-1451 |  | 2026-08-18 | Marimuthu | yuan.qin | Route issue | Praveen | Medium | 2026-08-18 | New requirements | 2026-08-18 | Closed | Route added done
P-1962 |  | 18-08-2026 | Mayur Tisage |  | Scada and Ems server moba not connecting | Jeffin vinod | Medium | 18-08-2026 |  | 18-08-2026 | Closed | issue resolved
P-1749 |  | 18-08-2026 | Mayur Tisage |  | Core switch ip not pinging in scada | Niteesh | Medium | 18-08-2026 |  | 18-08-2026 | Closed | issue resolved
P-1588 |  | 18-08-2026 | Mayur Tisage |  | Scada and EMS configuration | Niteesh | Medium | 18-08-2026 |  | 18-08-2026 | Closed | Configuration completed
P-1610 |  | 18-08-2026 | Mayur Tisage |  | Bridge issue | Sarita | Medium | 18-08-2026 |  | 18-08-2026 | Closed | issue resolved
P-1660 |  | 18-08-2026 | Mayur Tisage |  | telnet issue | Niteesh | Medium | 18-08-2026 |  | 18-08-2026 | Closed | issue resolved
P-8001 |  | 18-08-2026 | Marimuthu |  | EMS 2 system ip not reachble | Praveen | Medium | 18-08-2026 |  | 18-08-2026 | Closed | After replcae the New network cable now it's working fine
P-1587 |  | 18-08-2026 | Shadab.pinitod |  | inside fw 1,2 config | Niteesh | Medium | 18-08-2026 | New requirements | 18-08-2026 | Closed | config completed
P-1587 |  | 18-08-2026 | Shadab.pinitod |  | third party fw1,2 config | Niteesh | Medium | 18-08-2026 | New requirements | 18-08-2026 | Closed | config completed
p-1665 |  | 18-08-2026 | Ashok |  | outdide firewall ha issue | Niteesh | Medium | 18-08-2026 | New requirements |  | Closed | config completed
p-8020 |  | 18-08-2026 | Ashok |  | radius server down issue | Niteesh | Medium | 18-08-2026 | New requirements |  | Closed | issue resolved
p-1665 |  | 18-08-2026 | Ashok |  | zone 2 switch 1,zone 2 swiotch 2 config | Niteesh | Medium | 18-08-2026 | New requirements |  | Closed | issue resolved
P-1587 |  | 19-08-2026 | Shadab.pinitod |  | outside fw 1,2 config | Niteesh | Medium | 19-08-2026 | New requirements | 19-08-2026 | Closed | Configuration completed
P-1587 |  | 19-08-2026 | Shadab.pinitod |  | time server | Niteesh | Medium | 19-08-2026 | New requirements | 19-08-2026 | Closed | Configuration completed
P-1750 |  | 19-08-2026 | Shadab.pinitod |  | scada to opc data forwarding | sarita | Medium | 19-08-2026 | New requirements | 19-08-2026 | Closed | Configuration completed
P-1741 |  | 19-08-2026 | Shadab.pinitod |  | public ip | Nitheesh | Medium | 19-08-2026 |  | 19-08-2026 | Closed | extranet communication is working fine.
K299 |  | 19-08-2026 | Mayur Tisage |  | FEP server main and standby installed and configured | Praveen | Medium | 19-08-2026 |  | 19-08-2026 | Closed | Configuration completed
K317 |  | 19-08-2026 | Mayur Tisage |  | FEP server main and standby installed and configured | Praveen | Medium | 19-08-2026 |  | 19-08-2026 | Closed | Configuration completed
P-1748 |  | 19-08-2026 | Marimuthu |  | Galilio data server ip are not reachable | Abudhulla | Medium | 2026-08-19 | Server crash | 2026-08-19 | Closed | Ip address issue after configure the corrrcet ip address now ip is arechble and issue resolved
p-1451 |  | 19-08-2026 | Ashok |  | mppc to ems 3 ports not showing open | jeffin | Medium | 2026-08-19 | New requirements | 2026-08-19 | Closed | added nat policy for ems3
p-1665 |  | 19-08-2026 | Ashok |  | third party firewall 1,2 os installtion | nitheesh | Medium | 2026-08-19 | New requirements | 2026-08-19 | Closed | Configuration completed
p-1665 |  | 19-08-2026 | Ashok |  | zone 1 switch 1,2 configuration | nitheesh | Medium | 2026-08-19 | New requirements | 2026-08-19 | Closed | Configuration completed
p-1731 |  | 19-08-2026 | Ashok |  | public ip change configured | naveen | Medium | 2026-08-19 | New requirements | 2026-08-19 | Closed | Configuration completed
P-1615 |  | 20-08-2026 | Shadab.pinitod |  | public ip changes | nitheesh | Medium | 20-08-2026 | New requirements | 20-08-2026 | Closed | configured the new public ip but gateway and 8.8.8.8 is not pinging. need to check with customer
P-1812 |  | 2026-08-20 | Marimuthu |  | Time issue | Abudhulla | Medium | 2026-08-20 | New requirements | 21-08-2026 | Closed | After add the route ip NTP server reachbl and issue resolved
p-1451 |  | 1905-08-20 | Ashok |  | core ip not ping | mari muthu | Medium | 2026-08-20 | New requirements | 20-08-2026 | Closed | due power issue plant down then restarted switch
p-1665 |  | 1905-08-20 | Ashok |  | user firewall 1,2 os upgrade | nithesh | Medium | 2026-08-20 | New requirements | 20-08-2026 | Closed | Configuration completed
p-1479 |  | 1905-08-20 | Ashok |  | opc_ forwording | praveen | Medium | 2026-08-20 | New requirements | 20-08-2026 | Closed | Configuration completed
p-1479 |  | 1905-08-20 | Ashok |  | mppc forwording | praveen | Medium | 2026-08-20 | New requirements | 20-08-2026 | Closed | Configuration completed
P-1451 |  | 21-08-2026 | Marimuthu |  | Scada BE 1 bridge issue | jin zang | Medium | 2026-08-21 | New requirements |  | Closed | Bridge reconfigured bny Junjuima
P-1897 |  | 21-08-2026 | Shadab.pinitod |  | public ip | nithesh | Medium | 2026-08-21 |  | 2026-08-21 | Closed
P-1729 |  | 21-08-2026 | Shadab.pinitod |  | wrldc to scada data forwarding | Abudhulla | Medium | 2026-08-21 | New requirements | 2026-08-21 | Closed | Configuration completed and ports are open
P-1427 |  | 21-08-2026 | Shadab.pinitod |  | mppc to ems data forwarding | Abudhulla | Medium | 2026-08-21 | New requirements | 2026-08-21 | Closed | Configuration completed and ports are open
P-1729 |  | 21-08-2026 | Marimuthu |  | Both Scada not reachble | Sangappa | Medium | 2026-08-21 | New requirements | 2026-08-21 | Closed | After change the LAN cable connctivity both scada is
P-1588 |  | 21-08-2026 | Shadab.pinitod |  | level 3 switch 1 and level 3 swutch 2 config | Nitheesh | Medium | 2026-08-21 | New requirements | 2026-08-21 | Closed | Configuration completed
P-1707 |  | 21-08-2026 | Ashok |  | opc_forwording | abdulla | Medium | 2026-08-21 | New requirements | 2026-08-21 | Closed | Configuration completed
p-1811 |  | 21-08-2026 | Ashok |  | inside firewall core xl stablizing | abdulla | Medium | 2026-08-21 | New requirements | 2026-08-21 | Closed | Configuration completed
p-1811 |  | 21-08-2026 | Ashok |  | mppc data forwoding customer | abdulla | Medium | 2026-08-21 | New requirements | 2026-08-21 | Closed | Configuration completed
p-1811 |  | 21-08-2026 | Ashok |  | opc_data forwoding to customer | abdulla | Medium | 2026-08-21 | New requirements | 2026-08-21 | Closed | Configuration completed
p-1811 |  | 21-08-2026 | Ashok |  | wrldc forwoding to custopmer | abdulla | Medium | 2026-08-21 | New requirements | 2026-08-21 | Closed | Configuration completed
p-1451 |  | 21-08-2026 | Ashok |  | opc ip not reaching to customer | nithessh | Medium | 2026-08-21 | New requirements | 2026-08-21 | Closed | server side ports are not open
p-1707 |  | 22-08-2026 | Ashok |  | opc_ua forwoding to customer | praveen | Medium | 2026-08-21 | New requirements | 2026-08-21 | Closed | Configuration completed
P-1587 |  | 2026-08-20 | Mayur Tisage | jun.zhang | Servers getting hanged and not pinging | Manjunatha | medium | 2026-08-20 |  | 2026-08-20 | Closed | Removed core switch cables and corrected the cable connections
P-1707 |  | 2026-08-20 | Mayur Tisage |  | Scada BE server not pinging | Niteesh | medium | 2026-08-20 |  | 2026-08-21 | Closed | Some docker services were blocking ICMP and TCP connections, Issue resolved
P-1873 |  | 2026-08-21 | Mayur Tisage |  | Front end servers configuration | Niteesh | High | 2026-08-21 |  | 2026-08-21 | Closed | Server configured
P-1427 |  | 2026-08-21 | Shadab.pinitod |  | scada to opc data forwarding | abdullah | medium | 2026-08-21 | New requirements | 2026-08-21 | Closed | Configuration completed
P-1887 |  | 2026-08-21 | Mayur Tisage |  | Bridge issue | Thilak | Medium | 2026-08-21 |  | 2026-08-21 | Closed | Software team deleted bridge while running mtools, reconfigured bridge
p-1407 |  | 2026-08-24 | Ashok | qiang.wang | sftp server config | praveen | Medium | 2026-08-24 |  | 2026-08-24 | Closed | completed after modifiying iside outside
k-0229 |  | 2026-08-24 | Ashok | jun.zhang | user creation vpn | nitheesh | Medium | 2026-08-24 |  | 2026-08-24 | Closed | completed
k-0334 |  | 2026-08-24 | Ashok | qiang.wang | user creation vpn | nitheesh | Medium | 2026-08-24 |  | 2026-08-24 | Closed | completed
p-1843 |  | 2026-08-24 | Ashok | qiang.wang | mini rtu configuration | praveen | Medium | 2026-08-24 |  |  | Closed | completed
p-1665 |  | 2026-08-24 | Ashok | qiang.wang | pa user firewall os issue | nitheesh | Medium | 2026-08-24 |  | 2026-08-24 | Closed | put the os
P-1407 |  | 2026-08-24 | Shadab.pinitod |  | firewalls backup for VAPT purpose | nitheesh | Medium | 2026-08-24 |  | 2026-08-24 | Closed | completed
P-8001 |  | 2026-08-25 | Marimuthu |  | EMS 1 isuse | Praveen | Medium | 2025-08-25 | Server crash | 2026-08-25 | Closed | Collect the log details and checking issue has been resolved
P-8004 |  | 2026-08-25 | Marimuthu | yuan.qin | Scada BE1 hardware issue server replaced and Backup restore process | Nitheesh | High | 2025-08-25 | Hard drive failure |  | Closed | Yuan has replaced the Image with the backup sever
P-1407 |  | 2026-08-25 | Shadab.pinitod |  | VAPT task ( port mirroring and switches backup) | Nitheesh | Medium | 2025-08-25 |  | 2025-08-25 | Closed | Task completed.
P-1653 |  | 2026-08-25 | Marimuthu | yuan.qin | wtg galilio server not reachable | Nitheesh | Medium |  |  |  | Closed | Checked and rectified the issues
P-1653 |  | 2026-08-25 | Shadab.pinitod |  | Ipsec tunnel down | Nitheesh | Medium | 2025-08-25 |  | 2026-08-25 | Closed | tunnel is UP
P-1653 |  | 2026-08-25 | Shadab.pinitod | jun.zhang | SSL vpn creation | Nitheesh | Medium | 2025-08-25 |  | 2026-08-25 | Closed | wihtout radius server SSL vpn is connecting. none of the server ip is pinging
p-1731 |  | 2026-08-25 | Ashok | jun.zhang | opc ,mppc data not reciecng | Nitheesh | Medium | 2025-08-25 |  | 2026-08-25 | Closed | now data reaching to customer
p-1665 |  | 2026-08-25 | Ashok |  | user firewall 2 os installion | Nitheesh | Medium | 2025-08-25 |  | 2026-08-25 | Closed | Configuration completed
p-1436 |  | 2026-08-25 | Ashok | qiang.wang | kvm need to reach 8.8.8..8 | mayur | Medium | 2025-08-25 |  | 2026-08-25 | Closed | added route and policy
p-1731 |  | 2026-08-26 | Ashok |  | core xl mis match in third party firewall | ashok | Medium | 1900-01-25 |  | 2026-08-25 | Closed | core blanced
p-1731 |  | 2026-08-26 | Ashok | qiang.wang | public ip down | ashok | Medium | 2025-08-25 |  | 2026-08-25 | Closed | pulic ip configured
p-1436 |  | 2026-08-26 | Ashok | qiang.wang | port 80 allowed | mayur | Medium | 2025-08-25 |  | 2026-08-25 | Closed | added the port 80 via inside outside firewall
p-1731 |  | 2026-08-26 | Ashok | qiang.wang | third party firewall warning led blinking | naveenthan | Medium | 2025-08-25 |  | 2026-08-25 | Closed | after recconnecting power codes re solved
p-1660 |  | 2026-08-26 | Ashok | qiang.wang | op-c ip not reachable | sangappa |  |  |  | 2026-08-25 | Closed
P-1429 |  | 2026-08-27 | Shadab.pinitod |  | ip sec creation | Nitheesh | Medium | 2026-08-27 |  |  | Closed | Ip sec Created Checking need to done from both End Veeresh will check ,IP Sec is up
P-1436 |  | 2026-08-25 | Mayur Tisage |  | Gallio servers installation | Rongrong | high | 2026-08-25 |  | 2026-08-27 | Closed | Server is installed and configured
P-1480 |  | 2026-08-24 | Mayur Tisage |  | WTG Health BE server down | Rongrong | Medium | 2026-08-24 |  | 2026-08-24 | Closed | Server is getting tripped, asked local team to check power connectivity
P-1748 |  | 2026-08-24 | Mayur Tisage | yuan.qin | Telnet port add in Galilio | Sangappa | Medium | 2026-08-24 |  | 2026-08-24 | Closed | Telnet port added but verification needs to be done by software
P-1436 |  | 2026-08-25 | Mayur Tisage | jun.zhang | Radius, Jumpserver, Scada Front end having issues | Niteesh | Medium | 2026-08-25 |  | 2026-08-25 | Closed | Checked and rectified the issues
P-1578 |  | 2026-08-25 | Mayur Tisage |  | data ip not reachable in moba | Sangappa | Medium | 2026-08-25 |  | 2026-08-25 | Closed | Issue resolved
P-8001 |  | 2026-08-26 | Mayur Tisage | jun.zhang | PPC1 time sync issue | albert | Medium | 2026-08-26 |  | 2026-08-26 | Closed | Issue resolved
P-8001 |  | 2026-08-27 | Marimuthu | yuan.qin | PPC 1 and PPC 2 pre check | Praveen | Medium | 2026-08-27 |  |  | Closed | Completed and checked and taken the loggs and resolved
P-8001 |  | 2026-08-27 | Marimuthu | yuan.qin | Scada,EMS and PPC server network cable conncetivty checking | Praveen | Medium | 2026-08-27 |  |  | Closed | Completed and checked and taken the loggs and resolved
P-1451 |  | 2026-08-27 | Marimuthu | jun.zhang | EMS 4 not recahble | Niteesh | Medium | 2026-08-27 |  | 2026-08-27 | Closed | Network cable issue now it's working fine
P-1665 |  | 2026-08-27 | Marimuthu | yuan.qin | Both Scada and Both EMS Os version checking and Scada BE 1 server physically LAN port 4 showing | Praveen | Medium | 2026-08-27 |  |  | Closed | SCADA Completed And EMS installation on proegress
P-1741 |  | 2026-08-27 | Shadab.pinitod | jun.zhang | opc to scada ports are not open | sangappa | Medium | 2026-08-27 |  | 2026-08-27 | Closed | now the ports are open
P-1587 |  | 2026-08-27 | Mayur Tisage | jun.zhang | EMS and Scada time not sync | praveen | Medium | 2026-08-27 |  |  | Closed | time is synced
p-1436 |  | 2026-08-31 | Ashok | qiang.wang | time server issue | mayur | Medium | 2026-08-31 |  | 2026-08-31 | Closed | New antena arranged and the time sync as configured by Yuan
P-8001 |  | 2026-08-28 | Marimuthu | yuan.qin | EMS , PPC and Scada server frequentely disconncted and ip are not reachble | Praveen | Medium | 2026-08-27 |  | 2026-08-28 | Closed | EMS scada and PPC server log details collcted and checking the log lost details showing 24 power flucation issue MCP triped after MCP issue clear then again verify the log details now it's server working find without power intrpted
P-1741 |  | 2026-08-28 | Shadab.pinitod |  | data forwarding config modified | Sangappa | Medium | 2026-08-28 |  | 2026-08-28 | Closed | config completed and also ports are open.
k-0299 |  | 2026-08-31 | Ashok |  | fep forwoding | ashok | Medium | 2026-08-31 |  | 2026-08-31 | Closed | configured port 3
P-1843 |  | 2026-08-31 | Marimuthu | jun.zhang | EMS 1 not working | Jefin | Medium | 2026-08-29 |  | 2026-08-31 | Closed | Issue resolved
P-3598 |  | 2026-08-31 | Shadab.pinitod |  | public ip changes & time serevr checkup | Nitheesh | Medium |  |  | 2026-09-01 | Closed | configured the public ip and extranet communication is fine.
P-1587 |  | 2026-08-31 | Shadab.pinitod | jun.zhang | data forwarding scada ro srldc | manjunath | Medium | 2026-08-31 |  | 2026-08-31 | Closed | configured port 2 of third party fw 1
P-1799 |  | 2026-08-31 | Shadab.pinitod | jun.zhang | data forwarding ems to mppc | Niyaz | Medium | 2026-08-31 |  | 2026-08-31 | Closed | configured port 4 of inside fw 1
P-1962 |  | 2026-08-31 | Marimuthu | yuan.qin | Both Scada SSH issue | Saritha | Medium | 2026-08-31 |  |  | Closed | Solved Allow the IP iat server Level
P-1873 |  | 2026-08-31 | Marimuthu | yuan.qin | Galilio Issue | Nitheesh | Medium | 2026-08-31 |  |  | Closed | DNS issue solved
P-1962 |  | 2026-09-01 | Mayur Tisage | yuan.qin | Both Scada SSH issue | Sarita | Medium | 2026-09-01 |  | 2026-09-01 | Closed | issue resolved
P-3599 |  | 2026-09-01 | Mayur Tisage | yuan.qin | Scada BE server not pinging | Sarita | Medium | 2026-09-01 |  | 2026-09-01 | Closed | issue resolved
|  | 2026-09-01 | Mayur Tisage | yuan.qin | EMS Bridge issue | Niyasdin | Medium | 2026-09-01 |  | 2026-09-01 | Closed | issue resolved
P-1799 |  | 2026-09-01 | Shadab.pinitod |  | mppc to ems modifiaction | Niyasdin | Medium | 2026-09-01 |  | 2026-09-01 | Closed | config completed
P-1588 |  | 2026-09-01 | Shadab.pinitod | qiang.wang | Level 2 switch 1,2 configuration | Nitheesh | Medium | 2026-09-01 |  | 2026-09-01 | Closed | config completed
P-1615 |  | 2026-09-01 | Shadab.pinitod |  | ems to mppc port issue | sarita | Medium | 2026-09-01 |  | 2026-09-01 | Closed | ports are open
P-1799 |  | 2026-09-01 | Shadab.pinitod |  | opc to scada data forwarding | Niyasdin | Medium | 2026-09-01 |  | 2026-09-01 | Closed | config completed
p-1665 |  | 2026-09-01 | Ashok | qiang.wang | user firewall dlp file mismatch | nitheesh | Medium | 2026-09-01 |  | 2026-09-01 | Closed | after restoring the pa firewall its become okay
p-1665 |  | 2026-09-01 | Ashok | qiang.wang | userfirewall ha config | nitheesh | Medium | 2026-09-01 |  | 2026-09-01 | Closed | config completed
p-1665 |  | 2026-09-01 | Ashok | qiang.wang | third party firewall ha config | nitheesh | Medium | 2026-09-01 |  | 2026-09-01 | Closed | config completed
k-0229 |  | 2026-09-02 | Ashok | qiang.wang | opc_fep forwording | praveen | Medium | 2026-09-02 |  | 2026-09-02 | Closed | config completed
k-0317 |  | 2026-09-02 | Ashok |  | inside firewall license issue | praveen | Medium | 2026-09-02 |  | 2026-09-02 | Closed | config completed
P-3598 |  | 2026-09-02 | Shadab.pinitod |  | IPSec VPN tunnel | Nitheesh | Medium | 2026-09-02 |  | 2026-09-02 | Closed | vpn tunnel is Up
P-1578 |  | 2026-09-02 | Mayur Tisage | yuan.qin | Telnet issue | Niteesh | Medium | 2026-09-02 |  | 2026-09-02 | Closed | Issue resolved
P-1665 |  | 2026-09-02 | Ashok | qiang.wang | PUBLIC IP | Niteesh | Medium | 2026-09-02 |  | 2026-09-02 | Closed | Issue resolved
P-IN01 |  | 2026-09-02 | Ashok |  | airfoce forwording | Niteesh | Medium | 2026-09-02 |  | 2026-09-02 | Closed | after using airforce ip on laptop its okay
P-3598 |  | 2026-09-02 | Shadab.pinitod |  | pre check | Niteesh | Medium | 2026-09-02 |  | 2026-09-02 | Closed | pre chek completed
P-1587 |  | 2026-09-03 | Shadab.pinitod | jun.zhang | data forwarding modification | Manjunath | Medium | 2026-09-03 |  | 2026-09-03 | Closed | config completed
P-1610 |  | 2026-09-03 | Shadab.pinitod |  | public ip | marimuthu | Medium | 2026-09-03 |  | 2026-09-03 | Closed | 8.8.8.8 is pinging
P-1588 |  | 2026-09-03 | Shadab.pinitod |  | outside fw 1,2 config | Niteesh | Medium | 2026-09-03 |  | 2026-09-03 | Closed | config completed
P-1436 |  | 2026-09-03 | Mayur Tisage |  | Telnet issue | Niteesh | Medium | 2026-09-03 |  | 2026-09-03 | Closed | Issue resolved
P-1436 |  | 2026-09-03 | Mayur Tisage |  | Scada Front end power issue | Niteesh | Medium | 2026-09-03 |  | 2026-09-03 | Closed | Issue resolved
P-1812 |  | 2026-09-03 | Mayur Tisage |  | WTG Health BE server installation | Niteesh | Medium | 2026-09-03 |  | 2026-09-03 | Closed | config completed
p-1665 |  | 2026-09-03 | Ashok | qiang.wang | public ip conifig | nitheesh | Medium | 2026-09-03 |  | 2026-09-03 | Closed | config completed 8.8.8.8 rechable
p-1665 |  | 2026-09-03 | Ashok |  | outside firewall ha | nitheesh | Medium | 2026-09-03 |  | 2026-09-03 | Closed | sychronized
p-1665 |  | 2026-09-03 | Ashok |  | core switch 1 ,2 configuration | nitheesh | Medium | 2026-09-03 |  | 2026-09-03 | Closed | completed
p-1610 |  | 2026-09-03 | Ashok | qiang.wang | galileo data not able to go internet | nitheesh | Medium | 2026-09-03 |  | 2026-09-03 | Closed | configued
p-1665 |  | 2026-09-03 | Ashok |  | time server not rechable | nitheesh | Medium | 2026-09-03 |  | 2026-09-03 | Ongoing | waiting for vendor support(material)
P-1665 |  | 2026-09-04 | Marimuthu | yuan.qin | Both Scada and EMS server new configurtion | Praveen | Medium | 2026-09-01 |  | 2026-09-03 | Closed | Both scada and EMS configution done
P-1588 |  | 2026-09-04 | Shadab.pinitod |  | inside fw 1,2 config | nitheesh | Medium | 2026-09-04 |  | 2026-09-04 | Closed | config completed
P-1750 |  | 2026-09-04 | Shadab.pinitod |  | ems to mppc data forwarding | tilak | Medium | 2026-09-04 |  | 2026-09-04 | Closed | config completed
P-1660 |  | 2026-09-04 | Mayur Tisage | yuan.qin | Telnet and DNS ping check | Sangappa | Medium | 2026-09-04 |  | 2026-09-04 | Closed | Issue resolved
P-1588 |  | 2026-09-04 | Shadab.pinitod |  | third party fw 1,2 config | nitheesh | Medium | 2026-09-04 |  | 2026-09-04 | Closed | config completed
P-8004 |  | 2026-09-04 | yuan.qin |  | Scada1 need to reinstall | marimuthu | Medium | 2026-09-04 |  | 2026-09-07 | Closed | Issue resolved
P-1588 |  | 2026-09-07 | Mayur Tisage | yuan.qin | Scada ips are not pinging | Thilak | Medium | 2026-09-07 |  | 2026-09-07 | Closed | Issue resolved
P-1528 |  | 2026-09-07 | Mayur Tisage | yuan.qin | Audit support | Niteesh | Medium | 2026-09-07 |  | 2026-09-07 | Closed | supported
P-1528 |  | 2026-09-07 | Marimuthu | yuan.qin | Both Scada server hanging isssue | Praveen | Medium | 2026-09-07 | Server crash | 2026-09-07 | Closed | Issue resolved
P-1665 |  | 2026-09-07 | Marimuthu | yuan.qin | Scada BE 2 server bridge issue | Saritha | Medium | 2026-09-07 | Server crash | 2026-09-07 | Closed | Again reconfigured has been done and now it's issue resolved brigdhe both ip recahble
P-1407 |  | 2026-09-07 | Marimuthu | yuan.qin | Time server ip not recahble | Niteesh | Medium | 2026-09-07 | Network cabe connection error |  | Closed
P-1588 |  | 2026-09-07 | Shadab.pinitod |  | time server config | Niteesh | Medium | 2026-09-07 | New requirements | 2026-09-07 | Closed | config completed and time is showing correct
P-1588 |  | 2026-09-07 | Shadab.pinitod | jun.zhang | core switch 1, 2 config | Niteesh | Medium | 2026-09-07 | New requirements | 2026-09-07 | Closed | config completed
P-1528 |  | 2026-09-07 | Shadab.pinitod |  | VAPT Audit support | Niteesh | Medium | 2026-09-07 |  | 2026-09-07 | Closed
P-1587 |  | 2026-09-07 | Shadab.pinitod |  | data forwarding | Manjunath | Medium | 2026-09-07 |  | 2026-09-07 | Closed | config completed
P-1436 |  | 2026-09-07 | Mayur Tisage | yuan.qin | Scada Front End server issue | Niteesh | Medium | 2026-09-07 |  | 2026-09-07 | Closed | replaced Storage controller and Ram from WTG Health BE server
P-1427 |  | 2026-09-07 | Shadab.pinitod |  | data forwarding ems to mppc modification | abdullah | Medium | 2026-09-07 |  | 2026-09-07 | Closed | modification completed.
P-1565 |  | 2026-09-08 | Mayur Tisage | yuan.qin | Both Scada and EMS server configution | [5 empty] | Closed
P-1588 |  | 2026-09-08 | Mayur Tisage | yuan.qin | EMS SSH issue | Sangappa | Medium | 2026-09-08 |  | 2026-09-08 | Closed | issue resolved
K334 |  | 2026-09-08 | Mayur Tisage |  | Scada ip ping issue | Albert | Medium | 2026-09-08 |  | 2026-09-08 | Closed | issue resolved
P-1962 |  | 2026-09-08 | Marimuthu | yuan.qin | Both scada server mob not connecting | jeffin | Medium | 2026-09-07 | Server crash | 2026-09-08 | Closed | Issue resolved
P-1436 |  | 2026-09-08 | Shadab.pinitod | jun.zhang | Setup time manuallly in SCADA and EMS server | Niteesh | Medium | 2026-09-08 |  | 2026-09-08 | Closed
P-1746 |  | 2026-09-09 | Shadab.pinitod | jun.zhang | Level 3 switch 1,2 config | Niteesh | Medium | 2026-09-09 | New requirements | 2026-09-09 | Closed | config completed
P-1746 |  | 2026-09-09 | Shadab.pinitod | jun.zhang | Level 2 switch 1,2 config | Niteesh | Medium | 2026-09-09 | New requirements | 2026-09-09 | Closed | config completed
P-1746 |  | 2026-09-10 | Shadab.pinitod |  | Core switch 1,2 Config | Niteesh | Medium | 2026-09-10 | New requirements | 2026-09-10 | Closed | config completed
P-1588 |  | 2026-09-10 | Mayur Tisage |  | Core switch issue | sangappa | medium | 2026-09-10 |  | 2026-09-10 | Closed | issue found out to be from core switch side. Respective team is checking
P-1746 |  | 2026-09-10 | Shadab.pinitod |  | Core switch 3,4 Configuration | Niteesh | medium | 2026-09-10 | New requirements | 2026-09-10 | Closed | config completed
P-1746 |  | 2026-09-10 | Shadab.pinitod |  | outside fw 1 config | Niteesh | medium | 2026-09-10 | New requirements | 2026-09-10 | Closed | config completed
P-1660 |  | 2026-09-11 | Mayur Tisage |  | Time sync issue | Niteesh | Medium | 2026-09-11 |  | 2026-09-11 | Closed | issue resolved
P-1962 |  | 2026-09-11 | Shadab.pinitod | jun.zhang | scada to opc data forwarding | jeffin | Medium | 2026-09-11 | New requirements | 2026-09-11 | Closed | config completed
P-1587 |  | 2026-09-11 | Shadab.pinitod | jun.zhang | ems to mppc data forwarding | Manjunath | Medium | 2026-09-11 | New requirements | 2026-09-11 | Closed | config completed
P-1962 |  | 2026-09-11 | Shadab.pinitod |  | ems to mppc data forwarding config | jeffin | Medium | 2026-09-11 | New requirements | 2026-09-11 | Closed | config completed
P-1665 |  | 2026-09-12 | Marimuthu |  | Scada BE 1 server ssh issue | saritta | Medium | 2026-09-12 | Server crash | 2026-09-12 | Closed | Issue resolved
P-1750 |  | 2026-09-15 | Shadab.pinitod |  | ems to mppc data forwarding | sarita | Medium | 2026-09-15 |  | 2026-09-15 | Closed
P-1479 |  | 2026-09-15 | Marimuthu |  | WTG helath BE 1 and front end server power cable issue | Niteesh | Medium | 2026-09-15 | Server crash |  | Closed | SSH issue resolved and confirm by Rong Rong
P-1486 |  | 2026-09-15 | Marimuthu | jun.zhang | WTG health BE 1 sevre not working | Niteesh | Medium | 2026-09-15 | Server crash | 2026-09-15 | Closed | Issue resolved
P-1665 |  | 2026-09-15 | Marimuthu |  | Scada BE 2 SSH issue | Niteesh | Medium | 2026-09-15 | Server crash |  | Closed | Issue resolved | waiting site person provide remote support check issue
p-1707 |  | 2026-09-15 | qiang.wang |  | Zone 1 server is unreachable and still under investigation |  | Medium | 2026-09-15 |  |  | Ongoing
p-1846 |  | 2026-09-15 | Mayur Tisage | qiang.wang | Scada BE server not reachable zone2 server |  | Medium | 2026-09-15 | Network cabe connection error |  | Closed | issue resolved, interface was down
p-1812 |  | 2026-09-15 | Ashok | jun.zhang | ha clusteer issue | nitheesh | Medium | 2026-09-15 | New requirements | 2026-09-15 | Closed | ha configured
p-1812 |  | 2026-09-15 | Ashok |  | mppc to ems forwording | nitheesh | Medium | 2026-09-15 | New requirements | 2026-09-15 | Closed | configuration compleated
P-8003 |  | 2026-09-15 | yuan.qin |  | cms need to update | nitheesh | Medium | 2026-09-15 | New requirements
P-1747 |  | 2026-09-15 | Shadab.pinitod |  | Level 3 switch 1,2,3 config | nitheesh | Medium | 2026-09-15 | New requirements | 2026-09-15 | Closed | configuration compleated
P-1747 |  | 2026-09-15 | Shadab.pinitod |  | Level 2 switch 1 config | nitheesh | Medium | 2026-09-15 | New requirements | 2026-09-15 | Closed | configuration compleated
P-1453 |  | 2026-09-15 | Mayur Tisage | Ashok | Scada Servers not pinging | Sarita | Medium | 2026-09-15 | New requirements | 2026-09-15 | Closed | issue resolved
P-1746 |  | 2026-09-16 | Shadab.pinitod |  | outside fw 1,2 config | nitheesh | Medium | 2026-09-16 | New requirements | 2026-09-16 | Closed | configuration compleated and HA also stable
P-1746 |  | 2026-09-16 | Shadab.pinitod |  | inside fw 1,2 config | nitheesh | Medium | 2026-09-16 | New requirements | 2026-09-16 | Closed | configuration compleated and HA also stable
P-1746 |  | 2026-09-17 | Shadab.pinitod |  | third party fw 1,2 config | nitheesh | Medium | 2026-09-17 | New requirements | 2026-09-17 | Closed
P-1747 |  | 2026-09-17 | Shadab.pinitod |  | level 2 switch 2 config | nitheesh | Medium | 2026-09-17 | New requirements | 2026-09-17 | Closed | config completed
P-1588 |  | 2026-09-17 | Mayur Tisage |  | Scada ip issues | Niteesh | Medium | 2026-09-17 |  | 2026-09-17 | Closed | issue resolved
P-3598 |  | 2026-09-17 | Marimuthu |  | EMS 3and 4 OS version checking | Saritha | Medium | 2026-09-17 | New requirements | 2026-09-17 | Closed | Checked done
p-2022 |  | 2026-09-17 | Ashok |  | outside firewall internet config | nitheesh | Medium | 2026-09-16 | New requirements | 2026-09-17 | Closed | configuration compleated
p-2022 |  | 2026-09-16 | Ashok |  | outside firewall 1,2 os upgrade | nitheesh | Medium | 2026-09-16 | New requirements | 2026-09-17 | Closed | configuration compleated
p-2022 |  | 2026-09-16 | Ashok |  | level 3 switch ll 1,2 os config | nitheesh | Medium | 2026-09-16 | New requirements | 2026-09-17 | Closed | configuration compleated
P-1747 |  | 2026-09-17 | Shadab.pinitod |  | Core switch 1, 2 config | nitheesh | Medium | 2026-09-17 | New requirements | 2026-09-17 | Closed | config completed
P-1665 |  | 2026-09-17 | Marimuthu |  | Scada and EMS ip are not recahble | Saritha | Medium | 2026-09-17 | Network cabe connection error | 2026-09-17 | Closed | Issue resolved
P-1486 |  | 2026-09-17 | Marimuthu |  | WTG BE server not recahble | Saritha | Medium | 2026-09-17 | Server crash |  | Closed | IP conflict issue resolved
P-1747 |  | 2026-09-17 | Shadab.pinitod |  | OS upgrade of outside fw 1,2 | nitheesh | Medium | 2026-09-17 | New requirements | 2026-09-17 | Closed
p-1578 |  | 2026-09-17 | qiang.wang |  | Gailileo Public issue | RongRong Huang | High | 2026-09-17 | New requirements |  | Closed | Urgent need for Galileo data. On-site check to see if there is a compatible laptop for remote guidance in installing or mailing the Galileo operation and maintenance laptop for emergency fire suppression.
P-1565 |  | 2026-09-17 | Mayur Tisage |  | EMS, SCADA server configuration | Niteesh | High | 2026-09-17 | New requirements |  | Closed | Config conpleted
P-1749 |  | 2026-09-17 | Mayur Tisage |  | SCADA Ping issue | Revappa | Medium | 2026-09-17 |  |  | Closed | Issure resolved.
P-1707 |  | 2026-09-17 | Mayur Tisage |  | WTG BE server Raid Controller issue | Quing Wang | Medium | 2026-09-17 |  |  | Closed | replaced Storage controller from WTG Health BE server 2
P-1565 |  | 2026-09-17 | Mayur Tisage |  | PPC Server Configuration | Niteesh | High | 2026-09-18 |  |  | Closed | config completed
P-1747 |  | 2026-09-18 | Shadab.pinitod |  | outside fw 1,2 config | nitheesh | Medium | 2026-09-18 | New requirements | 2026-09-18 | Closed
p-2022 |  | 2026-09-17 | Ashok |  | level2 switch1,2 | nitheesh | Medium | 2026-09-17 | New requirements | 2026-09-17 | Closed | Config conpleted
p-2022 |  | 2026-09-17 | Ashok |  | level3switch 1,2 | nitheesh | Medium | 2026-09-17 | New requirements | 2026-09-17 | Closed | Config conpleted
p-2022 |  | 2026-09-17 | Ashok |  | Core switch 1,2 Config | nitheesh | Medium | 2026-09-17 | New requirements | 2026-09-17 | Closed | Config conpleted
P-1587 |  | 2026-09-18 | Ashok |  | public ip issue | nitheesh | Medium | 2026-09-17 | New requirements | 2026-09-18 | Closed | custopmer side gateway issue
p-2022 |  | 2026-09-18 | Ashok |  | ha config outside firewall | nitheesh | Medium | 2026-09-17 | New requirements | 2026-09-18 | Closed | config completed
p-2022 |  | 2026-09-18 | Ashok |  | ha config inside firewall | nitheesh | Medium | 2026-09-17 | New requirements | 2026-09-18 | Closed | config completed
P-1587 |  | 2026-09-18 | Shadab.pinitod |  | scada to srldc and ems to mppc data forwarding | manjunath | Medium | 2026-09-18 | New requirements | 2026-09-18 | Closed | config completed and ports are open
P-1747 |  | 2026-09-18 | Shadab.pinitod |  | inside fw 1,2 config | nitheesh | Medium | 2026-09-18 | New requirements | 2026-09-18 | Closed | config completed
P-1747 |  | 2026-09-18 | Shadab.pinitod |  | third party fw 1,2 config | nitheesh | Medium | 2026-09-18 | New requirements | 2026-09-18 | Closed | config completed
|  | 2026-09-18 | Marimuthu |  | WTG server mob not connecting | Thilak | Medium | 2026-09-18 | Server crash | 2026-09-18 | Closed | WTG server SSH issue resolved
P-1615 |  | 2026-09-18 | Marimuthu |  | WTG server mob not connecting | Jeffin | Medium | 2026-09-18 | Server crash | 2026-09-18 | Closed | WTG all server SSH issue resolved
P-1480 |  | 2026-09-18 | Marimuthu |  | WTG server hardware issue | Nitheesh | Medium | 2026-09-18 | Hard drive failure | 2026-09-18 | Closed | Remove the server in panel and clean then mounted again same issue now change the HDD to Network sever process is ongoing
P-1565 |  | 2026-09-18 | Shadab.pinitod |  | level 3 switch 1 config | Nitheesh | Medium | 2026-09-18 | New requirements | 2026-09-18 | Closed | config completed
P-1427 |  | 2026-09-22 | Mayur Tisage |  | Time sync issue with the SCADA & EMS | abdullah | Medium |  | Network cabe connection error |  | Closed
P-1846 |  | 2026-09-22 | Shadab.pinitod |  | Time server issue | Marimuthu | Medium |  | Network cabe connection error |  | Closed
p-2022 |  | 2026-09-21 | Ashok |  | inside firewall os issue | nitheesh | Medium | 2026-09-21 | New requirements | 2026-09-21 | Closed | configured
p-2022 |  | 2026-09-21 | Ashok |  | time server | nitheesh | Medium | 2026-09-21 | New requirements |  | Closed | configured
p-1945 |  | 2026-09-21 | Ashok |  | level3 switch 1,2,3 | nitheesh | Medium | 2026-09-21 | New requirements | 2026-09-21 | Closed | completed
p-1945 |  | 2026-09-21 | Ashok |  | level2 switch 1,2 | nitheesh | Medium | 2026-09-21 | New requirements | 2026-09-21 | Closed | completed
p-1945 |  | 2026-09-21 | Ashok |  | core switch 1,2 | nitheesh | Medium | 2026-09-21 | New requirements | 2026-09-21 | Closed | completed
p-2022 |  | 2026-09-21 | Ashok |  | inside ha config | nitheesh | Medium | 2026-09-21 | New requirements | 2026-09-21 | Closed | completed
p-1945 |  | 2026-09-21 | Ashok |  | inside firewall 1,2config | nitheesh | Medium | 2026-09-21 | New requirements | 2026-09-21 | Closed | completed
P-1962 |  | 2026-09-21 | Marimuthu |  | Edge STD & Galileo APP not reachble via 10 segment | Jeffin | Medium |  | New requirements |  | Closed
p-2022 |  | 2026-09-22 | Ashok |  | timeserver config | ashok | Medium | 2026-09-22 | New requirements | 2026-09-22 | Closed | config completed
P-1407 |  | 2026-09-21 | Marimuthu |  | All server auto power option issue | Praveen | Medium | 2026-09-21 | Server crash | 2026-09-21 | Closed | Auto power option enabled permentely now it's working fine and issue resolved
P-1846 |  | 2026-09-21 | Marimuthu |  | Scada BE 1 server not working | Nitheesh | High | 2026-09-21 | Server crash | 2026-09-21 | Closed | Issue resolved
P-1747 |  | 2026-09-22 | Marimuthu |  | Both Scada and EMS bridge configution | Nitheesh | Medium | 2026-09-22 | New requirements | 2026-09-22 | Closed | Bridge configuration done
P-1962 |  | 2026-09-22 | Marimuthu |  | .Galilio STD server mob not conecting | jeffin | Medium | 2026-09-22 | Server crash | 2026-09-22 | Closed | Issue resolved
P-1843 |  | 2026-09-22 | Marimuthu |  | EMS server1 not pinging | Jeffin | Medium | 2026-09-21 | Server crash |  | Closed
P-1747 |  | 2026-09-21 | Shadab.pinitod |  | outside ha config | nitheesh | Medium | 2026-09-21 | New requirements | 2026-09-21 | Closed | config completed
P-1747 |  | 2026-09-21 | Shadab.pinitod |  | inside ha config | nitheesh | Medium | 2026-09-21 | New requirements | 2026-09-21 | Closed | config completed
P-1747 |  | 2026-09-21 | Shadab.pinitod |  | third party ha config | nitheesh | Medium | 2026-09-21 | New requirements | 2026-09-21 | Closed | config completed
P-1846 |  | 2026-09-22 | Mayur Tisage |  | Front End server1 & 2 auto start and IP not reachble | abdullah | Medium |  | Server crash |  | Closed | Auto start enabled and reachable
P-1660 |  | 2026-09-22 | Mayur Tisage |  | galielo folder not accesible | rongrong | Medium |  | New requirements |  | Closed
p-1945 |  | 2026-09-22 | Ashok |  | inside firewall config | nitheesh | Medium | 2026-09-22 | New requirements | 2026-09-22 | Closed
p-1665 |  | 2026-09-22 | Ashok |  | time server | nitheesh | Medium | 2026-09-22 | New requirements |  | Closed | Time server installed and configured
P-1843 |  | 2026-09-23 | Marimuthu |  | EMS 2 not pinking | Nitheesh | Medium |  |  |  | Closed
P-1653 |  | 2026-09-23 | Mayur Tisage |  | Network 2 server ESXI not working | Nitheesh |  |  |  |  | Closed | Device are reachble
P-1747 |  | 2026-09-23 | Marimuthu |  | EMS 2 not working | Nitheeesh |  |  |  |  | Closed | Main IP was removed and reconfigured
K-3017 |  | 2026-09-23 | Ashok |  | Vpn user creation | Nitheeesh | medium | 2026-09-23 | New requirements | 2026-09-23 | Closed | config completed
K-0334 |  | 2026-09-23 | Ashok |  | Vpn user creation | Nitheeesh | medium | 2026-09-23 | New requirements | 2026-09-23 | Closed | config completed
K-0229 |  | 2026-09-23 | Ashok |  | Vpn user creation | Nitheeesh | medium | 2026-09-23 | New requirements | 2026-09-23 | Closed | config completed
p-1587 |  | 2026-09-23 | Ashok |  | mppc to ems data forwording | Nitheeesh | medium | 2026-09-23 | New requirements | 2026-09-23 | Closed | config completed
p-1587 |  | 2026-09-23 | Ashok |  | srldc to scada data forwording | Nitheeesh | medium | 2026-09-23 | New requirements | 2026-09-23 | Closed | config completed
P-1578 |  | 2026-09-24 | Mayur Tisage |  | Edge gateway can not login | Nitheesh | Medium | 2026-09-24 |  | 2026-09-24 | Closed | issue resolved
p-1945 |  | 2026-09-24 | Ashok |  | time server web page not accessible | Nitheesh | Medium | 2026-09-24 |  | 2026-09-24 | Closed | issue resolved
p-1587 |  | 2026-09-24 | Ashok |  | srldc to scada data forwording | Nitheeesh | medium | 2026-09-24 | New requirements | 2026-09-24 | Closed | config completed
p-1945 |  | 2026-09-24 | Ashok |  | time server config | Nitheesh | Medium | 2026-09-24 |  | 2026-09-24 | Closed | config completed
p-1565 |  | 2026-09-24 | Shadab.pinitod |  | level 2 switch config | Nitheesh | Medium | 2026-09-24 | New requirements | 2026-09-24 | Closed | config completed
P-1812 |  | 2026-09-24 | Mayur Tisage |  | Packet loss in core switch | Niteesh | Medium | 2026-09-24 |  | 2026-09-24 | Closed | Issure resolved.
P-1578 |  | 2026-09-24 | Mayur Tisage |  | Edge gateway can not login, precheck status | Niteesh | Medium | 2026-09-24 |  | 2026-09-24 | Closed | Issure resolved.
P-1747 |  | 2026-09-24 | Marimuthu |  | All server SSH and auto power option not working | Niteesh | Medium | 2026-09-24 | New requirements | 2026-09-24 | Closed | Issue resolved
P-1479 |  | 2026-09-24 | Marimuthu |  | WTG helath server SSH not connnecting | Dinesh | Medium | 2026-09-24 | Server crash | 2026-09-24 | Closed | Issue resolved
P-1565 |  | 2026-09-24 | Shadab.pinitod |  | level 2 switch 1 ,2 config | Niteesh | Medium | 2026-09-25 | New requirements | 2026-09-24 | Closed | config completed
P-1729 |  | 2026-09-25 | Shadab.pinitod |  | scada to srldc data forwarding | sangappa | Medium | 2026-09-25 | New requirements | 2026-09-25 | Closed | config completed
P-1576 |  | 2026-09-25 | Shadab.pinitod |  | pre check | Niteesh | Medium | 2026-09-25 |  | 2026-09-25 | Closed | config completed
P-1962 |  | 2026-09-25 | Shadab.pinitod |  | scada to srldc data forwarding | jeffin | Medium | 2026-09-25 | New requirements | 2026-09-25 | Closed | config completed
P-1945 |  | 2026-09-25 | Ashok |  | inside firewall core balance ha | nitheesh | Medium | 2026-09-25 | New requirements | 2026-09-25 | Closed | config completed
P-1945 |  | 2026-09-25 | Ashok |  | Outsidw firewall core balance ha | nitheesh | Medium | 2026-09-25 | New requirements | 2026-09-25 | Closed | config completed
P-1747 |  | 2026-09-25 | Ashok |  | time server | nitheesh | Medium | 2026-09-25 | New requirements | 2026-09-25 | Closed | config completed
P-1945 |  | 2026-09-25 | Ashok |  | public ip config | nitheesh | Medium | 2026-09-25 | New requirements | 2026-09-25 | Closed | config completed
P-1565 |  | 2026-09-25 | Shadab.pinitod |  | outside 1,2 OS upgrade | nitheesh | Medium | 2026-09-25 | New requirements | 2026-09-25 | Closed | config completed
P-1746 |  | 2026-09-28 | Shadab.pinitod |  | Time server config | nitheesh | Medium | 2026-09-28 | New requirements | 2026-09-28 | Closed | config completed
P-1746 |  | 2026-09-28 | Shadab.pinitod |  | public ip configured | nitheesh | Medium | 2026-09-28 | New requirements | 2026-09-28 | Closed | config completed
P-1962 |  | 2026-09-28 | Marimuthu |  | DNS,telnet,ENOS Pre check pending | Aaron | medium |  |  |  | Ongoing | Waiting for remote
P-1546 |  | 2026-09-28 | Shadab.pinitod |  | Turbine IP not reachable in core swicth | sangappa | Medium |  |  |  | Ongoing | Waiting for remote
P-1653 |  | 2026-09-28 | Mayur Tisage |  | WTG BE server not reachbale,Auto start ENOS & Galielo Pre check penidng | sangappa | Medium |  |  |  | Closed
P-1846 |  | 2026-09-28 | Mayur Tisage |  | Telnet,DNS,Autostart,Enos & Galielo Precheck Pending | Nitheesh | Medium |  |  |  | Closed | resolved by Niteesh sir
P-1812 |  | 2026-09-28 | Mayur Tisage |  | Radius Serevr not reachable,Auto start,ENOS& Galielo Prec checks pending | Veeresh,Nitheesh | Medium |  |  |  | Closed | Radius server ips are reachable, configuration is done by Veeresh
P-1846 |  | 2026-09-28 | Mayur Tisage |  | Radius Serevr not reachable,Auto start,ENOS& Galielo Prec checks pending | Veeresh,Nitheesh | Medium |  |  |  | Closed | Radius server ips are reachable, configuration is done by Veeresh
P-1812 |  | 2026-09-28 | Shadab.pinitod |  | ip sec vpn creation | Veeresh | Medium | 2026-09-28 | New requirements | 2026-09-28 | Closed | config completed
P-1511 |  | 2026-09-29 | Shadab.pinitod |  | data server unable to access | aaron | Medium | 2026-09-29 |  | 2026-09-29 | Closed
p-1588 |  | 2026-09-28 | Ashok |  | srldc _scada forwording | ashok | Medium | 2026-09-28 | New requirements | 2026-09-28 | Closed | config completed
p-1588 |  | 2026-09-28 | Ashok |  | mppc_ems forwording | ashok | Medium | 2026-09-28 | New requirements | 2026-09-28 | Closed | config completed
p-1588 |  | 2026-09-28 | Ashok |  | switch ha issuue | ashok | Medium | 2026-09-28 | New requirements | 2026-09-28 | Closed | config completed
p-1588 |  | 2026-09-28 | Ashok |  | third party ha issue | ashok | Medium | 2026-09-28 | New requirements | 2026-09-28 | Closed | config completed
p-1945 |  | 2026-09-29 | Ashok |  | zone1 not able to ping galileo data | ashok | Medium | 2026-09-29 | New requirements | 2026-09-29 | Closed | config completed
p-1945 |  | 2026-09-29 | Ashok |  | ntp sync issue | ashok | Medium | 2026-09-29 | New requirements | 2026-09-29 | Closed | config completed
p-2022 |  | 2026-09-29 | Ashok |  | time server issue | ashok | Medium | 2026-09-29 | New requirements | 2026-09-29 | Closed | config completed
p-2022 |  | 2026-09-29 | Ashok |  | inside ha issue | ashok | Medium | 2026-09-29 | New requirements | 2026-09-29 | Closed | config completed
P-1653 |  | 2026-09-29 |  |  | all servers mgmt ping issue | Niteesh | Medium | 2026-09-29 |  |  | Closed | issue resolved
P-1846 |  | 2026-09-29 |  |  | Network server Not recahble | Veeresh | Medium | 2026-09-29 |  | 2026-09-29 | Closed | issue resolved
P-2022 |  | 2026-09-29 |  |  | SCADA and EMS server configuration | Niteesh | Medium | 2026-09-29 |  | 2026-09-29 | Closed | Config conpleted
P-1747 |  | 2026-09-29 | Marimuthu |  | Bridge ip issue | Niteesh | Medium | 2026-09-29 | New requirements | 2026-09-29 | Closed | Issue resolved
P-1945 |  | 2026-09-29 | Marimuthu |  | Scada and EMS Time issue | Niteesh | Medium | 2026-09-29 | New requirements | 2026-09-29 | Closed | Issue resolved
P-1846 |  | 2026-09-29 | Shadab.pinitod |  | public ip issue | Niteesh | Medium | 2026-09-29 |  | 2026-09-29 | Closed | dns is pinging
P-1873 |  | 2026-09-30 | Mayur Tisage |  | WTG servers not connecting to moba | Niteesh | Medium | 2026-09-30 |  | 2026-09-30 | Closed | ips are pinging
P-1873 |  | 2026-09-30 | Mayur Tisage |  | Telnet issue | Sangappa | Medium | 2026-09-30 |  | 2026-09-30 | Closed | issue resolved
p-2022 |  | 2026-09-30 | Ashok |  | ntp sync issue | mayur | Medium | 2026-09-30 |  | 2026-09-30 | Closed | enabled the ntp d
p-1873 |  | 2026-09-30 | Ashok |  | telnet isssue | mayur | Medium | 2026-09-30 |  | 2026-09-30 | Closed | chck firewall end enabled front end server ufw status
p-2022 |  | 2026-09-30 | Ashok | yuan.qin | scada1 ems 2 time sync | mayur | Medium | 2026-09-30 |  | 2026-09-30 | Closed | time zone modified
P-1731 |  | 2026-09-30 | Shadab.pinitod |  | inside fw ha issue | Niteesh | Medium | 2026-09-30 |  | 2026-09-30 | Closed | HA is stable now
P-1799 |  | 2026-09-30 | Shadab.pinitod |  | ems to mppc data forwarding | Niyazdin | Medium | 2026-09-30 |  | 2026-09-30 | Closed
P-1731 |  | 2026-09-30 | Shadab.pinitod | yuan.qin | pre check | Niteesh | Medium | 2026-09-30 |  | 2026-09-30 | Closed | pre checked completed
P-1731 |  | 2026-09-30 | Shadab.pinitod |  | Public ip issue | Niteesh | Medium | 2026-09-30 |  | 2026-09-30 | Closed
P-1731 |  | 2026-09-30 | Shadab.pinitod |  | data forwarding mppc2 to ems2 | sarita | Medium | 2026-09-30 |  | 2026-09-30 | Closed | config completed
p-1586 |  | 2026-10-01 | Ashok |  | level 3 switch 1,2 config | nitheesh | medium | 2026-10-01 | New requirements | 2026-09-30 | Closed
p-1746 |  | 2026-10-01 | Ashok |  | sscad sever ntp sync | mari muthu | medium | 2026-10-01 | New requirements | 2026-09-30 | Closed
p-1731 |  | 2026-09-30 | Ashok |  | mppc to ems port not open | mari muthu | medium | 2026-10-01 | New requirements |  | Closed
P-1856 |  | 2026-10-05 | Shadab.pinitod |  | Level 2 switch 1,2 config | nitheesh | medium | 2026-10-05 | New requirements | 2026-10-05 | Closed | config completed
P-1665 |  | 2026-10-05 | Shadab.pinitod |  | ems to mppc data forwarding | sarita | medium | 2026-10-05 | New requirements | 2026-10-05 | Closed | config completed
P-1665 |  | 2026-10-05 | Shadab.pinitod |  | scada to srldc data forwarding | sarita | medium | 2026-10-05 | New requirements | 2026-10-05 | Closed | config completed
P-1965 |  | 2026-10-05 | Mayur Tisage |  | Scada ssh not working | nitheesh | Medium | 2026-10-05 |  | 2026-10-05 | Closed | issue resolved
P-2022 |  | 2026-10-05 | Mayur Tisage |  | ppc server installation | nitheesh |  | 2026-10-05 |  | 2026-10-05 | Closed | config completed
P-1856 |  | 2026-10-05 | Mayur Tisage |  | Scada configuration | nitheesh |  | 2026-10-05 |  | 2026-10-05 | Closed | config completed
p-1731 |  | 2026-10-05 | Ashok |  | vpn not connetcing / scada web page not working | veeresh | medium | 2026-10-05 | New requirements | 2026-10-05 | Closed | route missing after adding it worked
P-1856 |  | 2026-10-06 | Shadab.pinitod |  | Core switch 1,2 config | nitheesh | medium | 2026-10-06 | New requirements | 2026-10-06 | Closed | config completed
P-1746 |  | 2026-10-06 | Mayur Tisage |  | Scada os installation and configuration | nitheesh | Medium | 2026-10-06 | New requirements | 2026-10-06 | Closed | config completed
P-1856 |  | 2026-10-06 | Shadab.pinitod |  | Outside fw 1,2 OS upgrade | nitheesh | Medium | 2026-10-06 | New requirements | 2026-10-06 | Closed | config completed
P-2022 |  | 2026-10-06 | Mayur Tisage |  | WTG health be server installation | nitheesh | Medium | 2026-10-06 | New requirements | 2026-10-06 | Closed | Installation completed
P-1945 |  | 2026-10-06 | Mayur Tisage |  | Server ip ping issues at core switch | Abdullah | Medium | 2026-10-06 |  | 2026-10-06 | Closed | checked the issue is on switch side, reverted to network team for support
P-1632 |  | 2026-10-06 | Marimuthu |  | Scada and network cable routing issue | Praveen | Medium | 2026-10-06 | Network cabe connection error | 2026-10-06 | Closed | canle routing activity was completed all server was working fine
P-1856 |  | 2026-10-07 | Shadab.pinitod |  | outside fw 1,2 config and HA | nitheesh | Medium | 2026-10-07 | New requirements | 2026-10-07 | Closed | config completed and also HA stable
P-1856 |  | 2026-10-07 | Shadab.pinitod |  | inside fw 1, 2 config and HA | nitheesh | Medium | 2026-10-07 | New requirements | 2026-10-07 | Closed | config completed and also HA stable
P-1856 |  | 2026-10-07 | Shadab.pinitod |  | SSL vpn creation | nitheesh | Medium | 2026-10-07 | New requirements | 2026-10-07 | Closed | SSL VPN is created and verified without radius server
P-1856 |  | 2026-10-07 | Shadab.pinitod |  | Ip sec vpn creation | nitheesh | Medium | 2026-10-07 | New requirements | 2026-10-07 | Closed | ipsec vpn created and it is UP.
P-1856 |  | 2026-10-07 | Shadab.pinitod |  | time server configured | nitheesh | Medium | 2026-10-07 | New requirements | 2026-10-07 | Closed | config completed
P-1752 |  | 2026-10-08 | Shadab.pinitod |  | outside fw 1 config | nitheesh | Medium | 2026-10-08 | New requirements | 2026-10-08 | Closed | config completed
P-1752 |  | 2026-10-08 | Shadab.pinitod |  | Level3 access switch 1,2 config | nitheesh | Medium | 2026-10-08 | New requirements | 2026-10-08 | Closed | config completed
P-1846 |  | 2026-10-08 | Mayur Tisage |  | Time sync issue | abdullah | Medium | 2026-10-08 |  | 2026-10-08 | Closed | issue resolved
P-1856 |  | 2026-10-08 | Mayur Tisage |  | Front end servers configuration | Niteesh | Medium | 2026-10-08 |  | 2026-10-08 | Closed | config completed
P-1812 |  | 2026-10-08 | Shadab.pinitod |  | ems to mppc data forwarding | sangappa | Medium | 2026-10-08 |  | 2026-10-08 | Closed | config completed
P-1945 |  | 2026-10-09 | Marimuthu |  | SSH is both scada | nitheesh | Medium | 2026-10-09 | New requirements | 2026-10-09 | Closed | issue resolved
p-1660 |  | 2026-10-09 | Marimuthu |  | NTP issue | nitheesh | Medium | 2026-10-09 | New requirements | 2026-10-09 | Closed | issue resolved
P-1812 |  | 2026-10-09 | Mayur Tisage |  | Network server Not recahble | Niteesh | Medium | 2026-10-09 |  | 2026-10-09 | Closed | issue resolved
P-1653 |  | 2026-10-09 | Mayur Tisage |  | WTG Servers not reachable | Niteesh | Medium | 2026-10-09 |  | 2026-10-09 | Closed | issue resolved
P-1887 |  | 2026-10-12 | Shadab.pinitod |  | inside fw HA | thilak | Medium | 2026-10-12 |  | 2026-10-12 | Closed | issue resolved
P-1887 |  | 2026-10-12 | Shadab.pinitod |  | data forwarding ems to mppc | thilak | Medium | 2026-10-12 | New requirements | 2026-10-12 | Closed | config completed
P-1436 |  | 2026-10-12 | Marimuthu |  | NTP issue for WTG server | Niteesh | Medium | 2026-10-12 | New requirements | 2026-10-12 | Closed | Issue resolved
P-1665 |  | 2026-10-12 | Marimuthu |  | WTG server kvm and vm not working | Saritha | Medium | 2026-10-12 | Network cabe connection error | 2026-10-12 | Closed | Issue resolved all server are working fine
P-1665 |  | 2026-10-12 | Marimuthu |  | WTG helath server not working | Saritha | Medium | 2026-10-12 | Network cabe connection error | 2026-10-12 | Closed | Issue resolved
P-1744 |  | 2026-10-12 | Shadab.pinitod |  | Level3 access switch 1,2 config | Niteesh | Medium | 2026-10-12 | New requirements | 2026-10-12 | Closed | config completed
P-1665 |  | 2026-10-12 | Shadab.pinitod |  | saisi swicth config | Niteesh | Medium | 2026-10-12 | New requirements | 2026-10-12 | Closed | config completed
p-1737 |  | 2026-10-12 | Shadab.pinitod |  | time server not reachable from zone 1 | Niteesh | Medium | 2026-10-12 | New requirements | 2026-10-12 | Closed | config completed
P-1744 |  | 2026-10-12 | Shadab.pinitod |  | Level2 access switch 1,2 config | Niteesh | Medium | 2026-10-12 | New requirements | 2026-10-12 | Closed | config completed
P-1653 |  | 2026-10-12 | Mayur Tisage |  | Telnet issue in STD server | sangappa | Medium | 2026-10-12 |  | 2026-10-12 | Closed | issue resolved
P-1653 |  | 2026-10-12 | Mayur Tisage |  | Core switch ips are not pinging in WTG | sangappa | Medium | 2026-10-12 |  | 2026-10-12 | Closed | issue resolved
P-2022 |  | 2026-10-12 | Mayur Tisage |  | PPC Server Configuration | Niteesh | Medium | 2026-10-12 |  | 2026-10-12 | Closed | config completed
P-1427 |  | 2026-10-12 | Mayur Tisage |  | Galilio data server ip are not reachable | Niteesh | Medium | 2026-10-12 |  | 2026-10-12 | Closed | issue resolved
P-1746 |  | 2026-10-12 | Mayur Tisage |  | Scada Bridge ip issues | Niyasdin | Medium | 2026-10-12 |  | 2026-10-12 | Closed | issue resolved
P-1660 |  | 2026-10-13 | Marimuthu |  | NTP issue | Rongrong | Medium | 2026-10-13 |  | 2026-10-13 | Closed | issue resolved
P-2026 |  | 2026-10-13 | Marimuthu |  | ssh issue | Manjunath | Medium | 2026-10-13 |  | 2026-10-13 | Closed | issue resolved
P-1731 |  | 2026-10-13 | Marimuthu |  | DNS and telnet issue | jeffin | Medium | 2026-10-13 |  | 2026-10-13 | Closed | issue resolved
P-1615 |  | 2026-10-13 | Marimuthu |  | ssh issue | Niyazin | Medium | 2026-10-13 |  | 2026-10-13 | Ongoing
P-1744 |  | 2026-10-13 | Shadab.pinitod |  | Core switch 1,2 config | Niteesh | Medium | 2026-10-13 |  | 2026-10-13 | Closed | config completed
P-1427 |  | 2026-10-13 | Shadab.pinitod |  | data forwarding scada to opc | Abdullah | Medium | 2026-10-13 | New requirements | 2026-10-13 | Closed | config completed
P-1749 |  | 2026-10-13 | Marimuthu |  | Scada BE 1 server not working | Niteesh | High | 2026-10-13 |  | 2026-10-13 | Ongoing
P-1744 |  | 2026-10-13 | Shadab.pinitod |  | firewalls os upgrade | Niteesh | Medium | 2026-10-13 |  | 2026-10-13 | Closed
P-1749 |  | 2026-10-13 | Shadab.pinitod |  | ems to mppc data forwarding | niyasdin | Medium | 2026-10-13 | New requirements | 2026-10-13 | Closed | config completed
p-1721 |  | 2026-10-13 | Ashok |  | port forwording requirement | jeffin | Medium | 2026-10-13 | New requirements | 2026-10-13 | Closed | config completed
p-3598 |  | 2026-10-13 | Ashok |  | dual chanel internet requirement | bnitheesh | Medium | 2026-10-13 | New requirements | 2026-10-13 | Closed | config completed
p-1945 |  | 2026-10-13 | Ashok |  | mstp protocol enabed at core switch | abdulla | Medium | 2026-10-13 | New requirements | 2026-10-13 | Closed | config completed
p-2022 |  | 2026-10-13 | Ashok |  | scada high cpu utilisation | mari | Medium | 2026-10-13 | New requirements | 2026-10-13 | Closed | config completed
k-0410 |  | 2026-10-13 | Ashok |  | upper swicth A Config | nitheesh | Medium | 2026-10-13 | New requirements | 2026-10-13 | Closed | config completed
k-0410 |  | 2026-10-14 | Ashok |  | upper swicth B Config | nitheesh | Medium | 2026-10-13 | New requirements | 2026-10-14 | Closed | config completed
k-0410 |  | 2026-10-14 | Ashok |  | CORE SWITCH A,B,C Config | nitheesh | Medium | 2026-10-13 | New requirements | 2026-10-14 | Closed | config completed
k-0410 |  | 2026-10-14 | Ashok |  | dmz switch config | nitheesh | Medium | 2026-10-13 | New requirements | 2026-10-14 | Closed | config completed
p-1429 |  | 2026-10-14 | Ashok |  | data not reaching customer | nitheesh | Medium | 2026-10-13 | New requirements | 2026-10-14 | Closed | palo aldto tcp lock condition then restored it
P-1744 |  | 2026-10-14 | Shadab.pinitod |  | outside fw 1,2 config with HA | nitheesh | Medium | 2026-10-14 | New requirements | 2026-10-14 | Closed | config completed
P-1610 |  | 2026-10-14 | Shadab.pinitod |  | Time server ip ping issue | marimuthu | Medium | 2026-10-14 |  | 2026-10-14 | Closed | Issue resolved.
p-1610 |  | 2026-10-14 | Ashok |  | time sync issue | marimuthu | Medium | 2026-10-14 |  | 2026-10-14 | Closed | Issue resolved.
P-1752 |  | 2026-10-15 | Shadab.pinitod |  | Core switch 1,2 config | nitheesh | Medium | 2026-10-15 | New requirements | 2026-10-15 | Closed | config completed
P-1744 |  | 2026-10-15 | Shadab.pinitod |  | Inside fw 1,2 config with HA | nitheesh | Medium | 2026-10-15 | New requirements | 2026-10-15 | Closed | config completed
P-1547 |  | 2026-10-15 | Marimuthu |  | Time issue | Niteesh | Medium | 2026-10-15 | Network cabe connection error |  | Closed | Issue resolved
P-1749 |  | 2026-10-15 | Marimuthu |  | Scada not pinking
P-2022 |  | 2026-10-15 | Mayur Tisage |  | EMS servers not pinging and ssh | Niteesh | Medium | 2026-10-15 |  | 2026-10-15 | Closed | found out the issue and resolved, but root cause I asked yuan to check
P-1887 |  | 2026-10-15 | Mayur Tisage |  | Scada Core switch ips not pinging | Niteesh | medium | 2026-10-15 |  | 2026-10-15 | Closed | Ip configuration missing
P-1744 |  | 2026-10-15 | Shadab.pinitod |  | Third party fw 1,2 config with HA | Niteesh | medium | 2026-10-15 | New requirements | 2026-10-15 | Closed | config completed
P-1744 |  | 2026-10-15 | Shadab.pinitod |  | time server config | Niteesh | medium | 2026-10-15 | New requirements | 2026-10-15 | Closed | config completed
K-0410 |  | 2026-10-15 | Ashok |  | upper firewall A,B | Niteesh | medium | 2026-10-15 | New requirements | 2026-10-15 | Closed | config completed
K-0410 |  | 2026-10-15 | Ashok |  | DMZ FIREWALL | Niteesh | medium | 2026-10-15 | New requirements | 2026-10-15 | Closed | config completed
K-0410 |  | 2026-10-15 | Ashok |  | internet firewall | Niteesh | medium | 2026-10-15 | New requirements | 2026-10-15 | Closed | config completed
K-0410 |  | 2026-10-15 | Ashok |  | time server | Niteesh | medium | 2026-10-15 | New requirements |  | Ongoing | defaul ip not reachable
K-0410 |  | 2026-10-15 | Ashok |  | ssl vpn | Niteesh | medium | 2026-10-15 | New requirements |  | Ongoing | waiting for the public ip
P-1511 |  | 2026-10-16 | Marimuthu |  | SSH issue | Niteesh | medium | 2026-10-16 | Network cabe connection error |  | Closed | Issue resolved
P-1873 |  | 2026-10-16 | Marimuthu |  | NTP time issue | Niteesh | medium | 2026-10-16
P-1856 |  | 2026-10-16 | Mayur Tisage |  | NTP time issue | Manjunath | Medium | 2026-10-16 |  |  | Closed | Issue resolved
P-1744 |  | 2026-10-16 | Mayur Tisage |  | Scada server configuration | Niteesh | Medium | 2026-10-16 |  |  | Closed | config completed
P-1744 |  | 2026-10-16 | Mayur Tisage |  | EMS server configuration | Niteesh | Medium | 2026-10-16 |  |  | Closed | config completed
P-1744 |  | 2026-10-16 | Mayur Tisage |  | PPC server configuration | Niteesh | Medium | 2026-10-16 |  |  | Closed | config completed
P-1615 |  | 2026-10-16 | Shadab.pinitod | Ashok | data forwarding issue | sarita | High | 2026-10-16 |  |  | Closed | now both ports are open
P-1752 |  | 2026-10-16 | Shadab.pinitod |  | Outside 1,2 config | Niteesh | Medium | 2026-10-16 |  |  | Ongoing
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: yang zhu
Note on N127: Marimuthu S(Outsourcing): As per server evething is down Outside firewall WAN 1 is dpwn once up DNS and telent is working need to check Network end.
Note on N207: Marimuthu S(Outsourcing): Before, it was showing UTC time. After checking and resolving the issue, it is now showing IST time.

## Hardware failure
P-code | Date | Device name | Status | Replacement status | Remarks | Supporting Expert
P1429 | 25-3-2026 | Third-party 1 | hardware failure | Completed | completd | Ashok
P1429 | 25-3-2026 | Third-party 2 | hardware failure | Completed | completd | Ashok
P1429 | 25-3-2026 | user-firewall 1 | hardware failure | Completed | completd | Ashok
p-3599 | 25-3-2026 | Third-party 1 | hardware failure | Completed | completd | Ashok
p-3599 | 25-3-2026 | user-firewall 1 | hardware failure | Completed | completd | Ashok
p-1707 | 16-4-2026 | outside fw2 | booting issue | ongoing | need OEM expert support | ashok/jun
P-1576 | 22-4-2026 | Front end server 2 | Raid Controller damaged | ongoing | new server in transit | Mayur
P-8004 | 21-4-2026 | WTG Health Back end server | HDD Failure | ongoing |  | Mayur
P-1631 | 29-4-2026 | outside fw2 | booting issue | fixed | use Firmware IOS file fixed | Ashok/Qiang Wang/PanJie(CKP)
P-1453 | 2026-05-14 | Delta UPS | Short circuit | On going logg calle | need OEM expert support | Nitheesh
P-1812 |  | Core switch 2 bdcom | hardware failure | ongoing | need OEM expert support
P-1566 |  | Core switch 4 cisco | OS issue | ongoing | need OEM expert support
P-8003 |  | Raid failure | Zone1 Gailileo server raid card faiure | Completed | Need site team to raise the case
P-1566 | 2026-06-04 | 1HDD Failure | hardware failure | On going logg calle | Need spares | Revappa
P-1615 |  | 1HDD Failure | hardware failure | On going logg calle | Need spares | Revappa | fixed, power units
p-1729 | 24/7/2026 | keymond | hardware failure | congoing | replace | Ashok
p-1451 | 3/8/2026 | mexon | hardware failure | ongoing | replace | Ashok
P-1436 | 31/09/2026 | Time server Antena | Harware Missing | ongoing | Need to order | Ashok/Mayur
p-1707 | 14/09/2026 | Galileo Server Raid card faile down | hardware failure | Completed | replaced with backup server, change harddisk | Qiang.Wang/Mayur
P-1480 |  | WTG BE Server failure |  |  |  | Annath/Mari

## Galileo Caes Process
项目号 Project ID | CaseID | 填表日期 Filled_Date | 问题提出人 Requester | 当前卡点责任人 Case Owner | 问题描述和进展 Description and Process | 优先级 Priority | 期望解决日期 Expected Resolved Time | 基础架构跟进与反馈 Infra related update | 状态 Status(Ongoing/pending CX/Closed) Confirm/Fill by Galileo Team | 问题根因 RCA | 解决方案 Resolution | 实际完成时间 Real Completed Time | 处理周期 Period
P-8003 |  | 8/31/2026 | rongrong.huang | Yuan.Qin | Install the CMS Linux image version 1.3 | high | 9/4/2026 | 9.8- 1) Mayur will follow up with the site engineer 2) 9.11, please update the status on this friday 3）The pen drive arrive at the site on 2026.09.14 4）The pen drive arrive at the site on 2026.09.14, network conenction need help provide support from site person , next update "9-20" 5）The cms has reinstalled this case is completed | Confirmed by Rongrong. Closed |  |  |  | #VALUE!
P-1480 |  | 8/31/2026 | rongrong.huang | Nitheesh | Root cause analysis and solution for frequent server shutdowns after enabling auto-start on boot | high | 9/11/2026 | Site having power supply issue auto start enabled the server shutdown multiple times update: Dual power restored, keep monitoring for serval days | Confirmed by Rongrong. Closed
P-1578 |  | 9/1/2026 | Sangappa | Mayur | the data vm can not connect to cloud | high | 9/6/2026 | Telnet issue resolved, for dns network team is checking 9.8 Site team still not sharing the remote control. 9.10 Mayur will update the status 9.15, issue fixed, root cause "Telnet 6666 not reachable", Sangappa need continue configure for whole delivery | Confirmed by Rongrong. Closed
P-1741 |  | 9/1/2026 | Sangappa | Mayur/Customer | the data vm can not connect to cloud | high | 9/13/2026 | Public IP not reachble ---PC is still pending configuration（Yuan.Qin and Yuechao.Chen） 9.11 Yuan.QIn push site engineer to share the rmeote session. 9.15 Public issue fixed and case closed | Confirmed by Rongrong. Closed
P-1546 | 1 | 9/1/2026 | Sangappa | Marimuthu/Customer | the data vm can not connect to cloud | Mid | 9/15/2026 | Public IP not reachble----Pending Now the issue was resolved temporarily Via PC to upload data. 9.10--Push customer again to fix public issue. Marimuthu 9.15 Still need chase with Customer, Infra continue follow up 9.22 Please follow up with CX again. 9.29 Please follow up with CX again in teams group 10.13 Nitheesh will follow up | Still remote is not provided
| 2 | 2026-01-08 |  | Shadab | 9.18 3台风机无法ping通，但是Scada显示风机运行正 常，需基础架构排查 Three of the fans are unable to be pinged, but the Scada system indicates that the fans are operating normally. Need Infra investigation | high | 2026.9.28 | From core switch, the PC cannot ping WTG（10.1.） Totally 3 WTG need to troubleshoot the communication issue.(Nitheesh) 9.29 Shadab continuely follow up 10.13 Nitheesh will arrange the site to troubleshoot | 无CMS数据
P-1660 |  | 9/1/2026 | Sangappa | Mayur | s | high | 9/17/2026 | Completed. Please Rongrong to confirm data uploading status.---Pending 9.15 case closed | Confirmed by Rongrong. Closed | DNS Missing | DNS Added in both front end and backend serverand Telnet Restored
P-1660 | (repeated with above) | 2026-01-13 |  | Infra | 9.15部署完成，由于伽利略app虚机异常，数据 9.15 无法解析，基础架构处理中 Galileo deployment completed. However, due to an anomaly in the Galileo app VM, the data cannot be parsed. The infrastructure is currently being processed. | high | 2026.9.25 | Confirmed by Rongrong. Closed | Confirmed by Rongrong. Closed
P-1660 |  | 9/15/2026 | rongrong.huang | Mayur | Galileo app server show blank | high | 9/18/2026 | 1)9.15 Infra will check root case and fix | Confirmed by Rongrong. Closed
P-1610 |  | 9/1/2026 | Sangappa | Marimuthu | the data vm can not connect to cloud | mid | 9/25/2026 | Completed. However, there is currently an internet fluctuation issue at the customer end. ---- 1) Follow up with CX frequently.---Deliver the risk without Internet to CX. 2) For any sites with Internet connetion, check whether there is any available idle PC to reinstall dual-OS. （250 G9; 250R G10） 9.14---Checklist Script 9.15 Public issue fixed, Sanggeppa continue follow up next configuration 9.22 Please Sangappa confirm the issue is resolved or not 9.29 will update process end of today | Confirmed by Sangappa. Closed |  | Fixed DNS issue
P-1812 | 1 | 9/1/2026 | wu.hongxia | Mayur | checklist for all Galileo server | high | 9/3/2026 | WTG server has been installed, waiting for firewall issue to get resolved for checklist, also vga cable not in the site data vms 9.16--- Need to confirm why so long with Mayur 9.15 next update will at 9.18 9.18 the site guy hasn't arrived at the site, 9.22 Qinyuan will reconfigure the Zone2 Servers | 进行中
| 2 | 2026-05-30 |  | Infra | 服务器未安装系统，近期安装完成，待部署 OS installation was completed recently and is awaiting Galileo deployment. | high | 2026.9.25 | 9.22 1. Zone 1 server is correct like IP and password. 2. But Zone2 Server seems from another site. Please @Yuan.Qin change IP/Password as correct with checklist 9.30 update 10.13 Junjie has finished the OS deployment. Waiting Galileo team to deploy App. | Waiting Galileo team to deploy App.
P-1962 |  | 9/1/2026 | wu.hongxia | Mayur | checklist for all Galileo server | high | 9/15/2026 | Completed from server end. For DNS issue network team need to check 9.10---Discuss with Network engineer. Mayur 9.15 Infra team need check network connection issue 9.22 Yuan has been resolved from his site, just @Sangappa double confirm again. 10.13 Remote connection issue. Waiting site to provide remote access. Mayur will continue follow up (NTP, Telnet, DNS)
P-1731 | 1 | 9/1/2026 | wu.hongxia | Marimuthu | checklist for all Galileo server | mid | 9/30/2026 | Completed. However, there is currently an internet fluctuation issue at the customer end. ---- 1) Follow up with CX frequently.---Deliver the risk without Internet to CX. 2) For any sites with Internet connetion, check whether there is any available idle PC to reinstall dual-OS. （250 G9; 250R G10） 9.14---Checklist Script 9.15 Public issue fixed, Sanggeppa continue follow up next configuration 9.22 Please Sangappa confirm the issue is resolved or not 9.29 Galileo data server issue was pending need follow up
| 2 | 2026-07-23 |  | Galileo | 基础架构已装机&伽利略待部署 Infra finished OS installation & pending Galileo deployment | high |  | 9.29 Galileo data server hvaing the neywork. NTP, DNS issues 10.13 Infra team has fixed the related issue. Please Sangappa double check. | 10.13 Infra team has fixed the related issue. Please Sangappa double check.
P-1725 |  | 9/7/2026 | rongrong.huang | Marimuthu | nfs issue， mount disconnect | high | 9/11/2026 | Issue resolved 9.22 Please Sangappa confirm the issue is resolved or not | Confirmed by RongRong. Closed |  | I checked the log details and identified that the watchdog issue caused the NFS mount to disconnect.
P-1479 |  | 9/14/2026 | rongrong.huang | Mayur | Galileo back end server start failed | high | 9/18/2026 | Issue checked, time syching issue need to check software team, routes has been added in both Scada and WTG, but firewall side routes need to add from Network team. 9.15 Infra team continue follow up | Confirmed by RongRong. Closed
P-1486 |  | 9/14/2026 | rongrong.huang | Marimuthu | WTG Health front end server is in OFF condition, check the RC and auto start | high | 9/18/2026 | Currently, the server was restarted and showed a power off status because the auto power option was not enabled. We have now enabled the auto power option, and the server is working properly. 9.15 Infra team continue follow up | Confirmed by RongRong. Closed |  | Currently, the server was restarted and showed a power off status because the auto power option was not enabled. We have now enabled the auto power option, and the server is working properly.
P-1707 |  | 9/15/2026 | rongrong.huang | qiang.wang/Sangeppa | WTG Health back end server is not reachable | high | 9/18/2026 | 9.15) waiting site person provide remote support 9.17) Mayur check with site person, backup got the same brand and model with Primary server, take out harddisk and swap, re conf Raid 6, check result 9.18) System restored, waiting check data if uploaded 9.22: Backup Server was running after moved the HDD from Active to Backup server. Next Plan: 1. Please Nitheesh requested new server. 2. For other sites which have broken hardware. | Confirmed by Rongrong. Closed | 9.16The server can not dected harddisk OS image,Slot4 got the issue 1. contact with vendor for repair solution 2,if not possiable will swap back up server as primary (Plan)
P-1576 |  | 9/17/2026 | rongrong.huang | Jun Zhang | telnet s3.ap-south-1.amazonaws.com 443 failed from Galileo data server | mid | 9/25/2026 |  | Confirmed by Rongrong. Closed
P-1653 | 1 | 9/22/2026 | Sangappa | Mayur/Customer | Data cannot be reached. | high | 9/25/2026 | Data cannot be reached. 9.29 Galileo data server issue was pending need follow up | Confirmed by Sangappa. Closed
| 2 | 9/1/2026 | wu.hongxia | Marimuthu | checklist for all Galileo server | high | 9/7/2026 | Site having internet issue 9.10--Push customer again to fix public issue. Marimuthu 9.15 Public issue fixed, need continue follow up by Sangeppa 9.29 Galileo data server issue was pending need follow up | Confirmed by Sangappa. Closed | Currentely the site internet issue going on
P-1478 |  |  |  | Galileo |  |  |  | Confirmed by Rongrong. Closed | Confirmed by Rongrong. Closed
P-1479 | (repeated with above) | 2025-03-31 |  | Infra | 9.18 现场反馈是电源按键问题，目前服务器已经恢复 9.18 Site engineer replied the issue is caused by the power button. Now the server is normal | high |  | Confirmed by Rongrong. Closed | Confirmed by Rongrong. Closed
P-1701 |  | 2025-03-31 |  | Infra | 9.18 现场反馈是电源按键问题，目前服务器已经恢复 9.18 Site engineer replied the issue is caused by the power button. Now the server is normal |  |  | Confirmed by Rongrong. Closed | Confirmed by Rongrong. Closed
P-1511 | 1 | 2025-08-01 |  | Yuan.Qin | 9.18 CMS虚机UTC时间不对，需要基础架构处理 9.18 The UTC time of the CMS VM is incorrect and requires infrastructure processing. | high | 2026.9.25 | 9.22 1. Need to resolve NTP issue firstly. (Yuan.QIn) 9.29 update 10.13 Qinyuan will follow up the NTP issue by 10.16 | 进行中
| 2 | 9/1/2026 | wu.hongxia | Yuan.Qin | reinstall os WTG health Back-end server 2 Hongxia: Install backup server; Switch to Backup server; Run Service on the Backup Server as the main server Communicate with Galileo team before reinstalling Main Server. | mid | 10/15/2026 | Not enough background information 9.14---Follow the server reinstallation Yuan.QIn+Mayur 9.15 Follow the server reinstallation Yuan.QIn 9.18 site guy and Nitheesh haven't responded me, Nitheesh is having vacation,I need site guy to download the os image. 9.22---Send to site (Nitheesh) 9.29 USB reached site and operate installation 10.13 Sangappa and Qinyun will support the backup switch by 10.16 | 进行中
P-1873 |  | 2026-05-01 |  | Infra | 新部署完成，待排查 Galileo new deployed, pending troubleshooting | high |  | 9.29 Galileo server can ping but not access | Confirmed by Sangappa. Closed
P-1578 P-1735 P-1630 | P-1578(repeated with above) | 2026-05-21 |  | Infra | 9.18 反馈公网恢复，但是无法ping通8.8.8.8，需基础架构 排查 9.18 The public network has been restored, but it is not possible to ping 8.8.8.8. Further investigation is required on the infrastructure. | high |  | Confirmed by Rongrong. Closed | Confirmed by Rongrong. Closed
P-1750 |  | 2026-07-30 |  | Infra | 基础架构已装机&伽利略待部署 Infra finished OS installation & pending Galileo deployment | high | 2026.9.25 | Confirmed by Rongrong. Closed | Confirmed by Rongrong. Closed
P-1962 | (repeated with above) | 2026-08-22 |  | Infra | 基础架构已装机&伽利略待部署 Infra finished OS installation & pending Galileo deployment | high |  | Confirmed by Rongrong. Closed | Confirmed by Rongrong. Closed
P-1615 |  | 2026-05-20 | Sangappa | Infra | 基础架构已装机&伽利略待部署 Infra finished OS installation & pending Galileo deployment | high |  | 9.22 DNS issue, Nitheesh will help check. 9.29 waiting site person provide remote support 10.13 Will arrange remote session with site engineer by next Monday | /
P-1848 P-1846 |  | 2026-08-31 |  | Infra | 无wiki信息，需要尽快确认是否安装系统 No wiki information, need to confirm whether OS is installed or not | 1615 |  | 9.22 Data VM cannot be reached. Shadab is working. 9.29 Galileo data server hvaing the neywork. NTP, DNS issues | Confirmed by Sangappa. Closed
P-1576 |  | 2026-10-10 | rongrong.huang |  | Telnet 6666 failed | high | 2026-10-15 | 10.13 Will arrange remote session with site engineer by next Monday